## Dashboard
[Project Name] — Project Tracking Dashboard
Auto-summary from all tracking sheets · Update data in individual sheets
Total Deliverables | Done / Closed | In Progress | Not Started | Open Issues | Open Defects
-132 | 0 | 0 | 187 | 0 | 0
Open Issues | Open Defects | Unanswered Q&As | High/Critical Risks
0 | 0 | 0 | 0
Scope Milestone Status
Stage | Key Deliverable | Deadline | In Charge | Status
Stage 1 | Report 1 (Project Introduction) | Week 1
Stage 2 | SRS v0.9 + Project Management Plan | Week 3
Stage 3 | SDS v1.0 + Test Planning | Week 5
Stage 4 | Implementation Iterations 1–3 | Week 11
Stage 5 | System Test Report + User Guides + UAT | Week 13
Stage 6 | Final Report + Presentation | Week 14
WBS by Iteration
Iteration | Planned Functions | Est. Effort (pts) | Done | In Progress | % Complete
Iteration 1 | 0 | 0 | 0 | 0
Iteration 2 | 0 | 0 | 0 | 0
Iteration 3 | 0 | 0 | 0 | 0
Last updated: [DD/MM/YYYY] ¦ Project: [Project Name] ¦ PM: [Name]

## Scope
Scope — Project Deliverables & Milestones
Track all deliverables by stage · Update Status and Actual Effort each week · % Complete auto-calculated
# | Work Package / Deliverable | In Charge | Est. Effort (pds) | Deadline | % Complete | Status | Actual Effort (pds) | Dependency | Approved By | Notes
Stage 1: Project Initiating (Week 1)
1.1 | Report 1 — Project Introduction | PhuPD | 2 | Week 1 | 100 | Done | 2 |  | Lecturer
Stage 2: Project Planning & Initial Requirements (Weeks 2–3)
2.1 | Report 2 — Project Management Plan v1.0 | PhuPD, HieuLT, TungVPH | 3 | Week 2 | 100 | Done | 3 | 1.1, 2.1 | Lecturer | Planning, roles, timeline, risk, communication, tracking
2.2 | Report 3 — SRS v0.9 (Overall Requirements) | All team | 4 | Week 3 | 100 | Done | 4 | 1.1 | Lecturer | Scope, actors, functional requirements finalized
2.3 | Vertical Prototypes (Code Demo) | BE + FE | 5 | Week 3 | 100 | Done | 5 | 2.1 | Lecturer | Demonstrate a small end-to-end flow to prove the stack works.
Stage 3: Software Design (Weeks 4–5)
3.1 | Vertical Prototypes (POC / Proof of Concepts) | BE + FE | 4 | Week 4 | 100 | Done | 4 | 2.2 | Lecturer | Develop a Proof of Concept (POC) for technical components that involve risk or uncertainty.
3.2 | Report 3 — SRS v1.0 (Detailed — Iteration 1) | All team | 4 | Week 4 | 100 | Done | 4 | 2.1, 3.2 | Lecturer | Detailed requirements for features to be implemented in Iteration 1
3.3 | Report 4 — SDS v1.0 (High Level Design) | PhuPD, HieuLT, TungVPH | 5 | Week 5 | 100 | Done | 5 | 2.1, 2.2 | Lecturer | Architecture, service/module, DB high-level, API/interface, deployment overview
3.4 | Report 5 — Test Planning | PhuPD | 3 | Week 5 | 100 | Done | 3 | 2.1, 3.2 | Lecturer | Test strategy, test types, environment, entry/exit criteria, responsibilities
Stage 4a: Implementation — Iteration 1 (Weeks 6–7)
4.1.1 | Report 4 — SDS v1.1 (Detailed Design) |  |  | Week 6 |  | Not Started
4.1.2 | Code Package & Unit Testing Report — Iteration 1 |  |  | Week 6 |  | Not Started
4.1.3 | Report 5 — Integration Test Cases — Iteration 1 |  |  | Week 6 |  | Not Started
4.1.4 | Report 5 — Integration Test Report — Iteration 1 |  |  | Week 7 |  | Not Started
4.1.5 | Report 3 — SRS v1.1 (Detailed — Iteration 2) |  |  | Week 7 |  | Not Started
4.1.6 | Software Package Version 1 |  |  | Week 7 |  | Not Started
Stage 4b: Implementation — Iteration 2 (Weeks 8–9)
4.2.1 | Report 4 — SDS v1.2 |  |  | Week 8 |  | Not Started
4.2.2 | Code Package & Unit Testing Report — Iteration 2 |  |  | Week 8 |  | Not Started
4.2.3 | Report 5 — Integration Test Cases — Iteration 2 |  |  | Week 8 |  | Not Started
4.2.4 | Report 5 — Integration Test Report — Iteration 2 |  |  | Week 9 |  | Not Started
4.2.5 | Report 3 — SRS v1.2 (Detailed — Iteration 3) |  |  | Week 9 |  | Not Started
4.2.6 | Software Package Version 2 |  |  | Week 9 |  | Not Started
Stage 4c: Implementation — Iteration 3 (Weeks 10–11)
4.3.1 | Report 4 — SDS v1.3 |  |  | Week 10 |  | Not Started
4.3.2 | Code Package & Unit Testing Report — Iteration 3 |  |  | Week 10 |  | Not Started
4.3.3 | Report 5 — Integration Test Cases — Iteration 3 |  |  | Week 10 |  | Not Started
4.3.4 | Report 5 — Integration Test Report — Iteration 3 |  |  | Week 11 |  | Not Started
4.3.5 | Report 5 — System Test Cases |  |  | Week 11 |  | Not Started
4.3.6 | Software Package Version 3 |  |  | Week 11 |  | Not Started
Stage 5: Verification & Validation (Weeks 12–13)
5.1 | Report 5 — System Test Report |  |  | Week 12 |  | Not Started
5.2 | Report 6 — User Guides (Installation + User Manuals) |  |  | Week 12 |  | Not Started
5.3 | Acceptance Test and Support |  |  | Week 13 |  | Not Started
5.4 | Final Software Package (Docs + Source Codes) |  |  | Week 13 |  | Not Started
Stage 6: Closing (Week 14)
6.1 | Report 7 — Final Project Report |  |  | Week 14 |  | Not Started
6.2 | Presentation File |  |  | Week 14 |  | Not Started

## WBS
WBS — Work Breakdown Structure (Function / Screen Level)
Complexity: Simple (≤7 fields / ≤3 tx) · Medium (≤15 / ≤7) · Complex (>15 / >7) · Effort: Simple=3 / Medium=5 / Complex=8 pts (default)
Function / Screen | Type | Feature Group | Sub-Feature | Description | Complexity | Est. Effort (pts) | Planned Iteration | In Charge | Actual Effort (pts) | Status | Notes
Home Page | Non-UI | Common |  | Landing page / entry point | Medium | 5 | Iteration 2 |  |  | Not Started
User Login | Screen | Common |  | Email + password login with JWT | Simple | 3 | Iteration 1 |  |  | Not Started
User Register | Screen | Common |  | New account registration form | Simple | 3 | Iteration 1 |  |  | Not Started
Reset Password | Screen | Common |  | Email OTP-based password reset flow | Medium | 5 | Iteration 3 |  |  | Not Started
User Authorization | Non-UI | Common |  | Role-based access control (RBAC) | Complex | 8 | Iteration 1 |  |  | Not Started
User Profile | Screen | Common |  | View and edit user profile | Simple | 3 | Iteration 3 |  |  | Not Started
Change Password | Screen | Common |  | Change password from profile | Simple | 3 | Iteration 3 |  |  | Not Started
Blog List | Screen | Public |  | Paginated public blog listing | Medium | 5 | Iteration 2 |  |  | Not Started
Blog Details | Screen | Public |  | Single blog post view with comments | Simple | 3 | Iteration 2 |  |  | Not Started
Post List | Screen | Marketing |  | Marketing posts listing with filters | Medium | 5 | Iteration 1 |  |  | Not Started
Post Details | Screen | Marketing |  | Single marketing post detail view | Medium | 5 | Iteration 1 |  |  | Not Started
Users List | Screen | System Admin |  | Admin: list + search all users | Simple | 3 | Iteration 1 |  |  | Not Started
User Details | Screen | System Admin |  | Admin: view + edit single user record | Simple | 3 | Iteration 1 |  |  | Not Started
Iteration Summary
Iteration | Planned Functions | Est. Effort (pts) | Done | In Progress
Iteration 1 | 7 | 30
Iteration 2 | 3 | 13
Iteration 3 | 3 | 11
Grand Total | 13 | 54

## Q&A
Q&A — Project Questions & Answers Log
Log ALL questions — technical, business, process · Track from Open → Answered → Closed · Never delete a row
# | Date | Question | Raised By | Directed To | Priority | Due Date | Answer / Resolution | Answered By | Answered Date | Status | Notes
Q-001 | 2024-01-08 | [Describe the question clearly — what needs clarification?] | KienNT | [Assignee/Stakeholder] | Medium | 2024-01-15 | [Answer provided here] |  |  | Open
Q-002 |  |  |  |  | Medium |  |  |  |  | Open
Q-003 |  |  |  |  | Medium |  |  |  |  | Open
Q-004 |  |  |  |  | Medium |  |  |  |  | Open
Q-005 |  |  |  |  | Medium |  |  |  |  | Open
Q-006 |  |  |  |  | Medium |  |  |  |  | Open
Q-007 |  |  |  |  | Medium |  |  |  |  | Open
Q-008 |  |  |  |  | Medium |  |  |  |  | Open
Q-009 |  |  |  |  | Medium |  |  |  |  | Open
Q-010 |  |  |  |  | Medium |  |  |  |  | Open
Q-011 |  |  |  |  | Medium |  |  |  |  | Open
Q-012 |  |  |  |  | Medium |  |  |  |  | Open
Q-013 |  |  |  |  | Medium |  |  |  |  | Open
Q-014 |  |  |  |  | Medium |  |  |  |  | Open
Q-015 |  |  |  |  | Medium |  |  |  |  | Open
Q-016 |  |  |  |  | Medium |  |  |  |  | Open
Q-017 |  |  |  |  | Medium |  |  |  |  | Open
Q-018 |  |  |  |  | Medium |  |  |  |  | Open
Q-019 |  |  |  |  | Medium |  |  |  |  | Open
Q-020 |  |  |  |  | Medium |  |  |  |  | Open

## TimeLogs
TimeLogs — Project Timesheets
Log time daily · Link every entry to a WBS Ref · Approved by PM · # Hours must be filled — leave no blank
# | Date | Reporter | WBS Ref | Task Description | Activity | Type | # Hours | Product / Work Product | Iteration | Status | Approved By | Updated | Notes
TL-001 | 2024-10-13 | KienNT | WBS-1 | Set up project repository and CI pipeline | Coding | Newly-Created | 2 | Software Package | Iteration 1 | Submitted |  | 2024-10-26
TL-002 |  | KienNT | WBS-2 | Implement user login API with JWT | Coding | Newly-Created | 4 | Software Package | Iteration 1 | Submitted
TL-003 | [9 empty] | Submitted
TL-004 | [9 empty] | Submitted
TL-005 | [9 empty] | Submitted
TL-006 | [9 empty] | Submitted
TL-007 | [9 empty] | Submitted
TL-008 | [9 empty] | Submitted
TL-009 | [9 empty] | Submitted
TL-010 | [9 empty] | Submitted
TL-011 | [9 empty] | Submitted
TL-012 | [9 empty] | Submitted
TL-013 | [9 empty] | Submitted
TL-014 | [9 empty] | Submitted
TL-015 | [9 empty] | Submitted
TL-016 | [9 empty] | Submitted
TL-017 | [9 empty] | Submitted
TL-018 | [9 empty] | Submitted
TL-019 | [9 empty] | Submitted
TL-020 | [9 empty] | Submitted
TL-021 | [9 empty] | Submitted
TL-022 | [9 empty] | Submitted
TL-023 | [9 empty] | Submitted
TL-024 | [9 empty] | Submitted
TL-025 | [9 empty] | Submitted
TL-026 | [9 empty] | Submitted
TL-027 | [9 empty] | Submitted
TL-028 | [9 empty] | Submitted
TL-029 | [9 empty] | Submitted
TL-030 | [9 empty] | Submitted
TL-031 | [9 empty] | Submitted
Hours Summary
Activity | Total Hours
Training | 0
Analyzing | 0
Designing | 0
Coding | 6
Testing | 0
Reviewing | 0
Deploying | 0
Meeting | 0
Grand Total | 6

## Defects
Defects — Bug & Defect Tracking Log
Log ALL defects found in any review or test · Severity: Critical / High / Medium / Low · Status: Pending → Open → Fixed → Closed
# | Date Found | Defect Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Activity | Product | Product Details | Assigned By | Assigned To | Status | Fixed Date | Fixed In Version | Updated | Notes
D-001 | 2024-10-13 | [Describe the defect clearly] | [Step 1: ... Step 2: ...] | [What should happen] | [What actually happened] | Medium | Medium | Review | Software Package |  | KienNT | [Assignee] | Pending |  |  | 2024-10-26
D-002 | [5 empty] | Medium | Medium | [5 empty] | Pending
D-003 | [5 empty] | Medium | Medium | [5 empty] | Pending
D-004 | [5 empty] | Medium | Medium | [5 empty] | Pending
D-005 | [5 empty] | Medium | Medium | [5 empty] | Pending
D-006 | [5 empty] | Medium | Medium | [5 empty] | Pending
D-007 | [5 empty] | Medium | Medium | [5 empty] | Pending
D-008 | [5 empty] | Medium | Medium | [5 empty] | Pending
D-009 | [5 empty] | Medium | Medium | [5 empty] | Pending
D-010 | [5 empty] | Medium | Medium | [5 empty] | Pending
D-011 | [5 empty] | Medium | Medium | [5 empty] | Pending
D-012 | [5 empty] | Medium | Medium | [5 empty] | Pending
D-013 | [5 empty] | Medium | Medium | [5 empty] | Pending
D-014 | [5 empty] | Medium | Medium | [5 empty] | Pending
D-015 | [5 empty] | Medium | Medium | [5 empty] | Pending
D-016 | [5 empty] | Medium | Medium | [5 empty] | Pending
D-017 | [5 empty] | Medium | Medium | [5 empty] | Pending
D-018 | [5 empty] | Medium | Medium | [5 empty] | Pending
D-019 | [5 empty] | Medium | Medium | [5 empty] | Pending
D-020 | [5 empty] | Medium | Medium | [5 empty] | Pending
D-021 | [5 empty] | Medium | Medium | [5 empty] | Pending
D-022 | [5 empty] | Medium | Medium | [5 empty] | Pending
D-023 | [5 empty] | Medium | Medium | [5 empty] | Pending
D-024 | [5 empty] | Medium | Medium | [5 empty] | Pending
D-025 | [5 empty] | Medium | Medium | [5 empty] | Pending
D-026 | [5 empty] | Medium | Medium | [5 empty] | Pending
D-027 | [5 empty] | Medium | Medium | [5 empty] | Pending
D-028 | [5 empty] | Medium | Medium | [5 empty] | Pending
D-029 | [5 empty] | Medium | Medium | [5 empty] | Pending
D-030 | [5 empty] | Medium | Medium | [5 empty] | Pending

## Issues
Issues — Project Issues & Risk Events Log
Issues = problems that have already occurred · Risks = problems that might occur (see Risks sheet) · Category: Technical / Process / Resource / Scope / External
# | Date | Issue Description | Category | Priority | Impact (Scope / Effort / Timeline) | Raised By | Owner | Due Date | Resolution | Status | Closed Date | Notes
I-001 | 2024-10-13 | [Describe the issue — what happened and what is the impact?] | Technical | Medium | [Impact on scope / effort / timeline — e.g. delays Iteration 2 by 3 days] | KienNT | HuyNMG |  | [Resolution steps taken or planned] | Open
I-002 |  |  |  | Medium | [5 empty] | Open
I-003 |  |  |  | Medium | [5 empty] | Open
I-004 |  |  |  | Medium | [5 empty] | Open
I-005 |  |  |  | Medium | [5 empty] | Open
I-006 |  |  |  | Medium | [5 empty] | Open
I-007 |  |  |  | Medium | [5 empty] | Open
I-008 |  |  |  | Medium | [5 empty] | Open
I-009 |  |  |  | Medium | [5 empty] | Open
I-010 |  |  |  | Medium | [5 empty] | Open
I-011 |  |  |  | Medium | [5 empty] | Open
I-012 |  |  |  | Medium | [5 empty] | Open
I-013 |  |  |  | Medium | [5 empty] | Open
I-014 |  |  |  | Medium | [5 empty] | Open
I-015 |  |  |  | Medium | [5 empty] | Open
I-016 |  |  |  | Medium | [5 empty] | Open
I-017 |  |  |  | Medium | [5 empty] | Open
I-018 |  |  |  | Medium | [5 empty] | Open
I-019 |  |  |  | Medium | [5 empty] | Open
I-020 |  |  |  | Medium | [5 empty] | Open

## Risks
Risks — Risk Register & Mitigation Tracking
Probability: High(3) / Medium(2) / Low(1) · Impact: High(3) / Medium(2) / Low(1) · Risk Score = P × I · Score ≥ 6 = Critical; 4-5 = High; 2-3 = Medium; 1 = Low
# | Risk Description | Category | Probability | Impact | Risk Score (P×I) | Mitigation Plan | Contingency Plan | Owner | Due Date | Status | Notes
R-001 | Channel API approval (Facebook/Zalo app review) delayed — dev cannot test real channel integration | External | Medium | High | 6 | Start approval process in Week 1; use mock/test accounts during development | Continue with mock channels; adjust timeline for Iteration 2 | PM | Week 2 | Open
R-002 | Key team member unavailable (illness, withdrawal) mid-project | Resource | Low | High | 3 | Cross-train all members on critical modules; maintain shared knowledge base | Reassign tasks; PM escalates to instructor if unresolvable | PM |  | Open
R-003 | Requirements change after SRS v1.0 is approved (scope creep) | Scope | Medium | Medium | 4 | Strict change control: all changes go through ChangeLog; no mid-sprint changes | Negotiate scope with PO; defer low-priority features to later iteration | PM |  | Open
R-004 | Integration with third-party API (payment/courier) fails in sandbox | Technical | Medium | Medium | 4 | Implement WireMock stubs for all external API calls; test independently | Use manual entry fallback; document limitation in final report | Tech Lead |  | Open
R-005 | Performance targets not met (slow response at peak load) | Technical | Low | Medium | 2 | Performance testing starts Iteration 3; add DB indexes early | Scope down concurrent user target; document as known limitation | Tech Lead | Week 10 | Open
R-006 | UAT findings require significant rework, delaying go-live | Quality | Medium | High | 6 | Involve PO in every Sprint Review; demo features every 2 weeks | Prioritise P1 fixes; negotiate deferred fixes for post-go-live | PM | Week 13 | Open
R-007 |  |  | Medium | Medium | [5 empty] | Open
R-008 |  |  | Medium | Medium | [5 empty] | Open
R-009 |  |  | Medium | Medium | [5 empty] | Open
R-010 |  |  | Medium | Medium | [5 empty] | Open
R-011 |  |  | Medium | Medium | [5 empty] | Open
R-012 |  |  | Medium | Medium | [5 empty] | Open
R-013 |  |  | Medium | Medium | [5 empty] | Open
R-014 |  |  | Medium | Medium | [5 empty] | Open
R-015 |  |  | Medium | Medium | [5 empty] | Open

## ChangeLog
ChangeLog — Requirement & Scope Change Tracking
Log ALL changes to requirements, design, or scope · No mid-sprint changes without approval · Reference this log when versions of SRS/SDS increment
# | Date | Change Description | Requested By | Affects (SRS/WBS/Code) | Impact on Scope | Impact on Effort (pds) | Impact on Timeline | Priority | Approved By | Status | Notes
C-001 | 2024-01-08 | Add 'Forgot Password via OTP' feature to SRS — not in original scope | KienNT | SRS v1.0 Section 3, WBS #4 | Add Reset Password screen (WBS #4) | +3 pds | Delay Iteration 1 by 3 days | Medium | [Approver] | Pending | Moved to Iteration 3 to reduce risk
C-002 | [7 empty] | Medium |  | Pending
C-003 | [7 empty] | Medium |  | Pending
C-004 | [7 empty] | Medium |  | Pending
C-005 | [7 empty] | Medium |  | Pending
C-006 | [7 empty] | Medium |  | Pending
C-007 | [7 empty] | Medium |  | Pending
C-008 | [7 empty] | Medium |  | Pending
C-009 | [7 empty] | Medium |  | Pending
C-010 | [7 empty] | Medium |  | Pending
C-011 | [7 empty] | Medium |  | Pending
C-012 | [7 empty] | Medium |  | Pending
C-013 | [7 empty] | Medium |  | Pending
C-014 | [7 empty] | Medium |  | Pending
C-015 | [7 empty] | Medium |  | Pending
C-016 | [7 empty] | Medium |  | Pending
C-017 | [7 empty] | Medium |  | Pending
C-018 | [7 empty] | Medium |  | Pending
C-019 | [7 empty] | Medium |  | Pending
C-020 | [7 empty] | Medium |  | Pending