Project Management Plan

English Learning and IELTS Preparation Support System Based on Personalized Learning Pathways for IELTS Space

- Report 2 -

| Project Name | English Learning and IELTS Preparation Support System Based on Personalized Learning Pathways for IELTS Space |
| --- | --- |
| Vision & Scope Ref | Report 1 – Vision & Scope v1.1.0 (09/10/2026) |
| RTW Ref | Report 3.1 – Requirements Traceability Workbook v1.0.1 |
| Plan Version | v1.1.0 |
| Date Created | 14/09/2026 |
| Last Updated | 09/10/2026 |
| Author(s) | HieuLT, SonLH, HoangNV, TungVPH, PhuPD |
| Reviewer(s) | LinhNDM |
| Status | In Review |

1. Overview

1.1 Cost/Time Estimation

| # | Work Package | Est. Effort (wds) | Deadline |
| --- | --- | --- | --- |
| Stage 1: Project Initiating (Week 1) |  |  |  |
| 1.1 | Finalize the website scope, assign team members, define service responsibilities and complete Report 1. | 2 | Week 1 |
| Stage 2: Project Planning & Initial Requirements (Weeks 2–3) |  |  |  |
| 2.1 | Report 2: Project Management Plan v1.0 | 3 | Week 2 |
| 2.2 | Report 3: SRS – Overall Requirements, User Roles, and Key Functionality | 4 | Week 2 |
| 2.3 | Vertical Prototype – Demo code: create the backend structure and the website; send a request from the interface through the Gateway to a service and receive the response. | 5 | Week 3 |
| Stage 3: Software Design (Weeks 4–5) |  |  |  |
| 3.1 | Vertical Prototype – POC: Testing database connectivity and RabbitMQ communication. | 4 | Week 4 |
| 3.2 | Report 3 – SRS v1.0: complete the functional and non-functional requirements, scenarios, business rules and data requirements, with Report 3.1 RTW, Report 3.2 FDS and Report 3.3 Screen Design Specification. | 4 | Week 4 |
| 3.3 | Report 4 – TDS v1.0, overall design: microservice architecture, physical data model of each service, APIs, events and website structure, drawn with Draw.io. | 5 | Week 5 |
| 3.4 | Report 5 – Test Plan: scope, environment, data, test levels and completion criteria for the backend and the website. | 3 | Week 5 |
| Stage 4: Implementation (Weeks 6–11) |  |  |  |
| 4.1 Implementation Iteration 1 (Weeks 6–7) |  |  |  |
| 4.1.1 | Report 4 – TDS v1.1: detailed design of the User, Content and Learning services: learner profile, learning goal, courses, topics, lessons, the course-based learning path and progress; basic access rights in the Access service. | 4 | Week 6 |
| 4.1.2 | Code Package & Unit Testing Report: sign-in, profile and learning goal; courses, topics and lessons; the course-based learning path and the optional placement test; learners open a lesson, submit exercises and save progress; website integration and unit tests. | 32 | Week 6 |
| 4.1.3 | Report 5 – Integration Test Cases: sign in → set a learning goal → open a course → study a lesson → practice and review → save progress; check data ownership. | 4 | Week 7 |
| 4.1.4 | Report 5 – Integration Test Report: run the first test round, record the results, fix defects and retest. | 6 | Week 7 |
| 4.1.5 | Report 3 – SRS v1.1: Iteration 2 requirements – topic and course tests, AI and examiner grading, results, personal library and notifications. | 4 | Week 7 |
| 4.1.6 | Software Package Version 1: learners sign in, set a learning goal, study the lessons of a course and view their progress. | 2 | Week 7 |
| 4.2 Implementation Iteration 2 (Weeks 8–9) |  |  |  |
| 4.2.1 | Report 4 – TDS v1.2: detailed design of the Assessment, Library and Notification flows: APIs, data and RabbitMQ events. | 3 | Week 8 |
| 4.2.2 | Code Package & Unit Testing Report: topic and course tests, AI and examiner grading, results and knowledge-point evidence linked to the Learning service; vocabulary and video catalogs, flashcards, decks, notes, video progress, saved segments and notifications; website integration and unit tests. | 34 | Week 8 |
| 4.2.3 | Report 5 – Integration Test Cases: take a test → submit → result → learning progress updated; save to the personal library and receive notifications through RabbitMQ. | 4 | Week 8 |
| 4.2.4 | Report 5 – Integration Test Report: run the second test round; verify results, progress and the library, and handle errors and duplicate events. | 6 | Week 9 |
| 4.2.5 | Report 3 – SRS v1.2: Iteration 3 requirements – mastery and review refinements, plans and activation keys, points, games and community. | 4 | Week 9 |
| 4.2.6 | Software Package Version 2: the course-based learning path with topic and course tests, results, the personal library and notifications. | 2 | Week 9 |
| 4.3 Implementation Iteration 3 (Weeks 10–11) |  |  |  |
| 4.3.1 | Report 4 – TDS v1.3: complete the Access service; design the Game and Community services. | 3 | Week 10 |
| 4.3.2 | Code Package & Unit Testing Report: activity and streak; plans, subscriptions, activation keys and points; game rooms, game sessions and WebSockets; posts, comments and moderation; website and unit tests. | 32 | Week 10 |
| 4.3.3 | Report 5 – Integration Test Cases: Premium access by plan, points, game sessions and community flows. | 5 | Week 10 |
| 4.3.4 | Report 5 – Integration Test Report | 6 | Week 11 |
| 4.3.5 | Report 5 – System Test Cases: system-wide test cases, giving priority to the personalised learning flow on the website and its supporting functions. | 5 | Week 11 |
| 4.3.6 | Software Package Version 3: every function in the development scope is delivered and the system is ready for system testing. | 2 | Week 11 |
| Stage 5: Verification & Validation (Weeks 12–13) |  |  |  |
| 5.1 | Report 5 – System Test Report: test the whole system, access control, basic performance and the website; fix first the defects that block the learning path, lessons and progress saving. | 12 | Week 12 |
| 5.2 | Report 6 – User Guides: installation, configuration and use – choosing a course, studying lessons, taking tests and tracking progress. | 5 | Week 12 |
| 5.3 | Acceptance Test and Support: run the user workflows with IELTS Space, collect feedback, fix defects and check the acceptance criteria. | 10 | Week 13 |
| 5.4 | Final Software Package: hand over the software, source code, configuration, documents and test results; check that it can be installed again. | 4 | Week 13 |
| Stage 6: Closing (Week 14) |  |  |  |
| 6.1 | Report 7 – Final Project Report: results against the goals, actual effort, limitations and future work. | 4 | Week 14 |
| 6.2 | Presentation and demonstration | 4 | Week 14 |

1.2 Project Objectives

| # | Metric | Unit | Planned | Actual | Notes / References |
| --- | --- | --- | --- | --- | --- |
| 1 | The MVP function acceptance scenario meets the requirements. | % | 100% of test cases in the Must-Pass category must pass; the pass rate for all test cases undergoing acceptance testing must be at least 95%; at the time of acceptance testing, there should be no Critical or High level defects remaining in an unprocessed state. |  | Test results and bug list |
| 2 | Security testing meets requirements. | % | 100% of required security test cases passed; no critical/high-level vulnerabilities remained unpatched upon acceptance. This included testing authentication and authorization, data access, SQL Injection/XSS, password and sensitive data protection, security configuration, and anti-guessing measures. |  | Security test report, vulnerability list, and fix results. |
| 3 | API response speed | Time | 95% of primary requests that do not call the LLM respond within ≤ 2 seconds with 100 concurrent users (SRS NFR-P01). |  | Load test results |
| 4 | Active learners during the beta | Learners | ≥ 200 IELTS Space students use the system in the last 4 weeks of the beta (needs a hosted environment, RTW OI-15). |  | Website statistics |

1.3 Project Risks

| # | Risk Description | Impact | Possibility | Priority | Response Plans (Mitigation / Contingency) |
| --- | --- | --- | --- | --- | --- |
| 1 | The adaptive learning rules (mastery, practice gates and the review ladder) take longer to build and test than planned, which delays the main learning flow. | H | M | H | Mitigation: build the main flow first (lesson → practice → review → topic test) and test the gates early with seed data. Contingency: keep the simpler review rule of the current release and move refinements to the next iteration. |
| 2 | AI grading of Writing essays gives bands that do not match the IELTS criteria, or costs more than planned. | H | M | H | Mitigation: compare AI bands with essays graded by the centre’s teachers; cap gradings per day and charge points (NFR-SEC13). Contingency: hand test essays to an examiner when the AI fails or the daily limit is reached (BR-39). |
| 3 | The team underestimates the work and misses deadlines. | H | M | H | Mitigation: break tasks down, prioritise features and check progress every week. Contingency: reassign work and move lower-priority features to a later version. |

2. Management Approach

2.1 Project Processes

The team employs an iterative development approach, dividing the work into two-week phases. At the beginning of each phase, the team defines objectives, prioritizes functionalities, and assigns tasks. Throughout the process, members update progress and discuss any difficulties encountered. At the end of each phase, the team integrates, tests, and evaluates the results to adjust the plan for the next phase.

| Management activities | How to do it |
| --- | --- |
| Scope management | Identify the functions in the current version. These functions are prioritized to focus resources on the main requirements. |
| Change management | Requests for adding or modifying functionality are documented and discussed within the team. The team assesses the impact on workload, design, and deadlines before deciding whether to include it in the current development cycle or move it to the next. |
| Time management | Each task has a designated person, deadline, and expected outcome. The team checks progress weekly; tasks at risk of falling behind are reassigned or broken down into smaller parts to minimize impact on related work. |

2.2 Quality Management

The whole team owns quality through analysis, development and testing. Each function requires clear requirements and acceptance criteria so that team members agree on how to implement and evaluate the results.

| Work | How to do it |
| --- | --- |
| Error prevention | Review requirements and design before programming; agree on data structures and APIs between frontend and backend. Anticipate scenarios such as connection loss and multiple submission attempts. |
| Cross-checking | Code is reviewed by at least one other member before being merged into the common branch. The review includes correctness, readability, error handling, and access control checks. |
| Unit testing | Test critical logic such as scoring answers, submission status, saving results and the learning-path gates. |
| Integration and functional testing | Check the workflow from selecting the topic, completing the assignment, submitting it, transferring to the chosen grading method, and viewing the results. Also check the course flow: choose a course, study lessons, clear practice and the topic test, and update progress. |
| Code standards | Maintain consistency in naming conventions, directory structure, code formatting, and API responses. Do not include passwords or service keys in the source code. |
| Defect management and acceptance testing | Record each defect with the steps to reproduce, the severity and the owner. The error is re-tested after being fixed. The functionality is only considered complete when it meets the acceptance criteria and there are no more critical errors affecting the main workflow. |

2.3 Project Training Plan

The team organizes internal training and practice sessions to enhance knowledge of microservices architecture, inter-service communication, and system deployment. The practice content is linked to the functionalities of the IELTS platform so that members can directly apply it to their projects.

| Training Area | Participants | When / Duration |
| --- | --- | --- |
| Microservices architecture: Segmenting services, defining responsibilities for each service, and managing data separately. | All members | Week 1 / 1 session, 2 hours |
| Communication between services: REST API, OpenFeign, handling timeouts and errors when dependent services are unresponsive. | Backend members | Week 2 / 2 sessions, 1 hour each |
| Security in microservices: JWT, Gateway authentication, service-specific authorization, and internal API protection. | Backend members | Week 2 / 2 sessions, 2 hours each |
| RabbitMQ: Producer, consumer, exchange, queue; handling asynchronous operations, retrying, error queuing, and avoiding duplicate message processing. Practice the workflow of sending requests, parsing work, and receiving results. | Backend members | Week 3 / 2 sessions, 2 hours each |

3. Responsibility Assignments

The matrix uses RACI: R = Responsible (does the work), A = Accountable (owns and approves the result; one per work package), C = Consulted (gives input before the work is done), I = Informed (kept up to date). A/R means the same member is accountable and does the work.

| Work Package | PhuPD | HieuLT | SonLH | HoangNV | TungVPH |
| --- | --- | --- | --- | --- | --- |
| 1.1 Report 1 – Vision & Scope | C | A/R | C | C | R |
| Report 2.0 – Project Management Plan | R | A | I | I | R |
| Report 2.1 – Project Tracking | C | A/R | I | I | R |
| 2.2, 3.2 Report 3 – SRS & requirements traceability | C | A/R | R | R | R |
| 2.3, 3.1 Vertical prototype & POC | C | A/R | R | R | C |
| 3.3 Report 4 – TDS (architecture, database, API, events) | R | A/R | C | C | R |
| 3.4 Report 5 – Test Plan | R | A | C | R | R |
| Infrastructure: Config Server, Eureka, Gateway, Docker, PostgreSQL, RabbitMQ | C | A/R | I | I | C |
| User Service: accounts, authentication, profile, activity & streak | C | A/R | C | C | C |
| Content & Library Services: topics, lessons, questions, vocabulary, video | C | A/R | I | I | R |
| Learning Service: course path, practice, review, mastery | C | A/R | C | C | C |
| Assessment & Access Services: tests, grading, activation keys, points | R | A | I | C | C |
| Game, Community & Notification Services | R | A | C | C | R |
| Website UI | I | A | R | R | I |
| Frontend–backend integration: main learning flow, auth, practice, review | C | A | R | R | C |
| Integration & system testing, defect tracking | R | A/R | R | R | R |
| 5 Verification & acceptance: system test report, user guides, UAT | R | A/R | R | R | R |
| 6 Closing: final report & presentation | R | A/R | R | R | R |

4. Project Communications

| Communication Item | Who / Target | Owner | Purpose | When / Frequency | Type / Tool |
| --- | --- | --- | --- | --- | --- |
| Team meeting | All members | Project Lead | Progress, blockers and decisions | Twice a week | Google Meet; minutes in Excel |
| Client meeting | IELTS Space representative + team | Project Lead | Requirements, demo and feedback | Weekly | Google Meet; minutes in Excel |
| PR / test review | Developer + QA | Package owner | Review code, test results, and acceptance criteria | Per package | GitHub pull request + GitHub Actions CI + Project Tracking (Report 2.1) |

5. Configuration Management

5.1 Document Management

All project documents, including reports, requirements specifications, design documents, and test documents, will be stored in a shared folder on Microsoft OneDrive. Documents will be organized into subfolders by document type and project phase.

5.2 Source Code Management

The backend source code is managed using Git and centrally stored in a GitHub repository. Microservices are organized into separate folders under the services directory, which keeps each service’s code separate and makes development and maintenance easier. Changes are made on a feature or fix branch; a pull request is reviewed by at least one member and must pass the GitHub Actions build before it is merged into main.

5.3 Tools & Infrastructure

| Category | Tools / Infrastructure |
| --- | --- |
| Technology | Java 21 and Spring Boot 3.5 for the backend; Spring Cloud for the microservices; React, TypeScript and Vite for the website. |
| Microservices infrastructure | Spring Cloud Gateway, Eureka Service Registry, Spring Cloud Config, OpenFeign; RabbitMQ for events; Docker and Docker Compose. |
| Database | PostgreSQL; separate service-owned databases; Flyway migrations |
| IDEs / Editors | IntelliJ IDEA, Visual Studio Code. |
| Diagramming | Draw.io: to build system architecture diagrams, database diagrams, and diagrams describing functions, interactions, and processing flows. |
| Documentation | Microsoft Word and Excel, stored on Microsoft OneDrive |
| Version Control | Git and GitHub; GitHub Actions for build and tests |
| Deployment Server | Local Docker Compose during development; production hosting not decided yet (RTW OI-15) |
| Project Management | Project Tracking workbook (Report 2.1) and GitHub |