## Dashboard
[Project Name] — Project Tracking Dashboard
Auto-summary from all tracking sheets · Update data in individual sheets
Total Deliverables | Done / Closed | In Progress | Not Started | Open Issues | Open Defects
-132 | 0 | 0 | 187 | 0 | 0
Open Issues | Open Defects | Unanswered Q&As | High/Critical Risks
0 | 0 | 0 | 1
Scope Milestone Status
Stage | Key Deliverable | Deadline | In Charge | Status
Stage 1 | Report 1 (Project Introduction) | Week 1
Stage 2 | SRS v0.9 + Project Management Plan | Week 3
Stage 3 | SDS v1.0 + Test Planning | Week 5
Stage 4 | Implementation Iterations 1–3 | Week 11
Stage 5 | System Test Report + User Guides + UAT | Week 13
Stage 6 | Final Report + Presentation | Week 14
WBS by Iteration
Iteration | Planned Functions | Est. Effort (pts) | Done | In Progress | % Complete
Iteration 1 | 23 | 117 | 11 | 12 | 0.47826
Iteration 2 | 15 | 65 | 6 | 0 | 0.4
Iteration 3 | 26 | 141 | 0 | 0 | 0
Last updated: [DD/MM/YYYY] ¦ Project: [Project Name] ¦ PM: [Name]

## Scope
Scope — Project Deliverables & Milestones
Track all deliverables by stage · Update Status and Actual Effort each week · % Complete auto-calculated
# | Work Package / Deliverable | In Charge | Est. Effort (pds) | Deadline | % Complete | Status | Actual Effort (pds) | Dependency | Approved By | Notes
Stage 1: Project Initiating (Week 1)
1.1 | Report 1 — Project Introduction | PhuPD | 2 | Week 1 | 100 | Done | 2 |  | Lecturer
Stage 2: Project Planning & Initial Requirements (Weeks 2–3)
2.1 | Report 2 — Project Management Plan v1.0 | PhuPD, HieuLT, TungVPH | 3 | Week 2 | 100 | Done | 3 | 1.1, 2.1 | Lecturer | Planning, roles, timeline, risk, communication, tracking
2.2 | Report 3 — SRS v0.9 (Overall Requirements) | All team | 4 | Week 3 | 100 | Done | 4 | 1.1 | Lecturer | Scope, actors, functional requirements finalized
2.3 | Vertical Prototypes (Code Demo) | BE + FE | 5 | Week 3 | 100 | Done | 5 | 2.1 | Lecturer | Demonstrate a small end-to-end flow to prove the stack works.
Stage 3: Software Design (Weeks 4–5)
3.1 | Vertical Prototypes (POC / Proof of Concepts) | BE + FE | 4 | Week 4 | 100 | Done | 4 | 2.2 | Lecturer | Develop a Proof of Concept (POC) for technical components that involve risk or uncertainty.
3.2 | Report 3 — SRS v1.0 (Detailed — Iteration 1) | All team | 4 | Week 4 | 100 | Done | 4 | 2.1, 3.2 | Lecturer | Detailed requirements for features to be implemented in Iteration 1
3.3 | Report 4 — SDS v1.0 (High Level Design) | PhuPD, HieuLT, TungVPH | 5 | Week 5 | 100 | Done | 5 | 2.1, 2.2 | Lecturer | Architecture, service/module, DB high-level, API/interface, deployment overview
3.4 | Report 5 — Test Planning | PhuPD | 3 | Week 5 | 100 | Done | 3 | 2.1, 3.2 | Lecturer | Test strategy, test types, environment, entry/exit criteria, responsibilities
Stage 4a: Implementation — Iteration 1 (Weeks 6–7)
4.1.1 | Report 4 — SDS v1.1 (Detailed Design) |  |  | Week 6 |  | Not Started
4.1.2 | Code Package & Unit Testing Report — Iteration 1 |  |  | Week 6 |  | Not Started
4.1.3 | Report 5 — Integration Test Cases — Iteration 1 |  |  | Week 6 |  | Not Started
4.1.4 | Report 5 — Integration Test Report — Iteration 1 |  |  | Week 7 |  | Not Started
4.1.5 | Report 3 — SRS v1.1 (Detailed — Iteration 2) |  |  | Week 7 |  | Not Started
4.1.6 | Software Package Version 1 |  |  | Week 7 |  | Not Started
Stage 4b: Implementation — Iteration 2 (Weeks 8–9)
4.2.1 | Report 4 — SDS v1.2 |  |  | Week 8 |  | Not Started
4.2.2 | Code Package & Unit Testing Report — Iteration 2 |  |  | Week 8 |  | Not Started
4.2.3 | Report 5 — Integration Test Cases — Iteration 2 |  |  | Week 8 |  | Not Started
4.2.4 | Report 5 — Integration Test Report — Iteration 2 |  |  | Week 9 |  | Not Started
4.2.5 | Report 3 — SRS v1.2 (Detailed — Iteration 3) |  |  | Week 9 |  | Not Started
4.2.6 | Software Package Version 2 |  |  | Week 9 |  | Not Started
Stage 4c: Implementation — Iteration 3 (Weeks 10–11)
4.3.1 | Report 4 — SDS v1.3 |  |  | Week 10 |  | Not Started
4.3.2 | Code Package & Unit Testing Report — Iteration 3 |  |  | Week 10 |  | Not Started
4.3.3 | Report 5 — Integration Test Cases — Iteration 3 |  |  | Week 10 |  | Not Started
4.3.4 | Report 5 — Integration Test Report — Iteration 3 |  |  | Week 11 |  | Not Started
4.3.5 | Report 5 — System Test Cases |  |  | Week 11 |  | Not Started
4.3.6 | Software Package Version 3 |  |  | Week 11 |  | Not Started
Stage 5: Verification & Validation (Weeks 12–13)
5.1 | Report 5 — System Test Report |  |  | Week 12 |  | Not Started
5.2 | Report 6 — User Guides (Installation + User Manuals) |  |  | Week 12 |  | Not Started
5.3 | Acceptance Test and Support |  |  | Week 13 |  | Not Started
5.4 | Final Software Package (Docs + Source Codes) |  |  | Week 13 |  | Not Started
Stage 6: Closing (Week 14)
6.1 | Report 7 — Final Project Report |  |  | Week 14 |  | Not Started
6.2 | Presentation File |  |  | Week 14 |  | Not Started

## WBS
WBS — IELTSPath Phase 1 and FDS Delivery Breakdown
FDS v0.4: 50 screens + 7 jobs, with 7 supporting functions. Iteration allocation, roles and 3/5/8-point estimates are proposals. Done = implemented assigned scope, not UAT; mock/future work is labelled. Actual points unconfirmed.
Function / Screen | Type | Feature Group | Sub-Feature | Description | Complexity | Est. Effort (pts) | Planned Iteration | In Charge | Actual Effort (pts) | Status | Notes
WBS-001 — Home | Screen | Public / Access | FT-10, FT-11, FT-12 | Introduces IELTS Space, shows the FREE / Premium plans and point cards, and lets a signed-in learner redeem an activation key for Premium days or points. Route: /home · Public page (default route for guests) | Simple | 3 | Iteration 1 | FE owner |  | In Progress | FDS §2.1; FT-10, FT-11, FT-12; UC-30, UC-26; FE: partly built; Specified (key activation not wired in the frontend: GAP-03). Role: Guest and any signed-in user. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Done means implemented screen scope, not formal UAT approval. Phase allocation is proposed.
WBS-002 — Login | Screen | Authentication | FT-02, FT-03, FT-05, FT-07 | Lets a registered user sign in with email and password, so the app can return to the page the user wanted or open the learning path. Route: /login · Public page (GuestOnly) | Medium | 5 | Iteration 1 | FE owner |  | In Progress | FDS §2.2; FT-02, FT-03, FT-05, FT-07; UC-02, UC-03; FE: built, real API; Specified (OAuth button: Draft; role-based home: GAP-02). Role: Guest. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Done means implemented screen scope, not formal UAT approval. Phase allocation is proposed.
WBS-003 — Register | Screen | Authentication | FT-01, FT-02 | Lets a guest create a learner account and signs the guest in straight away, so learning can start. Route: /register · Public page (GuestOnly) | Simple | 3 | Iteration 1 | FE owner |  | Done | FDS §2.3; FT-01, FT-02; UC-01; FE: built, real API; Specified. Role: Guest. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Done means implemented screen scope, not formal UAT approval. Phase allocation is proposed.
WBS-004 — Forgot Password | Screen | Authentication | FT-04 | Lets a user who forgot the password ask for a reset code, so a new password can be set. Route: /forgot-password · Public page (GuestOnly) | Simple | 3 | Iteration 1 | FE owner |  | In Progress | FDS §2.4; FT-04; UC-04, UC-05; FE: built, real API; Specified (email delivery: Draft, GAP-06). Role: Guest. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Done means implemented screen scope, not formal UAT approval. Phase allocation is proposed.
WBS-005 — Reset Password | Screen | Authentication | FT-04 | Lets the user set a new password with the reset code, so the user can sign in again. Route: /reset-password?token=… · Public page (GuestOnly) | Simple | 3 | Iteration 1 | FE owner |  | In Progress | FDS §2.5; FT-04; UC-04; FE: built, real API; Specified (link delivery: Draft, GAP-06). Role: Guest. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Done means implemented screen scope, not formal UAT approval. Phase allocation is proposed.
WBS-006 — OAuth Callback | Screen | Authentication | FT-05 | Finishes a sign-in with the OAuth identity provider and opens the learning path. Route: /auth/oauth/callback · Public page (GuestOnly) | Simple | 3 | Iteration 3 | FE owner |  | Not Started | FDS §2.6; FT-05; UC-03; FE: placeholder route; Draft. Role: Guest. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Future iteration proposal, outside current Phase 1 acceptance.
WBS-007 — Overview | Screen | Prototype | FT-26, FT-44, FT-45 (intended) | Gives the learner a dashboard of study time, four-skill progress, words to review, mentor feedback, courses and the study streak. Route: /overview · RequireAuth (default route when signed in) | Simple | 3 | Iteration 2 | FE owner |  | Done | FDS §2.7; FT-26, FT-44, FT-45 (intended); UC-19, UC-18; FE: built on mock data; Draft (UI on mock data, OQ-17). Role: Any signed-in user. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Done refers only to the mock prototype; backend integration and acceptance are not complete. Iteration assignment is proposed, not an approved schedule.
WBS-008 — Learning Path | Screen | Core Learning | FT-13, FT-20, FT-28 | Shows the learner's topics as an ordered trail with each topic's status, so the learner knows which topic to study next. Route: /learn · RequireAuth | Simple | 3 | Iteration 1 | FE owner |  | In Progress | FDS §2.8; FT-13, FT-20, FT-28; UC-08; FE: built, real API; Specified (skill grouping: GAP-01; Premium lock: Draft). Role: Signed-in learner. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Done means implemented screen scope, not formal UAT approval. Phase allocation is proposed.
WBS-009 — Topic Detail | Screen | Core Learning | FT-20, FT-21, FT-27, FT-29 | Lists the ordered lessons of a topic and the final test card, so the learner can open the next lesson, go to practice or start the final test. Route: /learn/topics/:topicId · RequireAuth | Medium | 5 | Iteration 1 | FE owner |  | Done | FDS §2.9; FT-20, FT-21, FT-27, FT-29; UC-08, UC-20; FE: built, real API; Specified. Role: Signed-in learner. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Done means implemented screen scope, not formal UAT approval. Phase allocation is proposed.
WBS-010 — Lesson Player | Screen | Core Learning | FT-21, FT-22, FT-23, FT-24, FT-25 | Presents a lesson's blocks in order — text, passage, audio, exercises and essays — grades each exercise block, so the learner can pass the lesson and move on. Route: /learn/lessons/:lessonId · RequireAuth | Medium | 5 | Iteration 1 | FE owner |  | Done | FDS §2.10; FT-21, FT-22, FT-23, FT-24, FT-25; UC-09, UC-12, UC-13; FE: built, real API; Specified. Role: Signed-in learner. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Done means implemented screen scope, not formal UAT approval. Phase allocation is proposed.
WBS-011 — Writing Feedback | Screen | Core Learning | FT-12, FT-25 | Shows the AI grading of a Writing essay — estimated band, pass or not, criteria, corrections and the sample answer — so the learner can improve the next essay. Route: Inline panel in /learn/lessons/:lessonId (EssayBlock) | Simple | 3 | Iteration 1 | FE owner |  | In Progress | FDS §2.11; FT-12, FT-25; UC-12, UC-13, UC-27; FE: partly built; Specified (separate page and re-reading a submission: GAP-08). Role: Signed-in learner. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Done means implemented screen scope, not formal UAT approval. Phase allocation is proposed.
WBS-012 — Practice Set | Screen | Core Learning | FT-23, FT-24, FT-26, FT-27 | Lists the practice sets of a completed lesson and lets the learner answer one set, see every solution and start the review it creates. Route: /learn/lessons/:lessonId/practice · RequireAuth | Simple | 3 | Iteration 1 | FE owner |  | In Progress | FDS §2.12; FT-23, FT-24, FT-26, FT-27; UC-10; FE: built, real API; Specified (Premium sets disabled: GAP-05). Role: Signed-in learner. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Done means implemented screen scope, not formal UAT approval. Phase allocation is proposed.
WBS-013 — Review List | Screen | Core Learning | FT-28 | Lists the learner's reviews, oldest first, so the learner can finish the ones that block a skill. Route: /learn/reviews (proposed) | Simple | 3 | Iteration 2 | FE owner |  | Not Started | FDS §2.13; FT-28; UC-11; FE: not built; Specified (backend); screen not built (GAP-07). Role: CUSTOMER. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Future iteration proposal, outside current Phase 1 acceptance.
WBS-014 — Review Session | Screen | Core Learning | FT-23, FT-24, FT-26, FT-28 | Guides the learner through one review — theory with a quick check, then a set of questions — so a weak knowledge point is repaired and the skill is unblocked. Route: /learn/reviews/:reviewId · RequireAuth | Medium | 5 | Iteration 1 | FE owner |  | In Progress | FDS §2.14; FT-23, FT-24, FT-26, FT-28; UC-11; FE: built, real API; Specified (empty quick-check: GAP-12). Role: Signed-in learner. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Done means implemented screen scope, not formal UAT approval. Phase allocation is proposed.
WBS-015 — Mastery | Screen | Core Learning | FT-26 | Shows the learner's mastery from 0 to 1 for every knowledge point, grouped by skill and topic, so the learner can see strong and weak points. Route: /learn/mastery (proposed) | Simple | 3 | Iteration 2 | FE owner |  | Not Started | FDS §2.15; FT-26; UC-18; FE: not built; Specified (backend); screen not built (GAP-07). Role: CUSTOMER. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Future iteration proposal, outside current Phase 1 acceptance.
WBS-016 — Test Attempt | Screen | Core Learning | FT-24, FT-30, FT-31 | Lets the learner sit the topic final test section by section, with answers saved as they go, and submit it for grading. Route: /learn/tests/:attemptId?topic=… · RequireAuth | Simple | 3 | Iteration 1 | FE owner |  | In Progress | FDS §2.16; FT-24, FT-30, FT-31; UC-20; FE: built, real API; Specified (text answers saved at submit; no timer: GAP-09). Role: Signed-in learner. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Done means implemented screen scope, not formal UAT approval. Phase allocation is proposed.
WBS-017 — Test Result | Screen | Core Learning | FT-14, FT-24, FT-29, FT-31, FT-33 | Shows the score of the submitted topic test, per-question correctness and — at 70% or more — the correct answers, and tells the learner whether the topic is passed. Route: /learn/tests/:attemptId/result?topic=… · RequireAuth | Medium | 5 | Iteration 1 | FE owner |  | In Progress | FDS §2.17; FT-14, FT-24, FT-29, FT-31, FT-33; UC-22, UC-16, UC-25; FE: built, real API; Specified (examiner and AI grading requests: Draft). Role: Signed-in learner. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Done means implemented screen scope, not formal UAT approval. Phase allocation is proposed.
WBS-018 — Mock & Placement Tests | Screen | Core Learning | FT-34, FT-35 | Lists the published mock tests and the one-time placement test, so the learner can estimate a starting level or practise under exam conditions. Route: /tests (proposed) | Simple | 3 | Iteration 3 | FE owner |  | Not Started | FDS §2.18; FT-34, FT-35; UC-21, UC-23; FE: not built; Draft. Role: CUSTOMER. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Future iteration proposal, outside current Phase 1 acceptance.
WBS-019 — Practice Test Catalog | Screen | Prototype | — (no SRS feature; closest FT-34 Mock test) | Lets the learner browse practice tests by skill and open one in practice or exam mode. Route: /practice-tests · RequireAuth | Simple | 3 | Iteration 2 | FE owner |  | Done | FDS §2.19; — (no SRS feature; closest FT-34 Mock test); No UC assigned; FE: built on mock data; Prototype (mock data, OQ-17). Role: Any signed-in user. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Done refers only to the mock prototype; backend integration and acceptance are not complete. Iteration assignment is proposed, not an approved schedule.
WBS-020 — Practice Workspaces (Reading, Listening, Writing, Speaking) | Screen | Prototype | — (closest FT-25, FT-39, FT-42, FT-43) | Gives a full-screen workspace for one practice test per skill, with tools for highlighting, notes, a small dictionary and flashcards. Route: /practice/test/:testId · /practice/listening/:testId · /practice/writing/:taskId · /practice/speaking/:cueId · RequireAuth | Simple | 3 | Iteration 2 | FE owner |  | Done | FDS §2.20; — (closest FT-25, FT-39, FT-42, FT-43); No UC assigned; FE: built on mock data; Prototype (mock data and browser storage, OQ-17). Role: Any signed-in user. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Done refers only to the mock prototype; backend integration and acceptance are not complete. Iteration assignment is proposed, not an approved schedule.
WBS-021 — Classroom | Screen | Prototype | — (mentor classes are not in the SRS) | Shows the learner's class, teacher and a calendar of class sessions with a link to join or open each session. Route: /classroom · RequireAuth | Simple | 3 | Iteration 2 | FE owner |  | Done | FDS §2.21; — (mentor classes are not in the SRS); No UC assigned; FE: built on mock data; Prototype (mock data, OQ-17). Role: Any signed-in user. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Done refers only to the mock prototype; backend integration and acceptance are not complete. Iteration assignment is proposed, not an approved schedule.
WBS-022 — Classroom Lesson Workspace | Screen | Prototype | — (closest FT-36, FT-43) | Shows one class session with its materials, a short quiz and the topic vocabulary to review. Route: /lessons/:lessonId · RequireAuth | Simple | 3 | Iteration 2 | FE owner |  | Done | FDS §2.22; — (closest FT-36, FT-43); No UC assigned; FE: built on mock data; Prototype (mock data, OQ-17). Role: Any signed-in user. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Done refers only to the mock prototype; backend integration and acceptance are not complete. Iteration assignment is proposed, not an approved schedule.
WBS-023 — Profile & Account | Screen | Self-study / Account | FT-05, FT-06 | Lets a user keep account details and the learner profile up to date and manage linked sign-in providers. Route: /account/profile | Medium | 5 | Iteration 2 | FE owner |  | Not Started | FDS §2.23; FT-05, FT-06; UC-06; FE: not built; Specified (OAuth linking: Draft). Role: Any signed-in role. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Future iteration proposal, outside current Phase 1 acceptance.
WBS-024 — Learning Goals | Screen | Self-study / Account | FT-09, FT-35 | Lets the learner set one active goal — target band, exam date and daily study minutes — and pause, resume or close it, so progress can be tracked against a target. Route: /account/goals | Medium | 5 | Iteration 2 | FE owner |  | Not Started | FDS §2.24; FT-09, FT-35; UC-06, UC-23; FE: not built; Specified (edit of the active goal: Draft). Role: CUSTOMER. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Future iteration proposal, outside current Phase 1 acceptance.
WBS-025 — Subscription & Points | Screen | Self-study / Account | FT-10, FT-11, FT-12, FT-14 | Shows the learner's subscription, examiner credits, point balance and history, and lets the learner redeem an activation key for Premium days or points. Route: /account/subscription | Medium | 5 | Iteration 1 | FE owner |  | In Progress | FDS §2.25; FT-10, FT-11, FT-12, FT-14; UC-30, UC-27, UC-26; FE: partly built; Specified. Role: CUSTOMER. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Done means implemented screen scope, not formal UAT approval. Phase allocation is proposed.
WBS-026 — Activity & Streak | Screen | Self-study / Account | FT-44, FT-45 | Shows the learner's study activities and current and longest streak, so the learner can keep a daily study habit. Route: /account/activity | Medium | 5 | Iteration 2 | FE owner |  | Not Started | FDS §2.26; FT-44, FT-45; UC-19; FE: not built; Specified (server-side streak: Draft). Role: Any signed-in role. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Future iteration proposal, outside current Phase 1 acceptance.
WBS-027 — Notification Centre | Screen | Self-study / Account | FT-51, FT-52, FT-53, FT-54 | Lists the learner's in-app notifications and lets the learner choose channels, reminder time and registered devices. Route: /notifications | Medium | 5 | Iteration 3 | FE owner |  | Not Started | FDS §2.27; FT-51, FT-52, FT-53, FT-54; UC-32, UC-31; FE: not built; Draft. Role: CUSTOMER. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Future iteration proposal, outside current Phase 1 acceptance.
WBS-028 — Vocabulary | Screen | Self-study / Account | FT-36, FT-43 | Lets the learner look up topic vocabulary, hear the pronunciation and save words to review later. Route: /vocabulary · Public page | Medium | 5 | Iteration 2 | FE owner |  | Done | FDS §2.28; FT-36, FT-43; UC-37, UC-33; FE: built on mock data; Specified (backend); frontend on mock data (GAP-10). Role: Guest and any signed-in user. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Done refers only to the mock prototype; backend integration and acceptance are not complete. Iteration assignment is proposed, not an approved schedule.
WBS-029 — Video Library | Screen | Self-study / Account | FT-37, FT-38 | Lists the published learning videos with the learner's progress, so the learner can pick one to watch. Route: /library/videos | Simple | 3 | Iteration 2 | FE owner |  | Not Started | FDS §2.29; FT-37, FT-38; UC-37; FE: not built; Specified. Role: CUSTOMER, EXAMINER, CONTENT_AUTHOR, ADMIN. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Future iteration proposal, outside current Phase 1 acceptance.
WBS-030 — Video Player | Screen | Self-study / Account | FT-37, FT-38, FT-39, FT-40, FT-41 | Plays a learning video with its segment transcript, remembers progress, saves segments and lets the learner practise shadowing and dictation on a segment. Route: /library/videos/:videoId | Complex | 8 | Iteration 2 | FE owner |  | Not Started | FDS §2.30; FT-37, FT-38, FT-39, FT-40, FT-41; UC-38, UC-17, UC-39, UC-14, UC-15; FE: not built; Specified (shadowing / dictation scoring: Draft). Role: CUSTOMER. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Future iteration proposal, outside current Phase 1 acceptance.
WBS-031 — My Notes | Screen | Self-study / Account | FT-42 | Lets the learner write private notes, optionally linked to a knowledge point or a Reading section. Route: /library/notes | Medium | 5 | Iteration 2 | FE owner |  | Not Started | FDS §2.31; FT-42; UC-33; FE: not built; Specified. Role: Any signed-in role. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Future iteration proposal, outside current Phase 1 acceptance.
WBS-032 — Flashcards & Decks | Screen | Self-study / Account | FT-43 | Lets the learner create flashcards, group them into decks and study a deck card by card. Route: /library/flashcards | Complex | 8 | Iteration 2 | FE owner |  | Not Started | FDS §2.32; FT-43; UC-33; FE: not built; Specified. Role: Any signed-in role. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Future iteration proposal, outside current Phase 1 acceptance.
WBS-033 — Game Lobby | Screen | Self-study / Account | FT-46, FT-47, FT-48 | Lets the learner start a single-player game, create or join a multiplayer room, and see past sessions. Route: /games | Medium | 5 | Iteration 3 | FE owner |  | Not Started | FDS §2.33; FT-46, FT-47, FT-48; UC-34; FE: not built; Specified (matchmaking: Draft). Role: Any signed-in role. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Future iteration proposal, outside current Phase 1 acceptance.
WBS-034 — Single-player Game | Screen | Self-study / Account | FT-46 | Plays a single-player vocabulary or grammar game item by item on a frozen content snapshot and shows the final score. Route: /games/sessions/:sessionId | Simple | 3 | Iteration 3 | FE owner |  | Not Started | FDS §2.34; FT-46; UC-34; FE: not built; Specified. Role: Any signed-in role. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Future iteration proposal, outside current Phase 1 acceptance.
WBS-035 — Game Room | Screen | Self-study / Account | FT-47 | Gathers players in a multiplayer room, lets the host start the match and plays it in real time over WebSocket, ending with a ranking. Route: /games/rooms/:roomId | Medium | 5 | Iteration 3 | FE owner |  | Not Started | FDS §2.35; FT-47; UC-34; FE: not built; Specified. Role: Any signed-in role. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Future iteration proposal, outside current Phase 1 acceptance.
WBS-036 — Community Feed | Screen | Self-study / Account | FT-49, FT-50 | Lists active community posts newest first and lets users write a post, react, and — for Administrators — hide posts that break the rules. Route: /community | Medium | 5 | Iteration 3 | FE owner |  | Not Started | FDS §2.36; FT-49, FT-50; UC-35, UC-36; FE: not built; Specified. Role: Any signed-in role. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Future iteration proposal, outside current Phase 1 acceptance.
WBS-037 — Post Detail | Screen | Self-study / Account | FT-49, FT-50 | Shows one post with its comments and lets users comment, reply, edit or delete their own content, and Administrators hide or restore it. Route: /community/posts/:postId | Complex | 8 | Iteration 3 | FE owner |  | Not Started | FDS §2.37; FT-49, FT-50; UC-35, UC-36; FE: not built; Specified. Role: Any signed-in role. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Future iteration proposal, outside current Phase 1 acceptance.
WBS-038 — User Management | Screen | Staff | FT-07, FT-08 | Lets an Administrator find accounts, create staff or learner accounts with roles, and open an account to manage it. Route: /admin/users · ADMIN home | Simple | 3 | Iteration 3 | FE owner |  | Not Started | FDS §2.38; FT-07, FT-08; UC-07; FE: not built; Specified (paging and search: Draft). Role: ADMIN. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Future iteration proposal, outside current Phase 1 acceptance.
WBS-039 — User Detail | Screen | Staff | FT-04, FT-05, FT-08, FT-09, FT-10, FT-12, FT-13 | Lets an Administrator change one account's details, roles and status, and review its profile, goals, linked providers and account action tokens. Route: /admin/users/:userId | Complex | 8 | Iteration 3 | FE owner |  | Not Started | FDS §2.39; FT-04, FT-05, FT-08, FT-09, FT-10, FT-12, FT-13; UC-07; FE: not built; Specified. Role: ADMIN. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Future iteration proposal, outside current Phase 1 acceptance.
WBS-040 — Plans & Key Products | Screen | Staff | FT-10, FT-14 | Lets an Administrator define plans and the key products that activation keys grant (Premium days with examiner credits, or points). Route: /admin/access/plans | Medium | 5 | Iteration 3 | FE owner |  | Not Started | FDS §2.40; FT-10, FT-14; UC-29; FE: not built; Specified. Role: ADMIN. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Future iteration proposal, outside current Phase 1 acceptance.
WBS-041 — Activation Keys | Screen | Staff | FT-11 | Lets staff generate a batch of activation keys for a key product, copy them once, and revoke keys that were lost before use. Route: /admin/access/keys · SALES_STAFF home | Medium | 5 | Iteration 3 | FE owner |  | Not Started | FDS §2.41; FT-11; UC-28; FE: not built; Specified for ADMIN (SALES_STAFF access and key list: Draft). Role: ADMIN, SALES_STAFF. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Future iteration proposal, outside current Phase 1 acceptance.
WBS-042 — Points & Subscriptions | Screen | Staff | FT-10, FT-12, FT-14 | Lets an Administrator grant subscription days and examiner credits, adjust or refund a learner's points with a reason, and consume an examiner credit. Route: /admin/access/accounts | Medium | 5 | Iteration 3 | FE owner |  | Not Started | FDS §2.42; FT-10, FT-12, FT-14; UC-29; FE: not built; Specified. Role: ADMIN. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Future iteration proposal, outside current Phase 1 acceptance.
WBS-043 — Topics & Knowledge Points | Screen | Staff | FT-15 | Lets an author maintain the topic tree of each skill and the knowledge points each topic teaches. Route: /author/topics · CONTENT_AUTHOR home | Medium | 5 | Iteration 3 | FE owner |  | Not Started | FDS §2.43; FT-15; UC-40; FE: not built; Specified. Role: ADMIN, CONTENT_AUTHOR. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Future iteration proposal, outside current Phase 1 acceptance.
WBS-044 — Question Bank | Screen | Staff | FT-16 | Lets an author create versioned questions with answer, explanation, hint, purpose and knowledge points, and filter the bank by purpose and skill. Route: /author/questions | Medium | 5 | Iteration 3 | FE owner |  | Not Started | FDS §2.44; FT-16; UC-40; FE: not built; Specified. Role: ADMIN, CONTENT_AUTHOR. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Future iteration proposal, outside current Phase 1 acceptance.
WBS-045 — Packages | Screen | Staff | FT-17, FT-34, FT-35 | Lets an author group questions into versioned packages — practice sets, tests and quizzes — and publish them after the system checks question ownership and purpose. Route: /author/packages | Medium | 5 | Iteration 3 | FE owner |  | Not Started | FDS §2.45; FT-17, FT-34, FT-35; UC-40; FE: not built; Specified (TOPIC_TEST creation: Draft). Role: ADMIN, CONTENT_AUTHOR. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Future iteration proposal, outside current Phase 1 acceptance.
WBS-046 — Media Assets | Screen | Staff | FT-18, FT-24 | Lets an author register passage text, images and Listening audio as assets and link them to sections or question versions. Route: /author/assets | Medium | 5 | Iteration 3 | FE owner |  | Not Started | FDS §2.46; FT-18, FT-24; UC-40, UC-41; FE: not built; Specified (upload: Draft). Role: ADMIN, CONTENT_AUTHOR. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Future iteration proposal, outside current Phase 1 acceptance.
WBS-047 — Lesson Builder | Screen | Staff | FT-19 | Lets an author build a topic's ordered lessons from theory, assets, exercise blocks and essay blocks, and publish them to the learning path. Route: /author/lessons/:lessonId | Simple | 3 | Iteration 3 | FE owner |  | Not Started | FDS §2.47; FT-19; UC-42; FE: not built; Draft. Role: ADMIN, CONTENT_AUTHOR. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Future iteration proposal, outside current Phase 1 acceptance.
WBS-048 — Vocabulary Management | Screen | Staff | FT-36 | Lets an author add vocabulary items and their senses to the catalog used by lessons, videos, flashcards and games. Route: /author/vocabulary | Medium | 5 | Iteration 3 | FE owner |  | Not Started | FDS §2.48; FT-36; UC-40; FE: not built; Specified. Role: ADMIN, CONTENT_AUTHOR. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Future iteration proposal, outside current Phase 1 acceptance.
WBS-049 — Video Management | Screen | Staff | FT-37 | Lets an author register a YouTube learning video, split it into timed segments with transcripts and linked words, and publish it. Route: /author/videos | Medium | 5 | Iteration 3 | FE owner |  | Not Started | FDS §2.49; FT-37; UC-40; FE: not built; Specified. Role: ADMIN, CONTENT_AUTHOR. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Future iteration proposal, outside current Phase 1 acceptance.
WBS-050 — Grading Workspace | Screen | Staff | FT-32, FT-52 | Lets an Examiner open a submitted attempt, enter item scores, errors and knowledge-point judgments, and finalize the result so it reaches the learner's progress. Route: /examiner/grading · EXAMINER home | Medium | 5 | Iteration 3 | FE owner |  | Not Started | FDS §2.50; FT-32, FT-52; UC-24; FE: not built; Specified (work queue and response view: Draft). Role: ADMIN, EXAMINER. Estimate is provisional (3/5/8 pts from input/API complexity), not actual effort. Owner is a proposed role. Future iteration proposal, outside current Phase 1 acceptance.
WBS-051 — Backend build foundation | Non-UI | Infrastructure |  | Maven multi-module, Java service folders and repeatable build baseline. | Medium | 5 | Iteration 1 | BE owner |  | Done | Git backend 218e071. Foundation supporting FDS §2.0; implementation evidence, not UAT. Estimate / role assignment provisional; actual points unavailable.
WBS-052 — Config Server and Eureka | Non-UI | Infrastructure |  | Centralized configuration and service registration/discovery. | Medium | 5 | Iteration 1 | BE owner |  | Done | Git backend 218e071, dac8b03; backend/README.md. Estimate / role assignment provisional; actual points unavailable.
WBS-053 — Gateway security and routing | Non-UI | Security |  | Route public APIs; verify external JWT; sign internal JWT; enforce roles/ownership and prevent internal-route exposure. | Complex | 8 | Iteration 1 | BE owner |  | Done | FDS §2.0; FT-07; Git backend 218e071, a18a44e, 34335aa. Estimate / role assignment provisional; actual points unavailable.
WBS-054 — Docker and database baseline | Non-UI | Infrastructure |  | Local Docker Compose, service PostgreSQL schemas and Flyway migration foundation. | Complex | 8 | Iteration 1 | BE owner |  | Done | Git backend 218e071, dac8b03. Runtime reliability still requires test evidence. Estimate / role assignment provisional; actual points unavailable.
WBS-055 — Frontend build and UI foundation | Non-UI | Frontend Foundation |  | React/TypeScript/Vite, Tailwind/shadcn setup, theme, aliases and lint/typecheck/build. | Medium | 5 | Iteration 1 | FE owner |  | Done | Git frontend 241abca, 8581a72, 015701d. Baseline work supporting all FDS screens. Estimate / role assignment provisional; actual points unavailable.
WBS-056 — Session and shared request handling | Non-UI | Authentication |  | Memory-only access token, cookie refresh, single-flight retry, protected routes, timeout and shared error states. | Complex | 8 | Iteration 1 | FE / BE owners |  | Done | FDS §2.0 common conventions; FT-03, FT-07; frontend/src/lib/httpClient.ts. Role-based staff routing remains future work. Estimate / role assignment provisional; actual points unavailable.
WBS-057 — Mastery and submission integrity | Non-UI | Core Learning |  | Persist evidence and mastery, apply per-skill gates, enforce request replay and Writing point-charge consistency. | Complex | 8 | Iteration 1 | BE / QA owners |  | In Progress | FDS §2.10–2.17; FT-26–FT-28; BR-21–BR-25, BR-30. Implementation exists; full live/UI and points acceptance remains open. Estimate / role assignment provisional; actual points unavailable.
WBS-058 — JOB-01 Assessment outbox relay | Non-UI | Background Jobs |  | Publishes the AssessmentCompleted.v2 events that grading writes to the outbox table, so a result reaches the learning service only after its database transaction has committed. Trigger: @Scheduled fixed delay 2 s (assessment.outbox.relay.poll-interval = PT2S); enabled by ASSESSMENT_OUTBOX_RELAY_ENABLED (default true) | Complex | 8 | Iteration 1 | BE owner |  | Done | FDS Part 3 JOB-01; FT-29, FT-31, FT-32 · BR-25, BR-26, BR-30; Specified (implemented). Implemented runtime, separate operational acceptance required. Estimate / role assignment provisional; actual points unavailable.
WBS-059 — JOB-02 AssessmentCompleted.v2 consumer | Non-UI | Background Jobs |  | Applies each final assessment result to the learner's progress: knowledge-point evidence, topic test assignment, topic pass and reviews for weak knowledge points. Trigger: @RabbitListener on queue learning.assessment-completed.v2 (manual ack); learning.messaging.consumer-enabled (default true) | Complex | 8 | Iteration 1 | BE owner |  | Done | FDS Part 3 JOB-02; FT-26, FT-29, FT-34, FT-35 · BR-22, BR-23, BR-25; Specified (implemented). Implemented runtime, separate operational acceptance required. Estimate / role assignment provisional; actual points unavailable.
WBS-060 — JOB-03 AI grading worker | Non-UI | Background Jobs |  | Grades a learner's Writing or Speaking response that was sent for AI grading inside a test attempt, and finalizes the result so it feeds learning progress. Trigger: Polls grading_jobs with status QUEUED every [TBC] s (or consumes an internal queue [TBC]) | Complex | 8 | Iteration 3 | BE owner |  | Not Started | FDS Part 3 JOB-03; FT-33, FT-34, FT-39 · BR-09, BR-30; Draft. Draft/future iteration proposal, not Phase 1 delivered scope. Estimate / role assignment provisional; actual points unavailable.
WBS-061 — JOB-04 Grading-done alert dispatcher | Non-UI | Background Jobs |  | Creates one grading-done notification when an examiner finalizes a result and hands it to the delivery channels the learner enabled. Trigger: RabbitMQ: own queue bound to assessment.events / assessment.completed.v2 [TBC: queue name] | Complex | 8 | Iteration 3 | BE owner |  | Not Started | FDS Part 3 JOB-04; FT-51, FT-52 · BR-27, BR-32; Draft. Draft/future iteration proposal, not Phase 1 delivered scope. Estimate / role assignment provisional; actual points unavailable.
WBS-062 — JOB-05 Study reminder scheduler | Non-UI | Background Jobs |  | Creates at most one study reminder per learner per day, at the learner's preferred local time, on days without a qualifying study activity. Trigger: @Scheduled every [TBC] minutes; ShedLock or SKIP LOCKED to run on one instance [TBC] | Complex | 8 | Iteration 3 | BE owner |  | Not Started | FDS Part 3 JOB-05; FT-44, FT-51, FT-53 · BR-32; Draft. Draft/future iteration proposal, not Phase 1 delivered scope. Estimate / role assignment provisional; actual points unavailable.
WBS-063 — JOB-06 Notification delivery retry | Non-UI | Background Jobs |  | Sends pending notification deliveries to Firebase Cloud Messaging or the Email Service and retries failed ones without creating a second notification. Trigger: @Scheduled every [TBC] s | Complex | 8 | Iteration 3 | BE owner |  | Not Started | FDS Part 3 JOB-06; FT-52, FT-53, FT-54 · BR-32; Draft. Draft/future iteration proposal, not Phase 1 delivered scope. Estimate / role assignment provisional; actual points unavailable.
WBS-064 — JOB-07 Matchmaking queue sweeper | Non-UI | Background Jobs |  | Groups waiting learners of the same game type into a room and starts the match, and removes learners who waited too long. Trigger: @Scheduled every [TBC] s | Complex | 8 | Iteration 3 | BE owner |  | Not Started | FDS Part 3 JOB-07; FT-47, FT-48 · BR-29; Draft. Draft/future iteration proposal, not Phase 1 delivered scope. Estimate / role assignment provisional; actual points unavailable.
Iteration Summary (provisional allocation)
Iteration | Functions | Est. Effort (pts) | Done | In Progress
Iteration 1 | 23 | 117 | 11 | 12
Iteration 2 | 15 | 65 | 6 | 0
Iteration 3 | 26 | 141 | 0 | 0
Grand Total | 64 | 323 | 17 | 12

## Q&A
Q&A — IELTSPath Phase 1
Phase 1 working boundary: initial MVP. Questions consolidated 07/10/2026. Blank due dates require PM confirmation.
# | Date | Question | Raised By | Directed To | Priority | Due Date | Answer / Resolution | Answered By | Answered Date | Status | Notes
Q-001 | 2026-10-07 | What does Phase 1 cover, and how does it relate to WBS Iteration 1? | Project review | PM / supervisor | High |  | Working boundary: initial MVP, authentication and the core learning loop. WBS Iteration 1 lists a different feature set. Confirm the phase baseline before approval. |  |  | Open | docs/test-plan/IELTS_Space_Test_Plan_v1.docx; original WBS A5:L17. Review question recorded 07/10/2026; not an earlier meeting minute.
Q-002 | 2026-10-07 | Who are the Phase 1 users and what problem does IELTSPath address? | Project review | BA / IELTS Space | Medium |  | New visitors try the centre teaching before enrolment. Current and waiting-list learners practise between classes and see their own progress. | Repository evidence | 2026-10-07 | Answered | backend/capstone-docs/rp_1_vision-scope/Report 1_Vision_Scope_IeltsPath.docx §1, §3, §5
Q-003 | 2026-10-07 | Which implementation is the current learning backend? | Project review | Backend lead | High |  | Java learning-service owns lesson progress, mastery, review, practice and assessment-result consumption. The former Python AI Learning flow is superseded. | Repository evidence | 2026-10-07 | Answered | backend/AGENTS.md §1; backend/docs/system-architecture.md
Q-004 | 2026-10-07 | What authentication and authorization contract must FE follow? | Project review | Backend / frontend leads | High |  | Use Gateway APIs, Bearer access token and the existing refresh flow. Gateway validates external JWT and signs an internal JWT. Protected services enforce role and ownership. | Repository evidence | 2026-10-07 | Answered | backend/docs/fe-main-flow-guide.md §1, §4; frontend/src/lib/httpClient.ts; backend/README.md
Q-005 | 2026-10-07 | When does a learner unlock a topic test? | Project review | Learning owner | High |  | Complete required lessons and Practice, then clear applicable pending reviews. A lesson completion alone is insufficient. Topic test pass threshold is 70%. | Repository evidence | 2026-10-07 | Answered | backend/docs/fe-main-flow-guide.md §3–4; frontend/plans/reports/e2e-practice-261005/report.md
Q-006 | 2026-10-07 | Are live Writing AI grading and points already fully accepted? | Project review | QA / product owner | High |  | Lesson essay integration exists: at least 3 points, 3-point charge, request replay and >=60-second FE timeout. Live LLM quality and complete paid retry behaviour need separate acceptance evidence. |  |  | Open | backend/docs/fe-main-flow-guide.md; frontend/plans/reports/e2e-practice-261005/report.md; docs/test-plan/IELTS_Space_Test_Plan_v1.docx TP-LRN-06
Q-007 | 2026-10-07 | Is Listening playback ready for the Phase 1 demo? | Project review | Content owner / QA | High |  | AudioBlock is integrated. Provide valid media and test playback. Transcript must appear only when the backend exposes it after the permitted submission. |  |  | Open | backend/docs/fe-main-flow-guide.md; frontend/plans/reports/e2e-practice-261005/report.md; docs/test-plan/IELTS_Space_Test_Plan_v1.docx
Q-008 | 2026-10-07 | Does premium activation require online payment? | Project review | Product owner / sales | Medium |  | No. Sales distribute activation cards outside the system. The system records activations and grants access or points; payment, invoicing and revenue reporting are excluded. | Repository evidence | 2026-10-07 | Answered | backend/capstone-docs/rp_1_vision-scope/Report 1_Vision_Scope_IeltsPath.docx §4.2 LI-01; backend/capstone-docs/rp_3.0_system-requirements-system/Report 3.0_SRS_IELTSPath_IeltsPath_v1.docx SC-03
Q-009 | 2026-10-07 | Is a premium badge sufficient access protection? | Project review | Backend / product owner | High |  | No. Current MVP has UI flags but no learning subscription enforcement. Decide whether Phase 1 is free-only or must add server-side entitlement before a paid release. |  |  | Open | backend/docs/fe-main-flow-guide.md §6; docs/test-plan/IELTS_Space_Test_Plan_v1.docx Out of Scope
Q-010 | 2026-10-07 | Can the 05/10 E2E report be described as full browser acceptance? | Project review | QA | High |  | No. Fresh registration, test submit and result were exercised in browser. Lessons and Practice used API assistance; review was N/A. Full unassisted UI acceptance is still needed. | Repository evidence | 2026-10-07 | Answered | frontend/plans/reports/e2e-main-flow-261005-fresh/report.md Method and checklist; frontend/plans/reports/e2e-practice-261005/report.md E2E note
Q-011 | 2026-10-07 | Are band courses and placement recommendation available across BE and FE? | Project review | Backend / frontend leads | Medium |  | Backend course work merged on 07/10. FE currently loads topics and has no course methods in LearningApi. Live course smoke and phase inclusion remain open. |  |  | Open | backend/plans/261006-2228-course-band-levels/plan.md final verification; frontend/src/features/learning-path/api/learningApi.ts
Q-012 | 2026-10-07 | Are mixed-skill lessons and free assessment AI essays completed? | Project review | PM / backend lead | Medium |  | No. The multi-skill plan is pending. Keep its implementation and acceptance separate from the initial MVP results. | Repository evidence | 2026-10-07 | Answered | backend/plans/261006-2309-multi-skill-lessons/plan.md status and phase table
Q-013 | 2026-10-07 | Should Speaking, full mock tests, mobile, games and community count as Phase 1 accepted features? | Project review | PM / supervisor | High |  | They are product features in Vision & Scope, but outside the priority test v1 boundary or lack full flow evidence. Confirm future delivery allocation; do not mark accepted from code presence alone. |  |  | Open | backend/capstone-docs/rp_1_vision-scope/Report 1_Vision_Scope_IeltsPath.docx §4.1; docs/test-plan/IELTS_Space_Test_Plan_v1.docx Out of Scope
Q-014 | 2026-10-07 | What are the official reporters, hours, dates and approvals for timesheets? | Project review | PM / team members | High |  | No actual timesheets supplied. TimeLogs lists evidenced work products with hours and reporter pending. Obtain actual member entries before calculating approved effort. |  |  | Open | Original Scope names PhuPD, HieuLT, TungVPH; no row-level work-hour evidence found.
Q-015 | 2026-10-07 | Have the updated SRS, TDS and test plan been formally approved? | Project review | PM / supervisor | High |  | Approval evidence is not available. SRS still contains author/reviewer/date placeholders and the test plan reflects some older FE assumptions. Reconcile current implementation and obtain formal review. |  |  | Open | backend/capstone-docs/rp_3.0_system-requirements-system/Report 3.0_SRS_IELTSPath_IeltsPath_v1.docx metadata; docs/test-plan/IELTS_Space_Test_Plan_v1.docx baseline/out-of-scope; frontend/plans/reports/e2e-main-flow-261005-fresh/report.md

## TimeLogs
TimeLogs — IELTSPath Phase 1
Reconstructed work register from merged Git history through 07/10/2026. Date = Git author date; Reporter = Git author attribution. Actual hours / PM approval unconfirmed.
# | Date | Reporter | WBS Ref | Task Description | Activity | Type | # Hours | Product / Work Product | Iteration | Status | Approved By | Updated | Notes
TL-001 | 2026-09-15 | Git: hieuLeFpt | WBS-055 | Initialize React / TypeScript / Vite and application folders | Coding | Newly-Created |  | Frontend scaffold | Phase 1 | Pending |  | 2026-10-07 | Reconstructed from frontend commits 241abca on main. Date = latest Git author date in this work group, not confirmed work date. Author attribution, actual hours and PM approval require confirmation. Initial history snapshot may include earlier local work.
TL-002 | 2026-09-15 | Git: hieuLeFpt | WBS-055 | Configure Tailwind, shadcn setup, theme and import aliases | Coding | Newly-Created |  | FE styling foundation | Phase 1 | Pending |  | 2026-10-07 | Reconstructed from frontend commits 241abca on main. Date = latest Git author date in this work group, not confirmed work date. Author attribution, actual hours and PM approval require confirmation. Same commit as TL-001, distinct files/work product; avoid double-counting when entering hours.
TL-003 | 2026-09-15 | Git: hieuLeFpt | WBS-055 | Configure Node/npm constraints, dependencies, lint/typecheck/build | Coding | Newly-Created |  | FE tooling baseline | Phase 1 | Pending |  | 2026-10-07 | Reconstructed from frontend commits 241abca, 8581a72 on main. Date = latest Git author date in this work group, not confirmed work date. Author attribution, actual hours and PM approval require confirmation. Dependency installation does not prove router/store integration.
TL-004 | 2026-09-17 | Git: Lê Trung Hiếu | WBS-051 | Initialize Maven multi-module build and service structure | Coding | Newly-Created |  | Backend scaffold | Phase 1 | Pending |  | 2026-10-07 | Reconstructed from backend commits 218e071 on main. Date = latest Git author date in this work group, not confirmed work date. Author attribution, actual hours and PM approval require confirmation. Initial snapshot, not an exact creation-time record.
TL-005 | 2026-09-17 | Git: Lê Trung Hiếu | WBS-052 | Set up Config Server, configuration repository and Eureka | Coding | Newly-Created |  | Service infrastructure | Phase 1 | Pending |  | 2026-10-07 | Reconstructed from backend commits 218e071 on main. Date = latest Git author date in this work group, not confirmed work date. Author attribution, actual hours and PM approval require confirmation. Shares commit with TL-004–007; split actual time by work product, not by commit.
TL-006 | 2026-09-17 | Git: Lê Trung Hiếu | WBS-053 | Implement Gateway routing, external/internal JWT and service security | Coding | Modified |  | Ingress and security baseline | Phase 1 | Pending |  | 2026-10-07 | Reconstructed from backend commits 218e071, a18a44e on main. Date = latest Git author date in this work group, not confirmed work date. Author attribution, actual hours and PM approval require confirmation.
TL-007 | 2026-09-17 | Git: Lê Trung Hiếu | WBS-054 | Set up Docker Compose, PostgreSQL and container configuration | Coding | Modified |  | Local infrastructure setup | Phase 1 | Pending |  | 2026-10-07 | Reconstructed from backend commits 218e071, dac8b03 on main. Date = latest Git author date in this work group, not confirmed work date. Author attribution, actual hours and PM approval require confirmation.
TL-008 | 2026-09-22 | Git: Lê Trung Hiếu | WBS-002, WBS-003, WBS-056 | Add user unit tests and HttpOnly-cookie authentication | Coding | Modified |  | User/auth APIs and tests | Phase 1 | Pending |  | 2026-10-07 | Reconstructed from backend commits 115c36d, 2c9d37f on main. Date = latest Git author date in this work group, not confirmed work date. Author attribution, actual hours and PM approval require confirmation. Tests added are recorded work; test execution outcomes need their own evidence.
TL-009 | 2026-09-23 | Git: Lê Trung Hiếu | WBS-043, WBS-044, WBS-045, WBS-046 | Scaffold business services and implement Content schema and APIs | Coding | Modified |  | Content and service baseline | Phase 1 | Pending |  | 2026-10-07 | Reconstructed from backend commits 11a78fa on main. Date = latest Git author date in this work group, not confirmed work date. Author attribution, actual hours and PM approval require confirmation.
TL-010 | 2026-09-23 | Git: hieuLeFpt, PhuPham70 | WBS-025, WBS-050 | Initialize Access and Assessment service functionality and Access tests | Coding | Modified |  | Access / Assessment baseline | Phase 1 | Pending |  | 2026-10-07 | Reconstructed from backend commits 99b7d4f, 3678274, c087a3f on main. Date = latest Git author date in this work group, not confirmed work date. Author attribution, actual hours and PM approval require confirmation. Authors belong to their respective commits; this group is not a joint timesheet approval.
TL-011 | 2026-09-24 | Git: hieuLeFpt, Claude | WBS-057 | Build the historical Python AI Learning prototype and local runtime | Coding | Modified |  | Earlier learning prototype | Phase 1 | Pending |  | 2026-10-07 | Reconstructed from backend commits e1cf196, f430f61, 4ba99a5, 2860664 on main. Date = latest Git author date in this work group, not confirmed work date. Author attribution, actual hours and PM approval require confirmation. e1cf196: human author; later commits credit Claude. Automated commits do not establish a human reporter. Prototype later retired; historical work only. WBS reference covers the baseline supporting function only; the retired prototype/course extension has no standalone accepted FDS screen.
TL-012 | 2026-09-23 | Git: sonledz22 | WBS-007, WBS-019, WBS-020 | Build mock learning workspace and UI prototype | Coding | Modified |  | Initial learning UI | Phase 1 | Pending |  | 2026-10-07 | Reconstructed from frontend commits 6ffb8a4, b8d3f3f on main. Date = latest Git author date in this work group, not confirmed work date. Author attribution, actual hours and PM approval require confirmation. Historical mock prototype, not accepted HTTP integration.
TL-013 | 2026-09-30 | Git: sonledz22 | WBS-007, WBS-019, WBS-020, WBS-021, WBS-022, WBS-055 | Add shared UI utilities, learning pages and interactive workspaces | Coding | Modified |  | FE pages and UI components | Phase 1 | Pending |  | 2026-10-07 | Reconstructed from frontend commits 015701d, b93604b on main. Date = latest Git author date in this work group, not confirmed work date. Author attribution, actual hours and PM approval require confirmation.
TL-014 | 2026-09-30 | Git: sonledz22 | WBS-007, WBS-019, WBS-020, WBS-021, WBS-022 | Record learning page and interactive-tool verification | Testing | Modified |  | UI verification work | Phase 1 | Pending |  | 2026-10-07 | Reconstructed from frontend commits 43f537b on main. Date = latest Git author date in this work group, not confirmed work date. Author attribution, actual hours and PM approval require confirmation. Commit subject is not proof of a permanent automated test suite.
TL-015 | 2026-10-01 | Git: hieuLeFpt | WBS-026, WBS-028, WBS-029, WBS-030, WBS-031, WBS-032 | Split Library and move activity/streak into User; remove Learning Support | Coding | Modified |  | Service-boundary migration | Phase 1 | Pending |  | 2026-10-07 | Reconstructed from backend commits 465f543, d762660, fec5d14, ab613b1 on main. Date = latest Git author date in this work group, not confirmed work date. Author attribution, actual hours and PM approval require confirmation. Related architectural change C-002.
TL-016 | 2026-10-01 | Git: hieuLeFpt | WBS-010, WBS-043, WBS-044, WBS-045, WBS-053 | Implement lesson content endpoints and learner answer-redaction guard | Coding | Modified |  | Content lesson APIs / security | Phase 1 | Pending |  | 2026-10-07 | Reconstructed from backend commits 34335aa, 20bed3b on main. Date = latest Git author date in this work group, not confirmed work date. Author attribution, actual hours and PM approval require confirmation.
TL-017 | 2026-10-01 | Git: hieuLeFpt | WBS-008, WBS-009, WBS-010, WBS-057 | Build Java Learning Service and lesson/mastery persistence | Coding | Modified |  | Java learning runtime | Phase 1 | Pending |  | 2026-10-07 | Reconstructed from backend commits d96ab9e, 8195982 on main. Date = latest Git author date in this work group, not confirmed work date. Author attribution, actual hours and PM approval require confirmation. Related runtime replacement C-003.
TL-018 | 2026-10-01 | Git: hieuLeFpt | WBS-014, WBS-016, WBS-017, WBS-057, WBS-058, WBS-059 | Implement review/test assignments, result consumer and objective grading | Coding | Modified |  | Core learning / assessment loop | Phase 1 | Pending |  | 2026-10-07 | Reconstructed from backend commits 72d4e99, dd109f5, c2ed0f4 on main. Date = latest Git author date in this work group, not confirmed work date. Author attribution, actual hours and PM approval require confirmation.
TL-019 | 2026-10-01 | Git: hieuLeFpt | WBS-010, WBS-011, WBS-046 | Seed Writing, Listening and Reading-hint learning content | Coding | Modified |  | Published demo curriculum | Phase 1 | Pending |  | 2026-10-07 | Reconstructed from backend commits 37a330c, 555ab81, a163b6b, 70f17a2 on main. Date = latest Git author date in this work group, not confirmed work date. Author attribution, actual hours and PM approval require confirmation.
TL-020 | 2026-10-02 | Git: hieuLeFpt | WBS-010, WBS-011, WBS-016, WBS-057 | Implement lesson essay grading, Listening media contract and hint visibility | Coding | Modified |  | Writing / Listening / Reading APIs | Phase 1 | Pending |  | 2026-10-07 | Reconstructed from backend commits d08337a, 896fa2c, 60c72dd on main. Date = latest Git author date in this work group, not confirmed work date. Author attribution, actual hours and PM approval require confirmation. Live LLM/media acceptance remains separate.
TL-021 | 2026-10-02 | Git: Lê Trung Hiếu | WBS-008, WBS-009, WBS-010, WBS-011, WBS-014, WBS-016, WBS-017, WBS-058, WBS-059 | Record backend MVP end-to-end acceptance evidence | Testing | Modified |  | Backend E2E report | Phase 1 | Pending |  | 2026-10-07 | Reconstructed from backend commits 9140128 on main. Date = latest Git author date in this work group, not confirmed work date. Author attribution, actual hours and PM approval require confirmation. See backend/plans/260930-2057-mvp-reading-writing-listening-roadmap/reports/e2e-261002-mvp-reading-writing-listening.md.
TL-022 | 2026-10-03 | Git: Lê Trung Hiếu | WBS-009, WBS-012, WBS-014, WBS-057 | Implement skill-local progress, required Practice and remediation ladder | Coding | Modified |  | Practice / review rules | Phase 1 | Pending |  | 2026-10-07 | Reconstructed from backend commits a3447b9, a90e5e1, 853ab82, 1a96c77, 8bb72cf, 6d9f623 on main. Date = latest Git author date in this work group, not confirmed work date. Author attribution, actual hours and PM approval require confirmation. Related business-rule change C-005.
TL-023 | 2026-10-02 | Git: Nguyen Viet Hoang | WBS-002, WBS-003, WBS-008, WBS-009, WBS-010, WBS-016, WBS-017, WBS-056 | Connect frontend main flow to backend and correct submission behaviour | Coding | Modified |  | HTTP auth and learning flow | Phase 1 | Pending |  | 2026-10-07 | Reconstructed from frontend commits 5505282, f1d5bb0 on main. Date = latest Git author date in this work group, not confirmed work date. Author attribution, actual hours and PM approval require confirmation.
TL-024 | 2026-10-05 | Git: sonledz22 | WBS-001, WBS-056 | Build home access-plan views/navigation and merge real authentication | Coding | Modified |  | Home/auth integration | Phase 1 | Pending |  | 2026-10-07 | Reconstructed from frontend commits 5a0abcb, ac25901 on main. Date = latest Git author date in this work group, not confirmed work date. Author attribution, actual hours and PM approval require confirmation. WBS Home Page remains Iteration 2; phase allocation requires PM confirmation.
TL-025 | 2026-10-05 | Git: Nguyen Viet Hoang | WBS-004, WBS-005 | Implement forgot/reset pages and align password length/confirmation | Coding | Modified |  | Password recovery UI | Phase 1 | Pending |  | 2026-10-07 | Reconstructed from frontend commits 553a320, 51e64eb on main. Date = latest Git author date in this work group, not confirmed work date. Author attribution, actual hours and PM approval require confirmation. WBS Reset Password remains Iteration 3; real email/OAuth acceptance is not proven.
TL-026 | 2026-10-05 | Git: Nguyen Viet Hoang | WBS-012, WBS-014, WBS-016, WBS-017 | Fix assessment question snapshot parsing and integrate Practice/review UI | Coding | Modified |  | Test runner / Practice / Review UI | Phase 1 | Pending |  | 2026-10-07 | Reconstructed from frontend commits d2b737d, 6716dd9 on main. Date = latest Git author date in this work group, not confirmed work date. Author attribution, actual hours and PM approval require confirmation.
TL-027 | 2026-10-05 | Git: Nguyen Viet Hoang | WBS-008, WBS-009, WBS-010, WBS-012, WBS-014, WBS-016, WBS-017 | Document browser core-flow checks and API-assisted fresh-user E2E | Testing | Modified |  | FE E2E reports | Phase 1 | Pending |  | 2026-10-07 | Reconstructed from frontend commits caaf987, 6716dd9 on main. Date = latest Git author date in this work group, not confirmed work date. Author attribution, actual hours and PM approval require confirmation. Same commit as TL-026 includes reports and code; hours must be split. Practice/review full unassisted browser flow remains unverified.
TL-028 | 2026-10-07 | Git: hieuLeFpt, Lê Trung Hiếu | Scope 1.1 / 2.2 / 3.3 | Complete requirements/data/NFR sections and record scope/BA review | Analyzing | Modified |  | Requirements and review reports | Phase 1 | Pending |  | 2026-10-07 | Reconstructed from backend commits b2323f1, f2e00d4, 36b1092 on main. Date = latest Git author date in this work group, not confirmed work date. Author attribution, actual hours and PM approval require confirmation. Document approval and actual authorship still require confirmation.
TL-029 | 2026-10-07 | Git: Lê Trung Hiếu | WBS-008, WBS-016, WBS-017, WBS-057 | Implement band courses, placement recommendations and course tests | Coding | Modified |  | Backend course extension | Phase 1 | Pending |  | 2026-10-07 | Reconstructed from backend commits d867758, 5926d93, 6935369, 559bf82, a401a33, 5ea098a on main. Date = latest Git author date in this work group, not confirmed work date. Author attribution, actual hours and PM approval require confirmation. Related C-006. Phase 1 inclusion and FE course delivery are pending, not accepted scope. WBS reference covers the baseline supporting function only; the retired prototype/course extension has no standalone accepted FDS screen.
TL-030 | 2026-10-07 | Git: hieuLeFpt | WBS-016, WBS-017, WBS-057 | Stabilize course-test timestamp fixture and add course demo content | Coding | Modified |  | Course test fix / demo seeds | Phase 1 | Pending |  | 2026-10-07 | Reconstructed from backend commits a078675, a18241b on main. Date = latest Git author date in this work group, not confirmed work date. Author attribution, actual hours and PM approval require confirmation. Follow-up after course merge; no new scope change inferred from this work. WBS reference covers the baseline supporting function only; the retired prototype/course extension has no standalone accepted FDS screen.
Hours Summary
Activity | Total Hours
Training | n.a.
Analyzing | n.a.
Designing | n.a.
Coding | n.a.
Testing | n.a.
Reviewing | n.a.
Deploying | n.a.
Meeting | n.a.
Grand Total | n.a.

## Defects
Defects — IELTSPath Phase 1
Fixed = implementation/report evidence; Closed requires retest. Pending = observation needs reproduction. Earlier-sheet template defects are recorded, not repaired.
# | Date Found | Defect Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Activity | Product | Product Details | Assigned By | Assigned To | Status | Fixed Date | Fixed In Version | Updated | Notes
D-001 | 2026-10-05 | Topic lesson mapper omitted practiceStatus | Complete lessons while Practice is REQUIRED; open topic. | Show remaining Practice gate and a clear next action. | Gate state was dropped from mapped lessons. | High | High | Testing / Review | Frontend | Topic mapper and final-test checklist | Repository review | FE owner | Fixed | 2026-10-05 |  | 2026-10-07 | frontend/plans/reports/e2e-main-flow-261005/fix-ux-cta-gates.md; frontend/plans/reports/e2e-practice-261005/report.md confirms gap closed; full fresh browser retest still open.
D-002 | 2026-10-05 | PRACTICE_REQUIRED error lacked actionable handling | Try to assign a test while Practice is required. | Explain remaining Practice, show lesson links, reload state. | Generic locked message did not explain Practice requirement. | High | High | Testing / Review | Frontend | Assignment error handling | Repository review | FE owner | Fixed | 2026-10-05 |  | 2026-10-07 | frontend/plans/reports/e2e-main-flow-261005/fix-ux-cta-gates.md; frontend/plans/reports/e2e-practice-261005/report.md
D-003 | 2026-10-05 | Pending reviews were not hydrated in topic view | Open a topic with pending review. | Load reviews, display review checklist, hide locked test CTA. | Learner could not see why the final test was locked. | High | High | Testing / Review | Frontend | Topic ReviewGate / GET reviews | Repository review | FE owner | Fixed | 2026-10-05 |  | 2026-10-07 | frontend/plans/reports/e2e-main-flow-261005/fix-ux-cta-gates.md; frontend/plans/reports/e2e-practice-261005/report.md browser smoke only.
D-004 | 2026-10-05 | Primary CTA click reliability requires fresh retest | Use accessibility-ref click on login or test CTA. | Accessible activation consistently reaches the button handler. | Automation sometimes missed; Enter or JS click completed the action. | Medium | Medium | Testing / Review | Frontend | Auth and learning primary CTA | Repository review | FE owner | Open |  |  | 2026-10-07 | frontend/plans/reports/e2e-main-flow-261005/fix-ux-cta-gates.md records layout fix, but frontend/plans/reports/e2e-main-flow-261005-fresh/report.md repeats observation. Application-wide reproduction is not established.
D-005 | 2026-10-05 | Assessment result accessibility snapshot omitted visible score details | Inspect result page accessibility tree after submit. | Score percent and correct-answer count are perceivable by assistive technology. | Interactive snapshot lacked percent/count despite visible UI text. | Medium | Medium | Testing / Review | Frontend | Result summary accessibility | Repository review | FE owner | Pending |  |  | 2026-10-07 | frontend/plans/reports/e2e-main-flow-261005/report.md item 5. Verify with a screen reader before confirming defect.
D-006 | 2026-10-07 | Dashboard open-item formulas point at incorrect status columns | Populate Q&A, Defects and Issues statuses; inspect Dashboard formulas. | Counts read Q&A K, Defects N, Issues K. | Template reads Q&A G, Defects H and Issues H. | Medium | High | Testing / Review | Tracking workbook | Dashboard D8, G5/C8 and F5/B8 | Repository review | PM / documentation owner | Open |  |  | 2026-10-07 | Original workbook formulas. Dashboard is before requested edit boundary and was preserved.
D-007 | 2026-10-07 | WBS/dashboard iteration summaries use wrong template columns | Compare WBS headers with Dashboard iteration COUNTIF/SUMIF formulas. | Iteration from WBS H, points from G, status from K. | Dashboard uses G for iteration, F for points and H for status. | Medium | Medium | Testing / Review | Tracking workbook | Dashboard C22:F24; WBS summaries are static | Repository review | PM / documentation owner | Fixed | 2026-10-07 |  | 2026-10-07 | Corrected during FDS-based WBS revision: Dashboard C22:G24 uses WBS H (iteration), G (points), K (status); WBS summary recalculates. Historical issue kept for traceability.
D-008 | 2026-10-07 | Scope summary counts and progress interpretation are inconsistent | Compare Scope headers and formulas with Dashboard deliverable counts. | Count statuses in Scope G and treat effort usage separately from completion. | Dashboard reads Scope F as status; Scope % Complete is actual/estimated effort. | Medium | Medium | Testing / Review | Tracking workbook | Scope F and Dashboard B5:E5 | Repository review | PM / documentation owner | Open |  |  | 2026-10-07 | Original Scope/Dashboard. No silent changes made before Q&A.

## Issues
Issues — IELTSPath Phase 1
Current gaps consolidated 07/10/2026. Owners are responsible roles proposed for PM assignment. Due/closed dates remain blank without evidence.
# | Date | Issue Description | Category | Priority | Impact (Scope / Effort / Timeline) | Raised By | Owner | Due Date | Resolution | Status | Closed Date | Notes
I-001 | 2026-10-07 | Phase 1 boundary is not explicitly baselined against WBS. | Scope | High | Acceptance and phase reporting may use different feature populations. | Project review | PM / supervisor |  | Confirm MVP versus WBS Iteration 1. Record approved features and phase cut-off. Link Q-001. | Open |  | docs/test-plan/IELTS_Space_Test_Plan_v1.docx; original WBS
I-002 | 2026-10-07 | Actual member hours and approved timesheets were not supplied. | Process | High | Approved actual effort and productivity cannot be calculated. | Project review | PM / team members |  | Collect reporter, work date, actual hours and approval for every TimeLogs row. Link Q-014. | Open |  | Original tracking workbook contains unrelated sample hours and reporter.
I-003 | 2026-10-07 | Full fresh-user browser Practice/review/pass-to-next-topic flow lacks evidence. | Technical | High | Core MVP acceptance has an unverified UI segment. | Project review | QA / FE owner |  | Run without API gate clearance: lesson, first Practice submit, failed Practice review, pass test, next topic. Capture artifacts. | Open |  | frontend/plans/reports/e2e-main-flow-261005-fresh/report.md; frontend/plans/reports/e2e-practice-261005/report.md
I-004 | 2026-10-07 | Live Writing feedback quality and Listening media acceptance are unverified. | Technical | High | Writing quality and audio demo readiness cannot be concluded from UI/API wiring. | Project review | QA / content owner |  | Review real essays against rubric and play configured audio; verify timeout, points retry and transcript visibility. | Open |  | docs/test-plan/IELTS_Space_Test_Plan_v1.docx; frontend/plans/reports/e2e-practice-261005/report.md
I-005 | 2026-10-07 | Test Plan v1 describes FE as mock-only despite later HTTP E2E evidence. | Process | High | Test scope and traceability no longer match the integrated FE. | Project review | QA / documentation owner |  | Update FE baseline, integration scope and acceptance matrix after Phase 1 scope confirmation. | Open |  | docs/test-plan/IELTS_Space_Test_Plan_v1.docx TP-FE / Out of Scope versus frontend/plans/reports/e2e-main-flow-261005-fresh/report.md
I-006 | 2026-10-07 | Premium enforcement is absent in the current learning MVP. | Scope | High | Paid content cannot be accepted as protected solely by FE labels. | Project review | Product owner / backend lead |  | Confirm free-only demo scope or implement entitlement checks as an approved follow-up before paid release. | Open |  | backend/docs/fe-main-flow-guide.md §6; docs/test-plan/IELTS_Space_Test_Plan_v1.docx
I-007 | 2026-10-07 | Course backend has no corresponding FE course API and live acceptance smoke. | Technical | Medium | End-to-end course recommendation and course-test completion remain incomplete. | Project review | PM / BE / FE leads |  | Allocate to Phase 1 or later, wire FE course calls and run Gateway-to-course result smoke. Link Q-011. | Open |  | backend/plans/261006-2228-course-band-levels/plan.md final concerns; frontend/src/features/learning-path/api/learningApi.ts
I-008 | 2026-10-07 | SRS/TDS metadata and formal approval records remain incomplete. | Process | Medium | Cannot substantiate a formally approved requirement/design baseline. | Project review | PM / supervisor |  | Fill authors, reviewers, dates and approval references; reconcile Report 1, SRS and implementation. | Open |  | backend/capstone-docs/rp_3.0_system-requirements-system/Report 3.0_SRS_IELTSPath_IeltsPath_v1.docx metadata; backend/capstone-docs/rp_1_vision-scope/Report 1_Vision_Scope_IeltsPath.docx In Review; original Scope Approved By is not approval evidence.
I-009 | 2026-10-07 | Reset UI wiring exists but email delivery and OAuth acceptance are not evidenced. | External | Medium | Real password recovery and social login must not be reported as accepted. | Project review | Auth owner / QA |  | Keep OAuth disabled until implementation/QA. Verify email token delivery, reset and login separately. WBS places reset in Iteration 3. | Open |  | frontend/docs/journals/2026-10-05-fe-auth-forgot-reset-wiring.md; docs/test-plan/IELTS_Space_Test_Plan_v1.docx

## Risks
Risks — IELTSPath Phase 1
Probability / Impact: High=3, Medium=2, Low=1. Score=P×I: ≥6 Critical, 4–5 High, 2–3 Medium, 1 Low. Due dates require PM agreement.
# | Risk Description | Category | Probability | Impact | Risk Score (P×I) | Mitigation Plan | Contingency Plan | Owner | Due Date | Status | Notes
R-001 | Scope expands from the core MVP to every full-product feature before Phase 1 acceptance. | Scope | High | High | 9 | Baseline phase requirements; keep course/multi-skill/Speaking/mobile allocation explicit. | Replan approved changes and defer unaccepted extensions. | PM / product owner |  | Open | backend/capstone-docs/rp_1_vision-scope/Report 1_Vision_Scope_IeltsPath.docx versus docs/test-plan/IELTS_Space_Test_Plan_v1.docx; assessment: project-review judgement, not measured incidence.
R-002 | Frontend and backend gates or DTOs drift during course and lesson changes. | Technical | Medium | High | 6 | Review contract fields and error codes; run fresh-user integration after changes. | Keep the validated MVP baseline until compatible changes pass. | BE / FE leads |  | Open | backend/docs/fe-main-flow-guide.md; backend/plans/261006-2228-course-band-levels/plan.md; backend/plans/261006-2309-multi-skill-lessons/plan.md; assessment: project-review judgement, not measured incidence.
R-003 | LLM timeout, cost or grading inconsistency disrupts Writing feedback. | External | Medium | High | 6 | Validate rubric/corpus, timeout, quota and point idempotency; keep provider secrets server-side. | Report grading unavailable and support safe retry without duplicate debit. | Writing owner / QA |  | Open | docs/test-plan/IELTS_Space_Test_Plan_v1.docx TP-LRN-06 / NFR-P02; backend/docs/fe-main-flow-guide.md; assessment: project-review judgement, not measured incidence.
R-004 | RabbitMQ retries or result replay produces stale or duplicate learning progress. | Technical | Medium | High | 6 | Test consumer version/idempotency, ACK-after-commit, retry and DLQ with real infrastructure. | Investigate failed events and replay through the existing idempotent consumer. | Backend lead |  | Open | docs/test-plan/IELTS_Space_Test_Plan_v1.docx TP-LRN-05 / NFR-REL01; assessment: project-review judgement, not measured incidence.
R-005 | Protected content or answers are exposed through role, ownership or route mistakes. | Security | Medium | High | 6 | Run JWT, ownership, /internal route and answer-redaction cases through Gateway. | Block affected flow and fix authorization before acceptance. | Backend lead / QA |  | Open | docs/test-plan/IELTS_Space_Test_Plan_v1.docx NFR-SEC01 / TP-LRN-02; assessment: project-review judgement, not measured incidence.
R-006 | Missing media or question-pool data blocks a demo or remediation path. | Resource | Medium | High | 6 | Prepare validated audio URLs and unrevealed Practice/review packages before each cycle. | Use another real published package or document the blocked scenario. | Content owner |  | Open | backend/docs/fe-main-flow-guide.md; docs/test-plan/IELTS_Space_Test_Plan_v1.docx Data constraints; assessment: project-review judgement, not measured incidence.
R-007 | Docker or environment drift causes skipped integration tests to be reported as passes. | Technical | Medium | High | 6 | Record commits/config and Docker readiness; separate Passed, Skipped and Not Run. | Restore documented environment and rerun required integration tests. | QA / infrastructure owner |  | Open | docs/test-plan/IELTS_Space_Test_Plan_v1.docx NFR-OPS01; backend/plans/261006-2228-course-band-levels/plan.md verification; assessment: project-review judgement, not measured incidence.
R-008 | Insufficient browser coverage allows blocked controls or inaccessible feedback to escape. | Quality | Medium | Medium | 4 | Run fresh-user UI, keyboard, viewport and screen-reader checks on core screens. | Prioritize blocking usability fixes and rerun the affected flow. | FE owner / QA |  | Open | frontend/plans/reports/e2e-main-flow-261005-fresh/report.md; frontend/plans/reports/e2e-main-flow-261005/report.md; assessment: project-review judgement, not measured incidence.
R-009 | A key team member becomes unavailable before Phase 1 review. | Resource | Low | High | 3 | Document service contracts and share setup knowledge across the team. | PM reassigns remaining work and negotiates review schedule. | PM |  | Open | Original Risks R-002 adapted to Phase 1; no actual absence recorded.; assessment: project-review judgement, not measured incidence.
R-010 | Performance and operational targets are assumed from functional smoke results. | Quality | Medium | Medium | 4 | Agree test workload and measure non-LLM latency separately from provider latency. | Record unmet targets and obtain a scoped acceptance decision. | QA / backend lead |  | Open | docs/test-plan/IELTS_Space_Test_Plan_v1.docx NFR-P01/P02; SRS Part 6; assessment: project-review judgement, not measured incidence.
R-011 | A paid release uses UI premium flags without server entitlement enforcement. | Security | Medium | High | 6 | Resolve I-006 before accepting paid premium access. | Limit Phase 1 demo to explicitly free content. | Product owner / backend lead |  | Open | backend/docs/fe-main-flow-guide.md §6; assessment: project-review judgement, not measured incidence.

## ChangeLog
ChangeLog — IELTSPath Phase 1
Requirement, architecture and contract changes only. Routine setup/coding/testing stays in TimeLogs. Implemented does not mean formally approved or accepted for Phase 1.
# | Date | Change Description | Requested By | Affects (SRS/WBS/Code) | Impact on Scope | Impact on Effort (pds) | Impact on Timeline | Priority | Approved By | Status | Notes
C-001 | 2026-09-22 | Change auth transport to support HttpOnly cookies while retaining request-body refresh compatibility. | Not recorded | Auth API / FE session contract / security configuration | Changes login/refresh/logout token delivery. Baseline setup itself stays in TimeLogs. |  | Implemented in Git; no substantiated schedule change. | High |  | Implemented | backend 2c9d37f; TimeLogs TL-008. Recorded date comes from Git/docs, not an approval date. Measured effort delta and formal approver unavailable.
C-002 | 2026-10-01 | Change service ownership: separate Library from Content, move activity/streak to User and retire Learning Support. | Repository architecture plan; requester unconfirmed | TDS / service boundaries / databases / Gateway routes | Redistributes existing capabilities across bounded contexts. |  | Migration and routing work required; no approved time delta supplied. | High |  | Implemented | backend 465f543, d762660, fec5d14, ab613b1; 4350505 records catalog-migration approval specifically. TimeLogs TL-015. Recorded date comes from Git/docs, not an approval date. Measured effort delta and formal approver unavailable.
C-003 | 2026-10-01 | Replace Python AI Learning runtime with Java Learning Service. | Runtime-replacement plan; requester unconfirmed | Architecture / deployment / learning persistence and APIs | Retires the historical Python runtime and ports the core learning flow to Java. |  | Historical prototype work remains in TimeLogs; no reliable schedule delta. | High |  | Implemented | backend 746e7dc plan, d96ab9e skeleton, 23904e8 retirement docs. TimeLogs TL-011, TL-017, TL-018. Recorded date comes from Git/docs, not an approval date. Measured effort delta and formal approver unavailable.
C-004 | 2026-10-01 | Extend lesson contract with ESSAY blocks and Writing submissions with LLM grading and points. | Writing contract/roadmap; requester unconfirmed | SRS / lesson contract / Content / Learning / Access | Adds essay-answer semantics, Writing rubric grading, quota and point-charge/retry rules. |  | Requires implementation and acceptance across services; hours/delay not inferred. | High |  | Implemented | backend 4fc7be6 contract, f2dfc72 contract approval record, d08337a implementation. TimeLogs TL-019–020. Approval source applies only to that contract. Recorded date comes from Git/docs, not an approval date. Measured effort delta and formal approver unavailable.
C-005 | 2026-10-03 | Change progression rules to skill-local gates, required lesson Practice and theory/remediation review without revealed-package reuse. | Skill-tracks plan; requester unconfirmed | SRS / Content ownership rules / Learning gates / FE workflow | Lesson completion alone no longer unlocks final tests. Reviews are scoped by skill and unrevealed evidence rules. |  | BE recorded 03/10; FE followed 05/10. No measured delay asserted. | High |  | Implemented | backend a3447b9, 853ab82, 1a96c77, 8bb72cf, 6d9f623; frontend 6716dd9. TimeLogs TL-022, TL-026. Recorded date comes from Git/docs, not an approval date. Measured effort delta and formal approver unavailable.
C-006 | 2026-10-07 | Add band-level courses, optional placement recommendations and a non-blocking course final test. | Mentor/product-owner decisions recorded in course plan | SRS / TDS / Content / Learning / Assessment contracts | Courses group ordered topics by band; recommendation does not lock access. FE integration/Phase 1 allocation unconfirmed. |  | Backend merged 07/10; no accepted Phase 1 delivery delta. | High |  | Implemented | backend d867758, 559bf82, a401a33, 5ea098a; merge df6c57f (#45); backend/plans/261006-2228-course-band-levels/plan.md decisions. TimeLogs TL-029–030. Recorded date comes from Git/docs, not an approval date. Measured effort delta and formal approver unavailable.
C-007 | 2026-10-07 | Revise Vision & Scope to reflect mentor feedback and the full product feature set. | Mentor feedback recorded in Report 1 history | Report 1 / SRS traceability / phase allocation | Full product scope includes future features. This document revision does not prove their implementation or Phase 1 acceptance. |  | Reconcile phase baseline before approval. | High |  | In Review | Report 1 v1.1.0 dated 07/10/2026; backend 36b1092 records the supporting BA/vision review. TimeLogs TL-028. Recorded date comes from Git/docs, not an approval date. Measured effort delta and formal approver unavailable.
C-008 | 2026-10-06 | Propose multi-skill lessons and assessment AI essay grading as a future extension. | Multi-skill plan; formal requester/approver unconfirmed | Content / Learning / Assessment contracts and planned SRS changes | Pending extension, not an implemented change or completed Phase 1 work item. |  | Plan remains pending; no actual implementation TimeLog inferred. | High |  | Pending | backend/plans/261006-2309-multi-skill-lessons/plan.md; refresh recorded in ddef7d5 on 07/10. Plan date is 06/10. Recorded date comes from Git/docs, not an approval date. Measured effort delta and formal approver unavailable.