Project Management Plan

English Learning and IELTS Preparation Support System Based on Personalized Learning Pathways for IELTS Space

- Report 2 -

| Project Name | English Learning and IELTS Preparation Support System Based on Personalized Learning Pathways for IELTS Space |
| --- | --- |
| Vision & Scope Ref | Report 1 – Vision & Scope v1.0.0 (09/10/2026) |
| RTW Ref | Report 3.1 – Requirements Traceability Workbook v1.0.0 |
| Plan Version | v1.0.0 |
| Date Created | 14/09/2026 |
| Last Updated | 09/10/2026 |
| Author(s) | HieuLT, SonLH, HoangNV, TungVPH, PhuPD |
| Reviewer(s) | LinhNDM |
| Status | Approved |

1. Overview

1.1 Cost/Time Estimation

| # | Work Package | Est. Effort (wds) | Deadline |
| --- | --- | --- | --- |
| Stage 1: Project Initiating (Week 1) |  |  |  |
| 1.1 | Finalize the website/mobile scope, assign team members, define service responsibilities, and complete Report 1. | 2 | Week 1 |
| Stage 2: Project Planning & Initial Requirements (Weeks 2–3) |  |  |  |
| 2.1 | Report 2: Project Management Plan v1.0 | 3 | Week 2 |
| 2.2 | Report 3: SRS – Overall Requirements, User Roles, and Key Functionality | 4 | Week 2 |
| 2.3 | Vertical Prototype – Demo code: Create the backend structure, website/mobile; demo a request from the interface through the Gateway to the service and receive a response. | 5 | Week 3 |
| Stage 3: Software Design (Weeks 4–5) |  |  |  |
| 3.1 | Vertical Prototype – POC: Testing database connectivity and RabbitMQ communication. | 4 | Week 4 |
| 3.2 | Report 3 – SRS v1.0: Complete the functional and non-functional requirements specification; describe in detail the use cases, business flows, and business rules of the system. | 4 | Week 4 |
| 3.3 | Report 4 – SDS v1.0, overall design: Design the architecture of microservices, ERD, and data specific to each service; describe APIs, events, and website/mobile structure using Draw.io. | 5 | Week 5 |
| 3.4 | Report 5 – Test Plan: Define the scope, environment, data, testing methods, and completion criteria for the backend, website, and mobile platforms. | 3 | Week 5 |
| Stage 4: Implementation (Weeks 6–11) |  |  |  |
| 4.1 Implementation Iteration 1 (Weeks 6–7) |  |  |  |
| 4.1.1 | Report 4 – SDS v1.1: Detailed design of User, Content, and Learning Services; student profiles, learning paths, learning objectives, lessons, and progress; design of basic access rights for the Access Service. | 4 | Week 6 |
| 4.1.2 | Code Package & Unit Testing Report: Implement login, profile, and learning objectives; basic learning content; create a learning roadmap. Allow students to access each section, start a lesson, and save basic progress; integrate website/mobile interface and unit tests. | 32 | Week 6 |
| 4.1.3 | Report 5 – Integration Test Cases: Build a login test case → import target → create roadmap → open learning objective → learn and save progress; check data ownership. | 4 | Week 7 |
| 4.1.4 | Report 5 – Integration Test Report: Perform first-round testing, record results, fix bugs, and retest. | 6 | Week 7 |
| 4.1.5 | Report 3 – SRS v1.1: The requirements for iteration 2 include details about the assignment, AI/grader selection, results, error analysis, personal library, and notifications. | 4 | Week 7 |
| 4.1.6 | Software Package Version 1: The delivered runtime allows students to log in, create study plans, learn each module, and view their basic progress. | 2 | Week 7 |
| 4.2 Implementation Iteration 2 (Weeks 8–9) |  |  |  |
| 4.2.1 | Report 4 – SDS v1.2: Detailed design of Assessment, Library, and Notification flows; API, data, and RabbitMQ events. | 3 | Week 8 |
| 4.2.2 | Code Package & Unit Testing Report: Implement IELTS four-skills testing, select AI/markers, generate results and analyze errors; connect results with Learning Services. Implement vocabulary/video catalogs, flashcards, decks, notes, video progress, saved segments, and notifications; integrate interface and unit tests. | 34 | Week 8 |
| 4.2.3 | Report 5 – Integration Test Cases: Check exam questions → submit → results → update competency information; save to personal library, continue learning and receive notifications via RabbitMQ. | 4 | Week 8 |
| 4.2.4 | Report 5 – Integration Test Report: Perform phase 2 testing; verify results, progress, libraries, and handle errors or duplicates. | 6 | Week 9 |
| 4.2.5 | Report 3 – SRS v1.2: Details of Round 3 requirements regarding route adjustments, review materials, mastery, usage packages, points, games, and community. | 4 | Week 9 |
| 4.2.6 | Software Package Version 2: The learning flow is delivered according to a roadmap that includes tests, results, error analysis, libraries, and notifications. | 2 | Week 9 |
| 4.3 Implementation Iteration 3 (Weeks 10–11) |  |  |  |
| 4.3.1 | Report 4 – SDS v1.3: Complete Access Service; design Game and Community Service. | 3 | Week 10 |
| 4.3.2 | Code Package & Unit Testing Report: Complete the activity/streak. Finalize the package, subscription, activation key, and points; deploy game rooms, game sessions, WebSockets, posts, comments, and moderation; perform interface and unit testing. | 32 | Week 10 |
| 4.3.3 | Report 5 – Integration Test Cases: Check usage rights based on packages, points, game sessions, and community streams. | 5 | Week 10 |
| 4.3.4 | Report 5 – Integration Test Report | 6 | Week 11 |
| 4.3.5 | Report 5 – System Test Cases: Develop system-wide test cases, prioritizing personalized learning flows across website/mobile and support functions. | 5 | Week 11 |
| 4.3.6 | Software Package Version 3: The product will be delivered with all the necessary functions within the scope of development, and the system will be ready for testing. | 2 | Week 11 |
| Stage 5: Verification & Validation (Weeks 12–13) |  |  |  |
| 5.1 | Report 5 – System Test Report: Test the entire system, access control, basic performance, and website/mobile; prioritize fixing bugs that hinder roadmap creation, learning, and progress saving. | 12 | Week 12 |
| 5.2 | Report 6 – User Guides: Instructions for installation, configuration, and usage; clearly describing how to create a learning path, study each module, take tests, and track progress. | 5 | Week 12 |
| 5.3 | Acceptance Test and Support: Acceptance testing involves following user workflows, receiving feedback, fixing bugs, and verifying acceptance criteria. | 10 | Week 13 |
| 5.4 | Final Software Package: Hand over the software, source code, configuration, documentation, and test results; check for reinstallability. | 4 | Week 13 |
| Stage 6: Closing (Week 14) |  |  |  |
| 6.1 | Report 7 – Final Project Report: Summarize the results against the goals, the actual effort put in, the limitations, and the direction for future development. | 4 | Week 14 |
| 6.2 | Presentation and demonstration | 4 | Week 14 |

1.2 Project Objectives

| # | Metric | Unit | Planned | Actual | Notes / References |
| --- | --- | --- | --- | --- | --- |
| 1 | The MVP function acceptance scenario meets the requirements. | % | 100% of test cases in the Must-Pass category must pass; the pass rate for all test cases undergoing acceptance testing must be at least 95%; at the time of acceptance testing, there should be no Critical or High level defects remaining in an unprocessed state. |  | Test results and bug list |
| 2 | Security testing meets requirements. |  | 100% of required security test cases passed; no critical/high-level vulnerabilities remained unpatched upon acceptance. This included testing authentication and authorization, data access, SQL Injection/XSS, password and sensitive data protection, security configuration, and anti-guessing measures. |  | Security test report, vulnerability list, and fix results. |
| 3 | API response speed | Time | 95% of primary requests that do not call the LLM respond within ≤ 2 seconds with 100 concurrent users (SRS NFR-P01). |  | Load test results |
| 4 | User access | Single user | ≥ 200 in the last 4 weeks of beta testing. |  | Website/app statistics |

1.3 Project Risks

| # | Risk Description | Impact | Possibility | Priority | Response Plans (Mitigation / Contingency) |
| --- | --- | --- | --- | --- | --- |
| 1 | Integrating DeepTutor proved more difficult than expected, resulting in slower personalization functionality. | H | M | H | Mitigation: Try the early application submission process and receive your roadmap. Contingency: Use the sample learning plan developed by the teacher during the remedial period. |
| 2 | AI generates learning paths or questions that are not appropriate for the learner's level and goals. | H | M | H | Mitigation: Standardize input data and check results against sample student records. Contingency: Allow teachers to edit or replace inappropriate content. |
| 3 | The team underestimated the time constraints and failed to complete the tasks on time. | H | M | H | Mitigation: Break down tasks, prioritize functions, and check progress weekly. Contingency: Adjust the assignments, moving less important functions to a later version. |

2. Management Approach

2.1 Project Processes

The team employs an iterative development approach, dividing the work into two-week phases. At the beginning of each phase, the team defines objectives, prioritizes functionalities, and assigns tasks. Throughout the process, members update progress and discuss any difficulties encountered. At the end of each phase, the team integrates, tests, and evaluates the results to adjust the plan for the next phase.

| Management activities | How to do it |
| --- | --- |
| Scope management | Identify the functions in the current version. These functions are prioritized to focus resources on the main requirements. |
| Change management | Requests for adding or modifying functionality are documented and discussed within the team. The team assesses the impact on workload, design, and deadlines before deciding whether to include it in the current development cycle or move it to the next. |
| Time management | Each task has a designated person, deadline, and expected outcome. The team checks progress weekly; tasks at risk of falling behind are reassigned or broken down into smaller parts to minimize impact on related work. |

2.2 Quality Management

The quality control team oversees the entire process of analysis, development, and testing. Each function requires clear requirements and acceptance criteria so that team members agree on how to implement and evaluate the results.

| Work | How to do it |
| --- | --- |
| Error prevention | Review requirements and design before programming; agree on data structures and APIs between frontend and backend. Anticipate scenarios such as connection loss and multiple submission attempts. |
| Cross-checking | Code is reviewed by at least one other member before being merged into the common branch. The review includes correctness, readability, error handling, and access control checks. |
| Unit testing | Test critical logic such as scoring based on answers, managing submission status, saving results, and processing roadmap data… |
| Integration and functional testing | Check the workflow from selecting the topic, completing the assignment, submitting it, transferring to the chosen grading method, and viewing the results. Also check the workflow for creating a study plan, following the plan, and updating progress. |
| Code standards | Maintain consistency in naming conventions, directory structure, code formatting, and API responses. Do not include passwords or service keys in the source code. |
| Defect management and acceptance testing | Record the error along with the re-implementation step, severity level, and responsible person. The error is re-tested after being fixed. The functionality is only considered complete when it meets the acceptance criteria and there are no more critical errors affecting the main workflow. |

2.3 Project Training Plan

The team organizes internal training and practice sessions to enhance knowledge of microservices architecture, inter-service communication, and system deployment. The practice content is linked to the functionalities of the IELTS platform so that members can directly apply it to their projects.

| Training Area | Participants | When / Duration |
| --- | --- | --- |
| Microservices architecture: Segmenting services, defining responsibilities for each service, and managing data separately. | All members | Week 1 / 1 session, 2 hours |
| Communication between services: REST API, OpenFeign, handling timeouts and errors when dependent services are unresponsive. | Backend members | 2 sessions per week, 2 sessions, 1 hour each. |
| Security in microservices: JWT, Gateway authentication, service-specific authorization, and internal API protection. | Backend members | 2 sessions per week, 2 hours each. |
| RabbitMQ: Producer, consumer, exchange, queue; handling asynchronous operations, retrying, error queuing, and avoiding duplicate message processing. Practice the workflow of sending requests, parsing work, and receiving results. | Backend member and AI manager | Week 3 / 2 sessions, 2 hours each |

3. Responsibility Assignments

The matrix uses RACI: R = Responsible (does the work), A = Accountable (owns and approves the result; one per work package), C = Consulted (gives input before the work is done), I = Informed (kept up to date). A/R means the same member is accountable and does the work.

| Work Package | PhuPD | HieuLT | SonLH | HoangNV | TungVPH |
| --- | --- | --- | --- | --- | --- |
| 1.1 Report 1 – Vision & Scope | C | A/R | C | C | R |
| Report 2.0 – Project Management Plan | R | A | I | I | R |
| Report 2.1 – Project Tracking | C | A/R | I | I | R |
| 2.2, 3.2 Report 3 – SRS & requirements traceability | C | A/R | R | R | R |
| 2.3, 3.1 Vertical prototype & POC | C | A/R | R | R | C |
| 3.3 Report 4 – SDS (architecture, database, API, events) | R | A/R | C | C | R |
| 3.4 Report 5 – Test Plan | R | A | C | R | R |
| Infrastructure: Config Server, Eureka, Gateway, Docker, PostgreSQL, RabbitMQ | C | A/R | I | I | C |
| User Service: accounts, authentication, profile, activity & streak | C | A/R | C | C | C |
| Content & Library Services: topics, lessons, questions, vocabulary, video | C | A/R | I | I | R |
| Learning Service: course path, practice, review, mastery | C | A/R | C | C | C |
| Assessment & Access Services: tests, grading, activation keys, points | R | A | I | C | C |
| Game, Community & Notification Services | R | A | C | C | R |
| Website & mobile UI | I | A | R | R | I |
| Frontend–backend integration: main learning flow, auth, practice, review | C | A | R | R | C |
| Integration & system testing, defect tracking | R | A/R | R | R | R |
| 5 Verification & acceptance: system test report, user guides, UAT | R | A/R | R | R | R |
| 6 Closing: final report & presentation | R | A/R | R | R | R |

4. Project Communications

| Communication Item | Who / Target | Owner | Purpose | When / Frequency | Type / Tool |
| --- | --- | --- | --- | --- | --- |
| Daily sync | Implementers | Project Lead | Progress and blockers | Daily / 15 min | Google Meet |
| Weekly review | Team + reviewer | Project Lead | Demo, risks, baseline | Weekly | Google Meet + Jira |
| PR / test review | Developer + QA | Package owner | Review code, test results, and acceptance criteria | Per package | GitHub PR + test report + Jira |

5. Configuration Management

5.1 Document Management

All project documents, including reports, requirements specifications, design documents, and test documents, will be stored in a shared folder on Microsoft OneDrive. Documents will be organized into subfolders by document type and project phase.

5.2 Source Code Management

The backend source code is managed using Git and centrally stored in a GitHub repository. Microservices are organized into separate folders under the services directory, which keeps each service’s code separate and makes development and maintenance easier. Changes are made on the functional branch and a pull request is sent for review before being merged into the main branch.

5.3 Tools & Infrastructure

| Category | Tools / Infrastructure |
| --- | --- |
| Technology | Java, Spring Boot for backend; Spring Cloud for microservices; React for frontend. |
| Microservices infrastructure | Spring Cloud Gateway, Eureka Service Registry, Spring Cloud Config, OpenFeign. |
| Database | PostgreSQL; separate service-owned databases; Flyway migrations |
| IDEs / Editors | IntelliJ IDEA, Visual Studio Code. |
| Diagramming | Draw.io: to build system architecture diagrams, database diagrams, and diagrams describing functions, interactions, and processing flows. |
| Documentation | Google Docs, Google Sheets |
| Version Control | Git and GitHub |
| Deployment Server |  |
| Project Management |  |