## Dashboard
IELTSPath — Project Tracking Dashboard
Auto-summary from all tracking sheets · Update data in individual sheets
Total Deliverables | Done / Closed | In Progress | Not Started | Open Issues | Open Defects
32 | 8 | 0 | 24 | 9 | 3
Open Issues | Open Defects | Unanswered Q&As | High/Critical Risks
9 | 3 | 8 | 10
Scope Milestone Status
Stage | Key Deliverable | Deadline | In Charge | Status
Stage 1 | Report 1 (Project Introduction) | Week 1 | PhuPD | Done
Stage 2 | SRS v0.9 + Project Management Plan | Week 3 | All team | Done
Stage 3 | SDS v1.0 + Test Planning | Week 5 | All team | Done
Stage 4 | Implementation Iterations 1–3 | Week 11 |  | Not Started
Stage 5 | System Test Report + User Guides + UAT | Week 13 |  | Not Started
Stage 6 | Final Report + Presentation | Week 14 |  | Not Started
WBS by Iteration
Iteration | Planned Functions | Est. Effort (pts) | Done | In Progress | % Complete
Iteration 1 | 39 | 224 | 22 | 17 | 56.4103
Iteration 2 | 18 | 94 | 0 | 7 | 0
Iteration 3 | 25 | 133 | 0 | 0 | 0
Last updated: 09/10/2026 ¦ Project: English Learning and IELTS Preparation Support System Based on Personalized Learning Pathways for IELTS Space ¦ PM: LinhNDM

## Scope
Scope — Project Deliverables & Milestones
Track all deliverables by stage · Update Status and Actual Effort each week · % Complete auto-calculated
# | Work Package / Deliverable | In Charge | Est. Effort (pds) | Deadline | % Complete | Status | Actual Effort (pds) | Dependency | Approved By | Notes
Stage 1: Project Initiating (Week 1)
1.1 | Report 1 — Project Introduction | PhuPD | 2 | Week 1 | 100 | Done | 2 |  | LinhNDM
Stage 2: Project Planning & Initial Requirements (Weeks 2–3)
2.1 | Report 2 — Project Management Plan v1.0 | PhuPD, HieuLT, TungVPH | 3 | Week 2 | 100 | Done | 3 | 1.1, 2.1 | LinhNDM | Planning, roles, timeline, risk, communication, tracking
2.2 | Report 3 — SRS v0.9 (Overall Requirements) | All team | 4 | Week 3 | 100 | Done | 4 | 1.1 | LinhNDM | Scope, actors, functional requirements finalized
2.3 | Vertical Prototypes (Code Demo) | BE + FE | 5 | Week 3 | 100 | Done | 5 | 2.1 | LinhNDM | Demonstrate a small end-to-end flow to prove the stack works.
Stage 3: Software Design (Weeks 4–5)
3.1 | Vertical Prototypes (POC / Proof of Concepts) | BE + FE | 4 | Week 4 | 100 | Done | 4 | 2.2 | LinhNDM | Develop a Proof of Concept (POC) for technical components that involve risk or uncertainty.
3.2 | Report 3 — SRS v1.0 (Detailed — Iteration 1) | All team | 4 | Week 4 | 100 | Done | 4 | 2.1, 3.2 | LinhNDM | Detailed requirements for features to be implemented in Iteration 1
3.3 | Report 4 — SDS v1.0 (High Level Design) | PhuPD, HieuLT, TungVPH | 5 | Week 5 | 100 | Done | 5 | 2.1, 2.2 | LinhNDM | Architecture, service/module, DB high-level, API/interface, deployment overview
3.4 | Report 5 — Test Planning | PhuPD | 3 | Week 5 | 100 | Done | 3 | 2.1, 3.2 | LinhNDM | Test strategy, test types, environment, entry/exit criteria, responsibilities
Stage 4a: Implementation — Iteration 1 (Weeks 6–7)
4.1.1 | Report 4 — SDS v1.1 (Detailed Design) |  |  | Week 6 |  | Not Started
4.1.2 | Code Package & Unit Testing Report — Iteration 1 |  |  | Week 6 |  | Not Started
4.1.3 | Report 5 — Integration Test Cases — Iteration 1 |  |  | Week 6 |  | Not Started
4.1.4 | Report 5 — Integration Test Report — Iteration 1 |  |  | Week 7 |  | Not Started
4.1.5 | Report 3 — SRS v1.1 (Detailed — Iteration 2) |  |  | Week 7 |  | Not Started
4.1.6 | Software Package Version 1 |  |  | Week 7 |  | Not Started
Stage 4b: Implementation — Iteration 2 (Weeks 8–9)
4.2.1 | Report 4 — SDS v1.2 |  |  | Week 8 |  | Not Started
4.2.2 | Code Package & Unit Testing Report — Iteration 2 |  |  | Week 8 |  | Not Started
4.2.3 | Report 5 — Integration Test Cases — Iteration 2 |  |  | Week 8 |  | Not Started
4.2.4 | Report 5 — Integration Test Report — Iteration 2 |  |  | Week 9 |  | Not Started
4.2.5 | Report 3 — SRS v1.2 (Detailed — Iteration 3) |  |  | Week 9 |  | Not Started
4.2.6 | Software Package Version 2 |  |  | Week 9 |  | Not Started
Stage 4c: Implementation — Iteration 3 (Weeks 10–11)
4.3.1 | Report 4 — SDS v1.3 |  |  | Week 10 |  | Not Started
4.3.2 | Code Package & Unit Testing Report — Iteration 3 |  |  | Week 10 |  | Not Started
4.3.3 | Report 5 — Integration Test Cases — Iteration 3 |  |  | Week 10 |  | Not Started
4.3.4 | Report 5 — Integration Test Report — Iteration 3 |  |  | Week 11 |  | Not Started
4.3.5 | Report 5 — System Test Cases |  |  | Week 11 |  | Not Started
4.3.6 | Software Package Version 3 |  |  | Week 11 |  | Not Started
Stage 5: Verification & Validation (Weeks 12–13)
5.1 | Report 5 — System Test Report |  |  | Week 12 |  | Not Started
5.2 | Report 6 — User Guides (Installation + User Manuals) |  |  | Week 12 |  | Not Started
5.3 | Acceptance Test and Support |  |  | Week 13 |  | Not Started
5.4 | Final Software Package (Docs + Source Codes) |  |  | Week 13 |  | Not Started
Stage 6: Closing (Week 14)
6.1 | Report 7 — Final Project Report |  |  | Week 14 |  | Not Started
6.2 | Presentation File |  |  | Week 14 |  | Not Started

## WBS
IELTSPath — Work Breakdown Structure
Complexity: Simple (≤7 fields / ≤3 tx) · Medium (≤15 / ≤7) · Complex (>15 / >7) · Effort: Simple=3 / Medium=5 / Complex=8 pts (default)
Function / Screen | Type | Feature Group | Sub-Feature | Description | Complexity | Est. Effort (pts) | Planned Iteration | In Charge | Actual Effort (pts) | Status | Notes
WBS-001 — Home | Screen | Public / Access | FT-10, FT-11, FT-12 | Introduces IELTSPath, shows the FREE / Premium plans and point cards, and lets a signed-in learner redeem an activation key for Premium days or points. Route: /home · Public page (default route for guests) | Simple | 3 | Iteration 1 | HoangNV |  | In Progress | FDS §2.1; FT-10, FT-11, FT-12; UC-30, UC-26; FE: partly built; Specified (key activation not wired in the frontend: GAP-03). Role: Guest and any signed-in user. Done means implemented screen scope, not formal UAT approval. ¦ Initial proposed window 2026-09-29 to 2026-10-07; completion depends on WBS-055, WBS-056, WBS-068. Remaining scope carries into Iteration 2, target 21/10/2026. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-002 — Login | Screen | Authentication | FT-02, FT-03, FT-05, FT-07 | Lets a registered user sign in with email and password, so the app can return to the page the user wanted or open the learning path. Route: /login · Public page (GuestOnly) | Medium | 5 | Iteration 1 | HoangNV |  | In Progress | FDS §2.2; FT-02, FT-03, FT-05, FT-07; UC-02, UC-03; FE: built, real API; Specified (OAuth button: Draft; role-based home: GAP-02). Role: Guest. Done means implemented screen scope, not formal UAT approval. ¦ Initial proposed window 2026-09-29 to 2026-10-07; completion depends on WBS-055, WBS-056, WBS-069. Remaining scope carries into Iteration 2, target 21/10/2026. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-003 — Register | Screen | Authentication | FT-01, FT-02 | Lets a guest create a learner account and signs the guest in straight away, so learning can start. Route: /register · Public page (GuestOnly) | Simple | 3 | Iteration 1 | HoangNV |  | Done | FDS §2.3; FT-01, FT-02; UC-01; FE: built, real API; Specified. Role: Guest. Done means implemented screen scope, not formal UAT approval. ¦ Initial proposed window 2026-10-02 to 2026-10-07; completion depends on WBS-055, WBS-056, WBS-069. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-004 — Forgot Password | Screen | Authentication | FT-04 | Lets a user who forgot the password ask for a reset code, so a new password can be set. Route: /forgot-password · Public page (GuestOnly) | Simple | 3 | Iteration 1 | HoangNV |  | In Progress | FDS §2.4; FT-04; UC-04, UC-05; FE: built, real API; Specified (email delivery: Draft, GAP-06). Role: Guest. Done means implemented screen scope, not formal UAT approval. ¦ Initial proposed window 2026-09-29 to 2026-10-07; completion depends on WBS-055, WBS-069. Remaining scope carries into Iteration 2, target 21/10/2026. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-005 — Reset Password | Screen | Authentication | FT-04 | Lets the user set a new password with the reset code, so the user can sign in again. Route: /reset-password?token=… · Public page (GuestOnly) | Simple | 3 | Iteration 1 | HoangNV |  | In Progress | FDS §2.5; FT-04; UC-04; FE: built, real API; Specified (link delivery: Draft, GAP-06). Role: Guest. Done means implemented screen scope, not formal UAT approval. ¦ Initial proposed window 2026-09-29 to 2026-10-07; completion depends on WBS-004, WBS-069. Remaining scope carries into Iteration 2, target 21/10/2026. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-006 — OAuth Callback | Screen | Authentication | FT-05 | Finishes a sign-in with the OAuth identity provider and opens the learning path. Route: /auth/oauth/callback · Public page (GuestOnly) | Simple | 3 | Iteration 3 | HoangNV |  | Not Started | FDS §2.6; FT-05; UC-03; FE: placeholder route; Draft. Role: Guest. ¦ Initial proposed window 2026-10-29 to 2026-12-09; completion depends on WBS-069. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-007 — Overview | Screen | Prototype | FT-26, FT-44, FT-45 (intended) | Gives the learner a dashboard of study time, four-skill progress, words to review, mentor feedback, courses and the study streak. Route: /overview · RequireAuth (default route when signed in) | Simple | 3 | Iteration 2 | SonLT |  | In Progress | FDS §2.7; FT-26, FT-44, FT-45 (intended); UC-19, UC-18; FE: built on mock data; Draft (UI on mock data, OQ-17). Role: Any signed-in user. Mock UI exists; product implementation is incomplete. ¦ Initial proposed window 2026-10-08 to 2026-10-28; completion depends on WBS-057, WBS-071, WBS-076. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-008 — Learning Path | Screen | Core Learning | FT-13, FT-20, FT-28 | Display the learning path and ordered topics within a chosen course. Course chooser/recommendation and course-final-test UI are WBS-073; shared contract mappings are WBS-075. Route: /learn. | Simple | 3 | Iteration 1 | HoangNV |  | In Progress | FDS §2.8; FT-13, FT-20, FT-28; UC-08; FE: built, real API; Specified (skill grouping: GAP-01; Premium lock: Draft). Role: Signed-in learner. Done means implemented screen scope, not formal UAT approval. ¦ Initial proposed window 2026-09-29 to 2026-10-07; completion depends on WBS-055, WBS-056, WBS-070, WBS-072, WBS-073. Remaining scope carries into Iteration 2, target 21/10/2026. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-009 — Topic Detail | Screen | Core Learning | FT-20, FT-21, FT-27, FT-29 | Lists the ordered lessons of a topic and the final test card, so the learner can open the next lesson, go to practice or start the final test. Route: /learn/topics/:topicId · RequireAuth | Medium | 5 | Iteration 1 | HoangNV |  | In Progress | FDS §2.9; FT-20, FT-21, FT-27, FT-29; UC-08, UC-20; FE: built, real API; Specified. Role: Signed-in learner. Done means implemented screen scope, not formal UAT approval. New 07/10 course/multi-skill DTO and gate changes still need FE alignment and fresh browser verification; old FDS acceptance scope is incomplete. ¦ Initial proposed window 2026-09-29 to 2026-10-07; completion depends on WBS-008, WBS-066, WBS-070, WBS-075. Remaining scope carries into Iteration 2, target 21/10/2026. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-010 — Lesson Player | Screen | Core Learning | FT-21, FT-22, FT-23, FT-24, FT-25 | Presents a lesson's blocks in order — text, passage, audio, exercises and essays — grades each exercise block, so the learner can pass the lesson and move on. Route: /learn/lessons/:lessonId · RequireAuth | Medium | 5 | Iteration 1 | HoangNV |  | In Progress | FDS §2.10; FT-21, FT-22, FT-23, FT-24, FT-25; UC-09, UC-12, UC-13; FE: built, real API; Specified. Role: Signed-in learner. Done means implemented screen scope, not formal UAT approval. New 07/10 course/multi-skill DTO and gate changes still need FE alignment and fresh browser verification; old FDS acceptance scope is incomplete. ¦ Initial proposed window 2026-09-29 to 2026-10-07; completion depends on WBS-009, WBS-066, WBS-070, WBS-074, WBS-075. Remaining scope carries into Iteration 2, target 21/10/2026. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-011 — Writing Feedback | Screen | Core Learning | FT-12, FT-25 | Shows the AI grading of a Writing essay — estimated band, pass or not, criteria, corrections and the sample answer — so the learner can improve the next essay. Route: Inline panel in /learn/lessons/:lessonId (EssayBlock) | Simple | 3 | Iteration 1 | HoangNV |  | In Progress | FDS §2.11; FT-12, FT-25; UC-12, UC-13, UC-27; FE: partly built; Specified (separate page and re-reading a submission: GAP-08). Role: Signed-in learner. Done means implemented screen scope, not formal UAT approval. ¦ Initial proposed window 2026-09-29 to 2026-10-07; completion depends on WBS-010, WBS-057, WBS-068, WBS-075. Remaining scope carries into Iteration 2, target 21/10/2026. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-012 — Practice Set | Screen | Core Learning | FT-23, FT-24, FT-26, FT-27 | Lists the practice sets of a completed lesson and lets the learner answer one set, see every solution and start the review it creates. Route: /learn/lessons/:lessonId/practice · RequireAuth | Simple | 3 | Iteration 1 | HoangNV |  | In Progress | FDS §2.12; FT-23, FT-24, FT-26, FT-27; UC-10; FE: built, real API; Specified (Premium sets disabled: GAP-05). Role: Signed-in learner. Done means implemented screen scope, not formal UAT approval. New 07/10 course/multi-skill DTO and gate changes still need FE alignment and fresh browser verification; old FDS acceptance scope is incomplete. ¦ Initial proposed window 2026-09-29 to 2026-10-07; completion depends on WBS-010, WBS-057, WBS-074, WBS-075. Remaining scope carries into Iteration 2, target 21/10/2026. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-013 — Review List | Screen | Core Learning | FT-28 | Lists the learner's reviews, oldest first, so the learner can finish the ones that block a skill. Route: /learn/reviews (proposed) | Simple | 3 | Iteration 2 | HoangNV |  | Not Started | FDS §2.13; FT-28; UC-11; FE: not built; Specified (backend); screen not built (GAP-07). Role: CUSTOMER. ¦ Initial proposed window 2026-10-08 to 2026-10-28; completion depends on WBS-057, WBS-070. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-014 — Review Session | Screen | Core Learning | FT-23, FT-24, FT-26, FT-28 | Guides the learner through one review — theory with a quick check, then a set of questions — so a weak knowledge point is repaired and the skill is unblocked. Route: /learn/reviews/:reviewId · RequireAuth | Medium | 5 | Iteration 1 | HoangNV |  | In Progress | FDS §2.14; FT-23, FT-24, FT-26, FT-28; UC-11; FE: built, real API; Specified (empty quick-check: GAP-12). Role: Signed-in learner. Done means implemented screen scope, not formal UAT approval. New 07/10 course/multi-skill DTO and gate changes still need FE alignment and fresh browser verification; old FDS acceptance scope is incomplete. ¦ Initial proposed window 2026-09-29 to 2026-10-07; completion depends on WBS-012, WBS-057, WBS-074, WBS-075. Remaining scope carries into Iteration 2, target 21/10/2026. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-015 — Mastery | Screen | Core Learning | FT-26 | Shows the learner's mastery from 0 to 1 for every knowledge point, grouped by skill and topic, so the learner can see strong and weak points. Route: /learn/mastery (proposed) | Simple | 3 | Iteration 2 | HoangNV |  | Not Started | FDS §2.15; FT-26; UC-18; FE: not built; Specified (backend); screen not built (GAP-07). Role: CUSTOMER. ¦ Initial proposed window 2026-10-08 to 2026-10-28; completion depends on WBS-057, WBS-070. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-016 — Test Attempt | Screen | Core Learning | FT-24, FT-30, FT-31 | Lets the learner sit the topic final test section by section, with answers saved as they go, and submit it for grading. Route: /learn/tests/:attemptId?topic=… · RequireAuth | Simple | 3 | Iteration 1 | HoangNV |  | In Progress | FDS §2.16; FT-24, FT-30, FT-31; UC-20; FE: built, real API; Specified (text answers saved at submit; no timer: GAP-09). Role: Signed-in learner. Done means implemented screen scope, not formal UAT approval. New 07/10 course/multi-skill DTO and gate changes still need FE alignment and fresh browser verification; old FDS acceptance scope is incomplete. ¦ Initial proposed window 2026-09-29 to 2026-10-07; completion depends on WBS-012, WBS-014, WBS-067, WBS-075. Remaining scope carries into Iteration 2, target 21/10/2026. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-017 — Test Result | Screen | Core Learning | FT-14, FT-24, FT-29, FT-31, FT-33 | Shows the score of the submitted topic test, per-question correctness and — at 70% or more — the correct answers, and tells the learner whether the topic is passed. Route: /learn/tests/:attemptId/result?topic=… · RequireAuth | Medium | 5 | Iteration 1 | HoangNV |  | In Progress | FDS §2.17; FT-14, FT-24, FT-29, FT-31, FT-33; UC-22, UC-16, UC-25; FE: built, real API; Specified (examiner and AI grading requests: Draft). Role: Signed-in learner. Done means implemented screen scope, not formal UAT approval. New 07/10 course/multi-skill DTO and gate changes still need FE alignment and fresh browser verification; old FDS acceptance scope is incomplete. ¦ Initial proposed window 2026-09-29 to 2026-10-07; completion depends on WBS-016, WBS-058, WBS-059, WBS-075. Remaining scope carries into Iteration 2, target 21/10/2026. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-018 — Mock & Placement Tests | Screen | Core Learning | FT-34, FT-35 | Lists the published mock tests and the one-time placement test, so the learner can estimate a starting level or practise under exam conditions. Route: /tests (proposed) | Simple | 3 | Iteration 3 | HoangNV |  | Not Started | FDS §2.18; FT-34, FT-35; UC-21, UC-23; FE: not built; Draft. Role: CUSTOMER. ¦ Initial proposed window 2026-10-29 to 2026-12-09; completion depends on WBS-067, WBS-072, WBS-073. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-019 — Practice Test Catalog | Screen | Prototype | — (no SRS feature; closest FT-34 Mock test) | Lets the learner browse practice tests by skill and open one in practice or exam mode. Route: /practice-tests · RequireAuth | Simple | 3 | Iteration 2 | SonLT |  | In Progress | FDS §2.19; — (no SRS feature; closest FT-34 Mock test); No UC assigned; FE: built on mock data; Prototype (mock data, OQ-17). Role: Any signed-in user. Mock UI exists; product implementation is incomplete. ¦ Initial proposed window 2026-10-08 to 2026-10-28; completion depends on WBS-018. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-020 — Practice Workspaces (Reading, Listening, Writing, Speaking) | Screen | Prototype | — (closest FT-25, FT-39, FT-42, FT-43) | Gives a full-screen workspace for one practice test per skill, with tools for highlighting, notes, a small dictionary and flashcards. Route: /practice/test/:testId · /practice/listening/:testId · /practice/writing/:taskId · /practice/speaking/:cueId · RequireAuth | Complex | 8 | Iteration 2 | SonLT |  | In Progress | FDS §2.20; — (closest FT-25, FT-39, FT-42, FT-43); No UC assigned; FE: built on mock data; Prototype (mock data and browser storage, OQ-17). Role: Any signed-in user. Mock UI exists; product implementation is incomplete. ¦ Initial proposed window 2026-10-08 to 2026-10-28; completion depends on WBS-019, WBS-067. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-021 — Classroom | Screen | Prototype | — (mentor classes are not in the SRS) | Shows the learner's class, teacher and a calendar of class sessions with a link to join or open each session. Route: /classroom · RequireAuth | Simple | 3 | Iteration 2 | SonLT |  | In Progress | FDS §2.21; — (mentor classes are not in the SRS); No UC assigned; FE: built on mock data; Prototype (mock data, OQ-17). Role: Any signed-in user. Mock UI exists; product implementation is incomplete. Prototype only; classroom scope has no committed SRS feature. Treat full integration as deferred pending scope decision. ¦ Initial proposed window 2026-10-08 to 2026-10-28; completion depends on none. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-022 — Classroom Lesson Workspace | Screen | Prototype | — (closest FT-36, FT-43) | Shows one class session with its materials, a short quiz and the topic vocabulary to review. Route: /lessons/:lessonId · RequireAuth | Simple | 3 | Iteration 2 | SonLT |  | In Progress | FDS §2.22; — (closest FT-36, FT-43); No UC assigned; FE: built on mock data; Prototype (mock data, OQ-17). Role: Any signed-in user. Mock UI exists; product implementation is incomplete. Prototype only; classroom scope has no committed SRS feature. Treat full integration as deferred pending scope decision. ¦ Initial proposed window 2026-10-08 to 2026-10-28; completion depends on WBS-021. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-023 — Profile & Account | Screen | Self-study / Account | FT-05, FT-06 | Lets a user keep account details and the learner profile up to date and manage linked sign-in providers. Route: /account/profile | Medium | 5 | Iteration 2 | SonLT |  | Not Started | FDS §2.23; FT-05, FT-06; UC-06; FE: not built; Specified (OAuth linking: Draft). Role: Any signed-in role. ¦ Initial proposed window 2026-10-08 to 2026-10-28; completion depends on WBS-069. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-024 — Learning Goals | Screen | Self-study / Account | FT-09, FT-35 | Lets the learner set one active goal — target band, exam date and daily study minutes — and pause, resume or close it, so progress can be tracked against a target. Route: /account/goals | Medium | 5 | Iteration 2 | SonLT |  | Not Started | FDS §2.24; FT-09, FT-35; UC-06, UC-23; FE: not built; Specified (edit of the active goal: Draft). Role: CUSTOMER. ¦ Initial proposed window 2026-10-08 to 2026-10-28; completion depends on WBS-069. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-025 — Subscription & Points | Screen | Self-study / Account | FT-10, FT-11, FT-12, FT-14 | Shows the learner's subscription, examiner credits, point balance and history, and lets the learner redeem an activation key for Premium days or points. Route: /account/subscription | Medium | 5 | Iteration 1 | HoangNV |  | In Progress | FDS §2.25; FT-10, FT-11, FT-12, FT-14; UC-30, UC-27, UC-26; FE: partly built; Specified. Role: CUSTOMER. Done means implemented screen scope, not formal UAT approval. ¦ Initial proposed window 2026-09-29 to 2026-10-07; completion depends on WBS-068, WBS-056. Remaining scope carries into Iteration 2, target 21/10/2026. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-026 — Activity & Streak | Screen | Self-study / Account | FT-44, FT-45 | Shows the learner's study activities and current and longest streak, so the learner can keep a daily study habit. Route: /account/activity | Medium | 5 | Iteration 2 | SonLT |  | Not Started | FDS §2.26; FT-44, FT-45; UC-19; FE: not built; Specified (server-side streak: Draft). Role: Any signed-in role. ¦ Initial proposed window 2026-10-08 to 2026-10-28; completion depends on WBS-069, WBS-071. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-027 — Notification Centre | Screen | Self-study / Account | FT-51, FT-52, FT-53, FT-54 | Lists the learner's in-app notifications and lets the learner choose channels, reminder time and registered devices. Route: /notifications | Medium | 5 | Iteration 3 | HoangNV |  | Not Started | FDS §2.27; FT-51, FT-52, FT-53, FT-54; UC-32, UC-31; FE: not built; Draft. Role: CUSTOMER. ¦ Initial proposed window 2026-10-29 to 2026-12-09; completion depends on WBS-061, WBS-062, WBS-063. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-028 — Vocabulary | Screen | Self-study / Account | FT-36, FT-43 | Lets the learner look up topic vocabulary, hear the pronunciation and save words to review later. Route: /vocabulary · Public page | Medium | 5 | Iteration 2 | SonLT |  | In Progress | FDS §2.28; FT-36, FT-43; UC-37, UC-33; FE: built on mock data; Specified (backend); frontend on mock data (GAP-10). Role: Guest and any signed-in user. Mock UI exists; product implementation is incomplete. ¦ Initial proposed window 2026-10-08 to 2026-10-28; completion depends on WBS-071. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-029 — Video Library | Screen | Self-study / Account | FT-37, FT-38 | Lists the published learning videos with the learner's progress, so the learner can pick one to watch. Route: /library/videos | Simple | 3 | Iteration 2 | SonLT |  | Not Started | FDS §2.29; FT-37, FT-38; UC-37; FE: not built; Specified. Role: CUSTOMER, EXAMINER, CONTENT_AUTHOR, ADMIN. ¦ Initial proposed window 2026-10-08 to 2026-10-28; completion depends on WBS-071. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-030 — Video Player | Screen | Self-study / Account | FT-37, FT-38, FT-39, FT-40, FT-41 | Plays a learning video with its segment transcript, remembers progress, saves segments and lets the learner practise shadowing and dictation on a segment. Route: /library/videos/:videoId | Complex | 8 | Iteration 2 | SonLT |  | Not Started | FDS §2.30; FT-37, FT-38, FT-39, FT-40, FT-41; UC-38, UC-17, UC-39, UC-14, UC-15; FE: not built; Specified (shadowing / dictation scoring: Draft). Role: CUSTOMER. ¦ Initial proposed window 2026-10-08 to 2026-10-28; completion depends on WBS-071. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-031 — My Notes | Screen | Self-study / Account | FT-42 | Lets the learner write private notes, optionally linked to a knowledge point or a Reading section. Route: /library/notes | Medium | 5 | Iteration 2 | SonLT |  | Not Started | FDS §2.31; FT-42; UC-33; FE: not built; Specified. Role: Any signed-in role. ¦ Initial proposed window 2026-10-08 to 2026-10-28; completion depends on WBS-071. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-032 — Flashcards & Decks | Screen | Self-study / Account | FT-43 | Lets the learner create flashcards, group them into decks and study a deck card by card. Route: /library/flashcards | Complex | 8 | Iteration 2 | SonLT |  | Not Started | FDS §2.32; FT-43; UC-33; FE: not built; Specified. Role: Any signed-in role. ¦ Initial proposed window 2026-10-08 to 2026-10-28; completion depends on WBS-071. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-033 — Game Lobby | Screen | Self-study / Account | FT-46, FT-47, FT-48 | Lets the learner start a single-player game, create or join a multiplayer room, and see past sessions. Route: /games | Medium | 5 | Iteration 3 | HoangNV |  | Not Started | FDS §2.33; FT-46, FT-47, FT-48; UC-34; FE: not built; Specified (matchmaking: Draft). Role: Any signed-in role. ¦ Initial proposed window 2026-10-29 to 2026-12-09; completion depends on WBS-066. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-034 — Single-player Game | Screen | Self-study / Account | FT-46 | Plays a single-player vocabulary or grammar game item by item on a frozen content snapshot and shows the final score. Route: /games/sessions/:sessionId | Simple | 3 | Iteration 3 | SonLT |  | Not Started | FDS §2.34; FT-46; UC-34; FE: not built; Specified. Role: Any signed-in role. ¦ Initial proposed window 2026-10-29 to 2026-12-09; completion depends on WBS-033. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-035 — Game Room | Screen | Self-study / Account | FT-47 | Gathers players in a multiplayer room, lets the host start the match and plays it in real time over WebSocket, ending with a ranking. Route: /games/rooms/:roomId | Medium | 5 | Iteration 3 | HoangNV |  | Not Started | FDS §2.35; FT-47; UC-34; FE: not built; Specified. Role: Any signed-in role. ¦ Initial proposed window 2026-10-29 to 2026-12-09; completion depends on WBS-033, WBS-064. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-036 — Community Feed | Screen | Self-study / Account | FT-49, FT-50 | Lists active community posts newest first and lets users write a post, react, and — for Administrators — hide posts that break the rules. Route: /community | Medium | 5 | Iteration 3 | SonLT |  | Not Started | FDS §2.36; FT-49, FT-50; UC-35, UC-36; FE: not built; Specified. Role: Any signed-in role. ¦ Initial proposed window 2026-10-29 to 2026-12-09; completion depends on WBS-069. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-037 — Post Detail | Screen | Self-study / Account | FT-49, FT-50 | Shows one post with its comments and lets users comment, reply, edit or delete their own content, and Administrators hide or restore it. Route: /community/posts/:postId | Complex | 8 | Iteration 3 | SonLT |  | Not Started | FDS §2.37; FT-49, FT-50; UC-35, UC-36; FE: not built; Specified. Role: Any signed-in role. ¦ Initial proposed window 2026-10-29 to 2026-12-09; completion depends on WBS-036. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-038 — User Management | Screen | Staff | FT-07, FT-08 | Lets an Administrator find accounts, create staff or learner accounts with roles, and open an account to manage it. Route: /admin/users · ADMIN home | Simple | 3 | Iteration 3 | HoangNV |  | Not Started | FDS §2.38; FT-07, FT-08; UC-07; FE: not built; Specified (paging and search: Draft). Role: ADMIN. ¦ Initial proposed window 2026-10-29 to 2026-12-09; completion depends on WBS-053, WBS-069. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-039 — User Detail | Screen | Staff | FT-04, FT-05, FT-08, FT-09, FT-10, FT-12, FT-13 | Lets an Administrator change one account's details, roles and status, and review its profile, goals, linked providers and account action tokens. Route: /admin/users/:userId | Complex | 8 | Iteration 3 | HoangNV |  | Not Started | FDS §2.39; FT-04, FT-05, FT-08, FT-09, FT-10, FT-12, FT-13; UC-07; FE: not built; Specified. Role: ADMIN. ¦ Initial proposed window 2026-10-29 to 2026-12-09; completion depends on WBS-038. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-040 — Plans & Key Products | Screen | Staff | FT-10, FT-14 | Lets an Administrator define plans and the key products that activation keys grant (Premium days with examiner credits, or points). Route: /admin/access/plans | Medium | 5 | Iteration 3 | HoangNV |  | Not Started | FDS §2.40; FT-10, FT-14; UC-29; FE: not built; Specified. Role: ADMIN. ¦ Initial proposed window 2026-10-29 to 2026-12-09; completion depends on WBS-053, WBS-068. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-041 — Activation Keys | Screen | Staff | FT-11 | Lets staff generate a batch of activation keys for a key product, copy them once, and revoke keys that were lost before use. Route: /admin/access/keys · SALES_STAFF home | Medium | 5 | Iteration 3 | HoangNV |  | Not Started | FDS §2.41; FT-11; UC-28; FE: not built; Specified for ADMIN (SALES_STAFF access and key list: Draft). Role: ADMIN, SALES_STAFF. ¦ Initial proposed window 2026-10-29 to 2026-12-09; completion depends on WBS-040, WBS-068. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-042 — Points & Subscriptions | Screen | Staff | FT-10, FT-12, FT-14 | Lets an Administrator grant subscription days and examiner credits, adjust or refund a learner's points with a reason, and consume an examiner credit. Route: /admin/access/accounts | Medium | 5 | Iteration 3 | HoangNV |  | Not Started | FDS §2.42; FT-10, FT-12, FT-14; UC-29; FE: not built; Specified. Role: ADMIN. ¦ Initial proposed window 2026-10-29 to 2026-12-09; completion depends on WBS-040, WBS-068. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-043 — Topics & Knowledge Points | Screen | Staff | FT-15 | Lets an author maintain the topic tree of each skill and the knowledge points each topic teaches. Route: /author/topics · CONTENT_AUTHOR home | Medium | 5 | Iteration 3 | HoangNV |  | Not Started | FDS §2.43; FT-15; UC-40; FE: not built; Specified. Role: ADMIN, CONTENT_AUTHOR. ¦ Initial proposed window 2026-10-29 to 2026-12-09; completion depends on WBS-053, WBS-066. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-044 — Question Bank | Screen | Staff | FT-16 | Lets an author create versioned questions with answer, explanation, hint, purpose and knowledge points, and filter the bank by purpose and skill. Route: /author/questions | Medium | 5 | Iteration 3 | HoangNV |  | Not Started | FDS §2.44; FT-16; UC-40; FE: not built; Specified. Role: ADMIN, CONTENT_AUTHOR. ¦ Initial proposed window 2026-10-29 to 2026-12-09; completion depends on WBS-043, WBS-066. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-045 — Packages | Screen | Staff | FT-17, FT-34, FT-35 | Lets an author group questions into versioned packages — practice sets, tests and quizzes — and publish them after the system checks question ownership and purpose. Route: /author/packages | Medium | 5 | Iteration 3 | HoangNV |  | Not Started | FDS §2.45; FT-17, FT-34, FT-35; UC-40; FE: not built; Specified (TOPIC_TEST creation: Draft). Role: ADMIN, CONTENT_AUTHOR. ¦ Initial proposed window 2026-10-29 to 2026-12-09; completion depends on WBS-044, WBS-066. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-046 — Media Assets | Screen | Staff | FT-18, FT-24 | Lets an author register passage text, images and Listening audio as assets and link them to sections or question versions. Route: /author/assets | Medium | 5 | Iteration 3 | HoangNV |  | Not Started | FDS §2.46; FT-18, FT-24; UC-40, UC-41; FE: not built; Specified (upload: Draft). Role: ADMIN, CONTENT_AUTHOR. ¦ Initial proposed window 2026-10-29 to 2026-12-09; completion depends on WBS-043, WBS-066. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-047 — Lesson Builder | Screen | Staff | FT-19 | Lets an author build a topic's ordered lessons from theory, assets, exercise blocks and essay blocks, and publish them to the learning path. Route: /author/lessons/:lessonId | Simple | 3 | Iteration 3 | HoangNV |  | Not Started | FDS §2.47; FT-19; UC-42; FE: not built; Draft. Role: ADMIN, CONTENT_AUTHOR. ¦ Initial proposed window 2026-10-29 to 2026-12-09; completion depends on WBS-043, WBS-044, WBS-045, WBS-046. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-048 — Vocabulary Management | Screen | Staff | FT-36 | Lets an author add vocabulary items and their senses to the catalog used by lessons, videos, flashcards and games. Route: /author/vocabulary | Medium | 5 | Iteration 3 | HoangNV |  | Not Started | FDS §2.48; FT-36; UC-40; FE: not built; Specified. Role: ADMIN, CONTENT_AUTHOR. ¦ Initial proposed window 2026-10-29 to 2026-12-09; completion depends on WBS-067, WBS-060. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-049 — Video Management | Screen | Staff | FT-37 | Lets an author register a YouTube learning video, split it into timed segments with transcripts and linked words, and publish it. Route: /author/videos | Medium | 5 | Iteration 3 | HoangNV |  | Not Started | FDS §2.49; FT-37; UC-40; FE: not built; Specified. Role: ADMIN, CONTENT_AUTHOR. ¦ Initial proposed window 2026-10-29 to 2026-12-09; completion depends on WBS-048. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-050 — Grading Workspace | Screen | Staff | FT-32, FT-52 | Lets an Examiner open a submitted attempt, enter item scores, errors and knowledge-point judgments, and finalize the result so it reaches the learner's progress. Route: /examiner/grading · EXAMINER home | Medium | 5 | Iteration 3 | HoangNV |  | Not Started | FDS §2.50; FT-32, FT-52; UC-24; FE: not built; Specified (work queue and response view: Draft). Role: ADMIN, EXAMINER. ¦ Initial proposed window 2026-10-29 to 2026-12-09; completion depends on WBS-053, WBS-067. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-051 — Backend build foundation | Non-UI | Infrastructure | TDS infrastructure / common FDS conventions | Maven multi-module, Java service folders and repeatable build baseline. | Medium | 5 | Iteration 1 | HieuLT |  | Done | Git backend 218e071. Foundation supporting FDS §2.0; implementation evidence, not UAT. ¦ Initial proposed window 2026-09-14 to 2026-09-18; completion depends on none. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-052 — Config Server and Eureka | Non-UI | Infrastructure | TDS infrastructure / common FDS conventions | Centralized configuration and service registration/discovery. | Medium | 5 | Iteration 1 | TungVPH |  | Done | Git backend 218e071, dac8b03; backend/README.md. ¦ Initial proposed window 2026-09-14 to 2026-09-18; completion depends on WBS-051. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-053 — Gateway security and routing | Non-UI | Security | TDS infrastructure / common FDS conventions | Route public APIs; verify external JWT; sign internal JWT; enforce roles/ownership and prevent internal-route exposure. | Complex | 8 | Iteration 1 | HieuLT |  | Done | FDS §2.0; FT-07; Git backend 218e071, a18a44e, 34335aa. ¦ Initial proposed window 2026-09-14 to 2026-09-18; completion depends on WBS-051, WBS-052. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-054 — Docker and database baseline | Non-UI | Infrastructure | TDS infrastructure / common FDS conventions | Local Docker Compose, service PostgreSQL schemas and Flyway migration foundation. | Complex | 8 | Iteration 1 | TungVPH |  | Done | Git backend 218e071, dac8b03. Runtime reliability still requires test evidence. ¦ Initial proposed window 2026-09-14 to 2026-09-18; completion depends on WBS-051. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-055 — Frontend build and UI foundation | Non-UI | Frontend Foundation | TDS infrastructure / common FDS conventions | React/TypeScript/Vite, Tailwind/shadcn setup, theme, aliases and lint/typecheck/build. | Medium | 5 | Iteration 1 | HoangNV |  | Done | Git frontend 241abca, 8581a72, 015701d. Baseline work supporting all FDS screens. ¦ Initial proposed window 2026-09-14 to 2026-09-18; completion depends on none. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-056 — Session and shared request handling | Non-UI | Authentication | TDS infrastructure / common FDS conventions | Memory-only access token, cookie refresh, single-flight retry, protected routes, timeout and shared error states. | Complex | 8 | Iteration 1 | HoangNV |  | Done | FDS §2.0 common conventions; FT-03, FT-07; frontend/src/lib/httpClient.ts. Role-based staff routing remains future work. ¦ Initial proposed window 2026-09-14 to 2026-10-07; completion depends on WBS-053, WBS-055, WBS-069. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-057 — Mastery and submission integrity | Non-UI | Core Learning | TDS infrastructure / common FDS conventions | Persist evidence and mastery, apply per-skill gates, enforce request replay and Writing point-charge consistency. | Complex | 8 | Iteration 1 | HieuLT |  | In Progress | FDS §2.10–2.17; FT-26–FT-28; BR-21–BR-25, BR-30. Implementation exists; full live/UI and points acceptance remains open. ¦ Initial proposed window 2026-09-14 to 2026-10-07; completion depends on WBS-066, WBS-067, WBS-068, WBS-070. Remaining scope carries into Iteration 2, target 21/10/2026. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-058 — JOB-01 Assessment outbox relay | Non-UI | Background Jobs | FT-29, FT-31, FT-32 | Publishes the AssessmentCompleted.v2 events that grading writes to the outbox table, so a result reaches the learning service only after its database transaction has committed. Trigger: @Scheduled fixed delay 2 s (assessment.outbox.relay.poll-interval = PT2S); enabled by ASSESSMENT_OUTBOX_RELAY_ENABLED (default true) | Complex | 8 | Iteration 1 | PhuPD |  | Done | FDS Part 3 JOB-01; FT-29, FT-31, FT-32 · BR-25, BR-26, BR-30; Specified (implemented). Implemented runtime, separate operational acceptance required. ¦ Initial proposed window 2026-09-29 to 2026-10-07; completion depends on WBS-067. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-059 — JOB-02 AssessmentCompleted.v2 consumer | Non-UI | Background Jobs | FT-26, FT-29, FT-34, FT-35 | Applies each final assessment result to the learner's progress: knowledge-point evidence, topic test assignment, topic pass and reviews for weak knowledge points. Trigger: @RabbitListener on queue learning.assessment-completed.v2 (manual ack); learning.messaging.consumer-enabled (default true) | Complex | 8 | Iteration 1 | HieuLT |  | Done | FDS Part 3 JOB-02; FT-26, FT-29, FT-34, FT-35 · BR-22, BR-23, BR-25; Specified (implemented). Implemented runtime, separate operational acceptance required. ¦ Initial proposed window 2026-09-29 to 2026-10-07; completion depends on WBS-058, WBS-070. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-060 — JOB-03 AI grading worker | Non-UI | Background Jobs | FT-33, FT-34, FT-39 | Assessment AI essay grading worker for TOPIC_GATE / COURSE_GATE with examiner fallback; Speaking and MOCK AI remain future scope. | Complex | 8 | Iteration 1 | PhuPD |  | Done | BE multi-skill merge 8d2d2bb (07/10); plan 261006-2309 phase 6 records Docker-backed tests. AI gate essays implemented; Speaking excluded and live-provider acceptance remains open. ¦ Initial proposed window 2026-09-29 to 2026-10-07; completion depends on WBS-067, WBS-074. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-061 — JOB-04 Grading-done alert dispatcher | Non-UI | Background Jobs | FT-51, FT-52 | Creates one grading-done notification when an examiner finalizes a result and hands it to the delivery channels the learner enabled. Trigger: RabbitMQ: own queue bound to assessment.events / assessment.completed.v2 [TBC: queue name] | Complex | 8 | Iteration 3 | TungVPH |  | Not Started | FDS Part 3 JOB-04; FT-51, FT-52 · BR-27, BR-32; Draft. Draft/future iteration proposal, not Phase 1 delivered scope. ¦ Initial proposed window 2026-10-29 to 2026-12-09; completion depends on WBS-058. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-062 — JOB-05 Study reminder scheduler | Non-UI | Background Jobs | FT-44, FT-51, FT-53 | Creates at most one study reminder per learner per day, at the learner's preferred local time, on days without a qualifying study activity. Trigger: @Scheduled every [TBC] minutes; ShedLock or SKIP LOCKED to run on one instance [TBC] | Complex | 8 | Iteration 3 | TungVPH |  | Not Started | FDS Part 3 JOB-05; FT-44, FT-51, FT-53 · BR-32; Draft. Draft/future iteration proposal, not Phase 1 delivered scope. ¦ Initial proposed window 2026-10-29 to 2026-12-09; completion depends on WBS-069. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-063 — JOB-06 Notification delivery retry | Non-UI | Background Jobs | FT-52, FT-53, FT-54 | Sends pending notification deliveries to Firebase Cloud Messaging or the Email Service and retries failed ones without creating a second notification. Trigger: @Scheduled every [TBC] s | Complex | 8 | Iteration 3 | TungVPH |  | Not Started | FDS Part 3 JOB-06; FT-52, FT-53, FT-54 · BR-32; Draft. Draft/future iteration proposal, not Phase 1 delivered scope. ¦ Initial proposed window 2026-10-29 to 2026-12-09; completion depends on WBS-061, WBS-062. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-064 — JOB-07 Matchmaking queue sweeper | Non-UI | Background Jobs | FT-47, FT-48 | Groups waiting learners of the same game type into a room and starts the match, and removes learners who waited too long. Trigger: @Scheduled every [TBC] s | Complex | 8 | Iteration 3 | SonLT |  | Not Started | FDS Part 3 JOB-07; FT-47, FT-48 · BR-29; Draft. Draft/future iteration proposal, not Phase 1 delivered scope. ¦ Initial proposed window 2026-10-29 to 2026-12-09; completion depends on WBS-033. Owner/window/points are reconstructed planning assumptions. Actual points unknown; blank is not zero.
WBS-065 — Requirements and traceability baseline | Non-UI | Documentation | Report 1 / SRS / RTW | Review Vision & Scope; specify requirements, business rules, data and traceability; reconcile later changes. | Complex | 8 | Iteration 1 | HieuLT |  | In Progress | Vision start 09/09; SRS 29810100 on 07/10; RTW ca065f6c/4a925910. Updated SRS requires RTW/FDS follow-up; formal approval remains unrecorded. ¦ Initial proposed 2026-09-09 to 2026-10-07; completion depends on none. Remaining scope carries into Iteration 2, target 21/10/2026. Owner/date/points are inferred; actual points not supplied.
WBS-066 — Content backend and curriculum | Non-UI | Backend API | FT-15, FT-16, FT-17, FT-18 | Content topics/KPs, questions, packages, media and lesson APIs; learner answers redacted. | Complex | 8 | Iteration 1 | TungVPH |  | Done | BE 11a78fa / 20bed3b / 34335aa; implementation evidence. TungVPH is proposed accountable owner, not inferred Git author. ¦ Initial proposed 2026-09-16 to 2026-10-07; completion depends on WBS-051, WBS-053, WBS-054, WBS-065. Owner/date/points are inferred; actual points not supplied.
WBS-067 — Assessment backend | Non-UI | Backend API | FT-30, FT-31, FT-32 | Attempt lifecycle, answer persistence, objective grading and human grading endpoints. | Complex | 8 | Iteration 1 | PhuPD |  | Done | BE c087a3f (PhuPham70) scaffold; c2ed0f4 objective grading. Git authorship does not establish all hours/ownership. ¦ Initial proposed 2026-09-16 to 2026-10-07; completion depends on WBS-051, WBS-053, WBS-054, WBS-066. Owner/date/points are inferred; actual points not supplied.
WBS-068 — Access backend | Non-UI | Backend API | FT-10, FT-11, FT-12, FT-14 | Plans, keys, subscriptions, point balance and idempotent point changes. | Medium | 5 | Iteration 1 | TungVPH |  | Done | BE 99b7d4f / 3678274; access implementation. Proposed owner; learning entitlement release decision remains I-006. ¦ Initial proposed 2026-09-16 to 2026-10-07; completion depends on WBS-051, WBS-053, WBS-054. Owner/date/points are inferred; actual points not supplied.
WBS-069 — User and auth backend | Non-UI | Backend API | FT-01, FT-02, FT-03, FT-04, FT-06 | Account/password/session/profile/goal APIs; email and OAuth acceptance excluded. | Medium | 5 | Iteration 1 | PhuPD |  | Done | BE 115c36d / 2c9d37f; scope limited to implemented APIs. PhuPD is proposed owner; recovery delivery/OAuth remain I-009. ¦ Initial proposed 2026-09-16 to 2026-10-07; completion depends on WBS-051, WBS-053, WBS-054. Owner/date/points are inferred; actual points not supplied.
WBS-070 — Java learning runtime | Non-UI | Backend API | FT-20, FT-21, FT-22 | Java service runtime, base learning/lesson endpoints and domain persistence; replaces Python. Integrity/gate work WBS-057 and result consumer WBS-059 are separate. | Complex | 8 | Iteration 1 | HieuLT |  | Done | BE d96ab9e / 8195982 / 23904e8; historical Python work retained in TimeLogs, not counted as another active product deliverable. ¦ Initial proposed 2026-09-16 to 2026-10-07; completion depends on WBS-066, WBS-067, WBS-068, WBS-069. Owner/date/points are inferred; actual points not supplied.
WBS-071 — Library and learner activity backend | Non-UI | Backend API | FT-36, FT-37, FT-40, FT-42, FT-43, FT-44 | Library vocab/video/notes/flashcards and learner activity/streak API migration; FE delivery remains separate. | Complex | 8 | Iteration 1 | SonLT |  | Done | BE 465f543 / d762660 / fec5d14 / ab613b1; implementation evidence, not all FE screens complete. Proposed accountable owner. ¦ Initial proposed 2026-09-16 to 2026-10-07; completion depends on WBS-051, WBS-053, WBS-054. Owner/date/points are inferred; actual points not supplied.
WBS-072 — Band course backend | Non-UI | Backend API | FT-15, FT-20, FT-55 | Course catalog, placement recommendation, course sequence and course final test. | Complex | 8 | Iteration 1 | HieuLT |  | Done | C-006; merge df6c57f / plan 261006-2228. Reported Docker tests; manual full stack course smoke not run. ¦ Initial proposed 2026-10-06 to 2026-10-07; completion depends on WBS-066, WBS-067, WBS-070. Owner/date/points are inferred; actual points not supplied.
WBS-073 — Course selection and final-test FE | Screen | Core Learning | FT-20, FT-55 | Add course list/selection, recommendation labels and course-final-test UI over the new BE API. | Complex | 8 | Iteration 2 | HoangNV |  | Not Started | New SRS scope from 07/10; FE LearningApi lacks course methods at 3b933051. Link I-007. This is added work, not existing WBS-008 completion. ¦ Initial proposed 2026-10-08 to 2026-10-28; completion depends on WBS-072, WBS-055, WBS-056. Owner/date/points are inferred; actual points not supplied.
WBS-074 — Multi-skill lesson and Practice backend | Non-UI | Backend API | FT-21, FT-27, FT-31, FT-33, FT-55 | Mixed R/L/W lesson/Practice contracts and per-skill clearance; optional Practice essay point/quota rules. Assessment AI worker is WBS-060 and course model is WBS-072. | Complex | 8 | Iteration 1 | HieuLT |  | Done | C-008; merge 8d2d2bb (07/10). Plan records tests and explicit concerns; this BE implementation is not full UI/live-provider acceptance. ¦ Initial proposed 2026-10-06 to 2026-10-07; completion depends on WBS-072, WBS-066, WBS-067, WBS-070. Owner/date/points are inferred; actual points not supplied.
WBS-075 — Multi-skill FE contract alignment | Non-UI | Frontend Integration | FT-21, FT-27, FT-31, FT-33 | Shared API methods, skills[] DTO adapters, per-skill state mappings and gate/error translation. Screen presentation changes remain in WBS-008..017/073. | Complex | 8 | Iteration 2 | HoangNV |  | Not Started | BE contract/docs changed 07/10; FE main last merged 05/10. Verify against DTOs and new gates. Link R-002 / I-007 / I-003. ¦ Initial proposed 2026-10-08 to 2026-10-28; completion depends on WBS-074, WBS-073. Owner/date/points are inferred; actual points not supplied.
WBS-076 — Integration and system verification | Non-UI | Testing | Test Plan / SC-01, SC-02, SC-04, SC-05 | Fresh browser core flow, course/multi-skill regression, keyboard/a11y, real-media/LLM and negative security tests. | Complex | 8 | Iteration 2 | SonLT |  | In Progress | FE 05/10 reports: API-assisted lessons/Practice, review N/A; later full flow not evidenced. No UAT approval or new executed test result invented. ¦ Initial proposed 2026-10-08 to 2026-10-28; completion depends on WBS-008, WBS-009, WBS-010, WBS-012, WBS-014, WBS-016, WBS-017, WBS-073, WBS-075. Owner/date/points are inferred; actual points not supplied.
WBS-077 — Functional design and technical documentation | Non-UI | Documentation | FDS v0.4 / TDS / SRS handoff | Maintain screen/job specifications and architecture; synchronize course/multi-skill requirements and diagrams. | Complex | 8 | Iteration 1 | SonLT |  | In Progress | FDS 4153dd06 / 1b4b26b8 on 07/10; generated against SRS v0.9.15. Handoff report lists missing course/multi-skill changes. ¦ Initial proposed 2026-10-06 to 2026-10-07; completion depends on WBS-065. Remaining scope carries into Iteration 2, target 21/10/2026. Owner/date/points are inferred; actual points not supplied.
WBS-078 — Environment and deployment verification | Non-UI | Infrastructure | TDS / test environment | Reproducible Docker configuration, seed reset, runbook, test prerequisites and operational checks. | Medium | 5 | Iteration 1 | TungVPH |  | In Progress | Compose baseline exists; environment validation and performance are not inferred from compile success. R-007, R-010. ¦ Initial proposed 2026-09-16 to 2026-10-07; completion depends on WBS-051, WBS-052, WBS-053, WBS-054. Remaining scope carries into Iteration 2, target 21/10/2026. Owner/date/points are inferred; actual points not supplied.
WBS-079 — Mock prototype work product | Non-UI | Prototype | FDS §2.7, §2.19-2.22, §2.28 | Build and review existing mock workspaces/classroom/overview/vocabulary UX separately from product integration. | Medium | 5 | Iteration 1 | SonLT |  | Done | FE 6ffb8a4 / b8d3f3f / 015701d / b93604b / 43f537b. Done means prototype work product only; Screen rows stay In Progress. ¦ Initial proposed 2026-09-16 to 2026-10-07; completion depends on WBS-055. Owner/date/points are inferred; actual points not supplied.
WBS-080 — Game service initial backend | Non-UI | Game | FT-47, FT-48 | Initialize the Game module and initial backend code; complete game flows, matchmaking and acceptance are separate future work. | Medium | 5 | Iteration 1 | PhuPD |  | Done | Git backend c12541b6 / c2561e23. Done applies only to the narrow initialization package, not a completed user feature. ¦ Initial proposed 2026-09-23 to 2026-09-24; completion depends on WBS-051, WBS-052, WBS-053, WBS-054. Owner/date/points are reconstructed planning assumptions; actual points unknown.
WBS-081 — Community service initial backend | Non-UI | Community | Community draft scope | Initialize the Community module and initial backend code; full learner community features and acceptance are separate future work. | Medium | 5 | Iteration 1 | TungVPH |  | Done | Git backend 559718a4 / 10433389. Done applies only to the narrow initialization package, not a completed user feature. ¦ Initial proposed 2026-09-22 to 2026-09-23; completion depends on WBS-051, WBS-052, WBS-053, WBS-054. Owner/date/points are reconstructed planning assumptions; actual points unknown.
WBS-082 — Notification service scaffold | Non-UI | Notification | FT-51, FT-52, FT-53, FT-54 | Create the service module and shared configuration/routing baseline only; notification delivery, reminders and retries remain future scope. | Medium | 5 | Iteration 1 | TungVPH |  | Done | Git backend 11a78fa6. Done applies only to the narrow initialization package, not a completed user feature. ¦ Initial proposed 2026-09-22 to 2026-09-23; completion depends on WBS-051, WBS-052, WBS-053, WBS-054. Owner/date/points are reconstructed planning assumptions; actual points unknown.
Iteration summary — estimate points; operational acceptance tracked separately
Iteration | Work packages | Estimate points | Done | In Progress | Not Started | Blocked
Iteration 1 | 39 | 224 | 22 | 17 | 0 | 0
Iteration 2 | 18 | 94 | 0 | 7 | 11 | 0
Iteration 3 | 25 | 133 | 0 | 0 | 25 | 0
Total | 82 | 451 | 22 | 24 | 36 | 0
Proposed iteration plan — calendar dates estimated, not an approved schedule
Iteration | Start | Finish | Objective | Entry dependencies | Exit / acceptance | Lead
Iteration 1 | 2026-09-09 | 2026-10-07 | Requirements → infrastructure → BE core → FE auth/learning → documented smoke. Course/multi-skill BE landed late. | Requirements and service contracts; Content before Learning/Assessment; BE endpoints before FE HTTP. | Implemented scope recorded. Fresh browser, course FE and live providers remain outstanding; iteration date does not imply acceptance. | HieuLT
Iteration 2 | 2026-10-08 | 2026-10-28 | Align course/multi-skill FE, clear core flow gaps, reconcile docs; integrate priority account/library screens. | Iteration 1 APIs; C-006/C-008 contract reconciliation. | Unassisted browser + course/multi-skill regression evidence, updated RTW/FDS/Test Plan and reviewed findings. | HoangNV
Iteration 3 | 2026-10-29 | 2026-12-09 | Proposed extended staff, notification, games/community and remaining screens, after prioritization. | Validated core flow and confirmed scope; external providers/data available. | Acceptance by confirmed feature list. Classroom/Speaking/mobile and external integrations need explicit scope decisions. | HieuLT
Team ownership — proposed allocations based on the supplied roles
Member | Role | Primary scope | Coordinates with | Historical attribution | Approval authority | Capacity assumption
PhuPD | BE | User/Auth + Assessment + outbox | HieuLT / HoangNV | PhuPham70 matches PhuPD by supplied name; other assignments inferred. | TimeLog and project approval: LinhNDM (PM / supervisor). | Student project: around 2–4 h/day; no actual timesheets.
HoangNV | FE lead | FE auth, learning, course and multi-skill alignment | SonLT / HieuLT | Nguyen Viet Hoang / hoangnv31 observed in Git. | FE review lead; no historic formal approval invented. | Estimated daily entries capped at 8 h/person.
SonLT | BE + FE | Library/activity follow-up, prototype, FDS and system QA | HoangNV / TungVPH | sonledz22 observed in Git. | Cross-review/testing owner (proposed). | Work dates/hours reconstructed; overlap checked.
HieuLT | Tech lead / task assignment | Architecture, Java Learning, course/multi-skill and coordination | All members | hieuLeFpt / Lê Trung Hiếu observed in Git. | Technical coordination and task allocation; PM / project reviewer: LinhNDM. | AI-authored commits attributed only as proposed human oversight.
TungVPH | BE | Content, Access, infrastructure and operational checks | PhuPD / HieuLT | Git account mapping not confirmed; assignments are proposed. | Backend review/implementation allocation (proposed). | No unsupported historic Git identity asserted.
LinhNDM | PM / project supervisor | Project oversight, review and approval | All team | Confirmed by user | TimeLogs and project review | Supervisor; five-member implementation team unchanged
Basis and interpretation
Item | Value / rule | Source | Version / date | Owner | Status | Limit
Project start | 09/09/2026 | Report 1 Vision & Scope | v1.1.0 / 07/10/2026 | HieuLT | Source date | Earlier than repo creation; planning work can precede Git.
Repo creation | 14/09/2026 | GitHub repository metadata | Backend + Frontend | HieuLT | Source date | First commit is not necessarily first work day.
Snapshot | 07/10/2026 23:59 ICT | BE e24d9eef; FE 3b933051 | Main branches at cutoff | HieuLT | Git evidence | Current later documents are reference only, not dated evidence at cutoff.
Est. vs actual | Points in G; actual points J blank | Uploaded V1 + reconstructed task complexity | 3 / 5 / 8 points | All members | Estimated | No conversion between story points and hours/person-days.
Done | Implemented work-package scope | Code/commit/report cited per row | Prototype verification has separate scope | Assigned member | Implementation only | Not UAT approval or automatic end-to-end product acceptance.
Source access | Report 1, RTW, Test Plan text; FDS generator; SRS change/handoff reports; Git code/docs | backend/capstone-docs; frontend/plans | FDS v0.4 / SRS v0.9.21 handoff | HieuLT | Read/reference | Large SRS/TDS/FDS binaries unavailable via connector; content checked through source scripts and repository reports.
Dashboard / Scope review | Dashboard formulas repaired | Uploaded workbook | 09/10/2026 | LinhNDM | Dashboard fixed; Scope retained | Scope approver label normalized to LinhNDM. Scope F effort-ratio interpretation remains open (D-008).

## Q&A
Q&A — IELTSPath Phase 1
Log ALL questions — technical, business, process · Track from Open → Answered → Closed · Never delete a row
# | Date | Question | Raised By | Directed To | Priority | Due Date | Answer / Resolution | Answered By | Answered Date | Status | Notes
Q-001 | 2026-10-07 | What does Phase 1 cover, and how does it relate to WBS Iteration 1? | LinhNDM | HieuLT | High | 2026-10-09 | Proposed baseline: Iteration 1 covers 09/09–07/10 foundation/core and BE course/multi-skill. Iteration 2 closes FE contract/E2E gaps; Iteration 3 contains prioritized extensions. See WBS iteration plan. Team must confirm acceptance scope; dates alone do not prove acceptance. |  |  | Open | capstone-docs/rp_5.0_test_plan/Report 5.0_TestPlan_IELTSPath_v1.docx; original WBS A5:L17. Review question recorded 07/10/2026; not an earlier meeting minute. ¦ LinhNDM: supervisor asking; Directed To: responsible team member. Answered By is a simulated response assignment based on cited evidence.
Q-002 | 2026-10-07 | Who are the Phase 1 users and what problem does IELTSPath address? | LinhNDM | HieuLT | Medium | 2026-10-07 | New visitors try the centre teaching before enrolment. Current and waiting-list learners practise between classes and see their own progress. | HieuLT | 2026-10-07 | Answered | backend/capstone-docs/rp_1_vision-scope/Report 1_Vision_Scope_IeltsPath.docx §1, §3, §5 ¦ LinhNDM: supervisor asking; Directed To: responsible team member. Answered By is a simulated response assignment based on cited evidence.
Q-003 | 2026-10-07 | Which implementation is the current learning backend? | LinhNDM | HieuLT | High | 2026-10-07 | Java learning-service owns lesson progress, mastery, review, practice and assessment-result consumption. The former Python AI Learning flow is superseded. | HieuLT | 2026-10-07 | Answered | backend/AGENTS.md §1; backend/docs/system-architecture.md ¦ LinhNDM: supervisor asking; Directed To: responsible team member. Answered By is a simulated response assignment based on cited evidence.
Q-004 | 2026-10-07 | What authentication and authorization contract must FE follow? | LinhNDM | PhuPD | High | 2026-10-07 | Use Gateway APIs, Bearer access token and the existing refresh flow. Gateway validates external JWT and signs an internal JWT. Protected services enforce role and ownership. | PhuPD | 2026-10-07 | Answered | backend/docs/fe-main-flow-guide.md §1, §4; frontend/src/lib/httpClient.ts; backend/README.md ¦ LinhNDM: supervisor asking; Directed To: responsible team member. Answered By is a simulated response assignment based on cited evidence.
Q-005 | 2026-10-07 | When does a learner unlock a topic test? | LinhNDM | HieuLT | High | 2026-10-07 | Core final-test assignment requires all relevant lessons completed, Practice cleared and applicable reviews closed; topic pass requires >=70%. The 07/10 multi-skill BE clears Practice per objective skill; FE must align to updated contracts. | HieuLT | 2026-10-07 | Answered | backend/docs/fe-main-flow-guide.md §3–4; frontend/plans/reports/e2e-practice-261005/report.md ¦ LinhNDM: supervisor asking; Directed To: responsible team member. Answered By is a simulated response assignment based on cited evidence.
Q-006 | 2026-10-07 | Are live Writing AI grading and points already fully accepted? | LinhNDM | HieuLT | High | 2026-10-11 | Lesson essay integration exists: at least 3 points, 3-point charge, request replay and >=60-second FE timeout. Live LLM quality and complete paid retry behaviour need separate acceptance evidence. |  |  | Open | backend/docs/fe-main-flow-guide.md; frontend/plans/reports/e2e-practice-261005/report.md; capstone-docs/rp_5.0_test_plan/Report 5.0_TestPlan_IELTSPath_v1.docx TP-LRN-06 ¦ LinhNDM: supervisor asking; Directed To: responsible team member. Answered By is a simulated response assignment based on cited evidence.
Q-007 | 2026-10-07 | Is Listening playback ready for the Phase 1 demo? | LinhNDM | TungVPH | High | 2026-10-09 | AudioBlock is integrated. Provide valid media and test playback. Transcript must appear only when the backend exposes it after the permitted submission. |  |  | Open | backend/docs/fe-main-flow-guide.md; frontend/plans/reports/e2e-practice-261005/report.md; capstone-docs/rp_5.0_test_plan/Report 5.0_TestPlan_IELTSPath_v1.docx ¦ LinhNDM: supervisor asking; Directed To: responsible team member. Answered By is a simulated response assignment based on cited evidence.
Q-008 | 2026-10-07 | Does premium activation require online payment? | LinhNDM | TungVPH | Medium | 2026-10-07 | No. Sales distribute activation cards outside the system. The system records activations and grants access or points; payment, invoicing and revenue reporting are excluded. | TungVPH | 2026-10-07 | Answered | backend/capstone-docs/rp_1_vision-scope/Report 1_Vision_Scope_IeltsPath.docx §4.2 LI-01; backend/capstone-docs/rp_3.0_system-requirements-system/Report 3.0_SRS_IELTSPath_IeltsPath_v1.docx SC-03 ¦ LinhNDM: supervisor asking; Directed To: responsible team member. Answered By is a simulated response assignment based on cited evidence.
Q-009 | 2026-10-07 | Is a premium badge sufficient access protection? | LinhNDM | HieuLT | High | 2026-10-11 | No. Current MVP has UI flags but no learning subscription enforcement. Decide whether Phase 1 is free-only or must add server-side entitlement before a paid release. |  |  | Open | backend/docs/fe-main-flow-guide.md §6; capstone-docs/rp_5.0_test_plan/Report 5.0_TestPlan_IELTSPath_v1.docx Out of Scope ¦ LinhNDM: supervisor asking; Directed To: responsible team member. Answered By is a simulated response assignment based on cited evidence.
Q-010 | 2026-10-07 | Can the 05/10 E2E report be described as full browser acceptance? | LinhNDM | SonLT | High | 2026-10-07 | No. Fresh registration, test submit and result were exercised in browser. Lessons and Practice used API assistance; review was N/A. Full unassisted UI acceptance is still needed. | SonLT | 2026-10-07 | Answered | frontend/plans/reports/e2e-main-flow-261005-fresh/report.md Method and checklist; frontend/plans/reports/e2e-practice-261005/report.md E2E note ¦ LinhNDM: supervisor asking; Directed To: responsible team member. Answered By is a simulated response assignment based on cited evidence.
Q-011 | 2026-10-07 | Are band courses and placement recommendation available across BE and FE? | LinhNDM | HoangNV | Medium | 2026-10-10 | Backend course work merged on 07/10. FE currently loads topics and has no course methods in LearningApi. Live course smoke and phase inclusion remain open. |  |  | Open | backend/plans/261006-2228-course-band-levels/plan.md final verification; frontend/src/features/learning-path/api/learningApi.ts ¦ LinhNDM: supervisor asking; Directed To: responsible team member. Answered By is a simulated response assignment based on cited evidence.
Q-012 | 2026-10-07 | Are mixed-skill lessons and free assessment AI essays completed? | LinhNDM | HieuLT | Medium | 2026-10-07 | Backend multi-skill implementation merged 07/10 via 8d2d2bb (#47), with phase verification and documented concerns. FE mixed-skill/assessment-essay alignment and live-provider acceptance are not established. See WBS-074/075 and C-008. | HieuLT | 2026-10-07 | Answered | BE merge 8d2d2bb; plans/261006-2309-multi-skill-lessons/plan.md verification; FE 3b933051. Supersedes V1 stale Pending claim. ¦ LinhNDM: supervisor asking; Directed To: responsible team member. Answered By is a simulated response assignment based on cited evidence.
Q-013 | 2026-10-07 | Should Speaking, full mock tests, mobile, games and community count as Phase 1 accepted features? | LinhNDM | HieuLT | High | 2026-10-09 | They are product features in Vision & Scope, but outside the priority test v1 boundary or lack full flow evidence. Confirm future delivery allocation; do not mark accepted from code presence alone. |  |  | Open | backend/capstone-docs/rp_1_vision-scope/Report 1_Vision_Scope_IeltsPath.docx §4.1; capstone-docs/rp_5.0_test_plan/Report 5.0_TestPlan_IELTSPath_v1.docx Out of Scope ¦ LinhNDM: supervisor asking; Directed To: responsible team member. Answered By is a simulated response assignment based on cited evidence.
Q-014 | 2026-10-07 | What are the official reporters, hours, dates and approvals for timesheets? | LinhNDM | HieuLT | High | 2026-10-10 | Five implementation members confirmed. PM and project reviewer are both LinhNDM; HieuLT remains tech lead/task coordinator. TimeLogs contains 48 consecutively numbered entries totaling 211.5 hours. PM identity is confirmed; actual member timesheets and historical approval records still require reconciliation. |  |  | Open | Original Scope names PhuPD, HieuLT, TungVPH; no row-level work-hour evidence found. ¦ LinhNDM: supervisor asking; Directed To: responsible team member. Answered By is a simulated response assignment based on cited evidence.
Q-015 | 2026-10-07 | Have the updated SRS, TDS and test plan been formally approved? | LinhNDM | HieuLT | High | 2026-10-11 | Formal document approval not evidenced. SRS was updated to v0.9.21 on 07/10, while RTW/FDS and the later Test Plan still need course/multi-skill reconciliation. The Test Plan now includes browser system testing; the old mock-only claim is superseded. |  |  | Open | backend/capstone-docs/rp_3.0_system-requirements-system/Report 3.0_SRS_IELTSPath_IeltsPath_v1.docx metadata; capstone-docs/rp_5.0_test_plan/Report 5.0_TestPlan_IELTSPath_v1.docx baseline/out-of-scope; frontend/plans/reports/e2e-main-flow-261005-fresh/report.md ¦ LinhNDM: supervisor asking; Directed To: responsible team member. Answered By is a simulated response assignment based on cited evidence.

## TimeLogs
TimeLogs — IELTSPath Phase 1
Log time daily · Link every entry to a WBS Ref · Approved by PM · # Hours must be filled — leave no blank
# | Date | Reporter | WBS Ref | Task Description | Activity | Type | # Hours | Product / Work Product | Iteration | Status | Approved By | Updated | Notes
TL-001 | 2026-09-09 | PhuPD | WBS-065 | Project kickoff, initial problem/scope and member task allocation | Meeting | Newly-Created | 1.5 | Initial project plan | Iteration 1 | Approved | LinhNDM | 2026-10-09 | Start date: Report 1; participation estimated.
TL-002 | 2026-09-09 | HoangNV | WBS-065 | Project kickoff, initial problem/scope and member task allocation | Meeting | Newly-Created | 1.5 | Initial project plan | Iteration 1 | Approved | LinhNDM | 2026-10-09 | Start date: Report 1; participation estimated.
TL-003 | 2026-09-09 | SonLT | WBS-065 | Project kickoff, initial problem/scope and member task allocation | Meeting | Newly-Created | 1.5 | Initial project plan | Iteration 1 | Approved | LinhNDM | 2026-10-09 | Start date: Report 1; participation estimated.
TL-004 | 2026-09-09 | HieuLT | WBS-065 | Project kickoff, initial problem/scope and member task allocation | Meeting | Newly-Created | 1.5 | Initial project plan | Iteration 1 | Submitted |  | 2026-10-07 | Start date: Report 1; participation estimated.
TL-005 | 2026-09-09 | TungVPH | WBS-065 | Project kickoff, initial problem/scope and member task allocation | Meeting | Newly-Created | 1.5 | Initial project plan | Iteration 1 | Approved | LinhNDM | 2026-10-09 | Start date: Report 1; participation estimated.
TL-006 | 2026-09-15 | HieuLT | WBS-055 | Initialize React / TypeScript / Vite and application folders | Coding | Newly-Created | 3 | Frontend scaffold | Iteration 1 | Submitted |  | 2026-10-07 | FE 241abca.
TL-007 | 2026-09-15 | HieuLT | WBS-055 | Configure Tailwind, shadcn setup, theme and import aliases | Coding | Newly-Created | 2.5 | FE styling foundation | Iteration 1 | Submitted |  | 2026-10-07 | FE 241abca.
TL-008 | 2026-09-15 | HieuLT | WBS-055 | Configure Node/npm constraints, dependencies, lint/typecheck/build | Coding | Newly-Created | 2 | FE tooling baseline | Iteration 1 | Submitted |  | 2026-10-07 | FE 241abca, 8581a72.
TL-009 | 2026-09-16 | HieuLT | WBS-053 | Implement Gateway routing, external/internal JWT and service security | Coding | Updating | 5 | Ingress and security baseline | Iteration 1 | Submitted |  | 2026-10-07 | BE 218e071, a18a44e.
TL-010 | 2026-09-17 | HieuLT | WBS-051 | Initialize Maven multi-module build and service structure | Coding | Newly-Created | 2.5 | Backend scaffold | Iteration 1 | Submitted |  | 2026-10-07 | BE 218e071: Maven multi-module build and backend service structure.
TL-011 | 2026-09-17 | TungVPH | WBS-052 | Set up Config Server, configuration repository and Eureka | Coding | Newly-Created | 3.5 | Service infrastructure | Iteration 1 | Approved | LinhNDM | 2026-10-09 | BE 218e071.
TL-012 | 2026-09-17 | TungVPH | WBS-054 | Set up Docker Compose, PostgreSQL and container configuration | Coding | Updating | 4 | Local infrastructure setup | Iteration 1 | Approved | LinhNDM | 2026-10-09 | BE 218e071, dac8b03.
TL-013 | 2026-09-17 | PhuPD | WBS-069 | Initialize User service module, configuration and account/auth structure | Coding | Newly-Created | 1.5 | User service initialization | Iteration 1 | Approved | LinhNDM | 2026-10-09 | BE 218e071: User service initialization; auth updates and tests recorded separately.
TL-014 | 2026-09-22 | PhuPD | WBS-069 | Add user unit tests and HttpOnly-cookie authentication | Coding | Updating | 6.5 | User/auth APIs and tests | Iteration 1 | Approved | LinhNDM | 2026-10-09 | BE 115c36d, 2c9d37f.
TL-015 | 2026-09-22 | TungVPH | WBS-082 | Scaffold Notification service and register shared configuration/routing | Coding | Newly-Created | 1.5 | Notification service scaffold/config | Iteration 1 | Approved | LinhNDM | 2026-10-09 | BE 11a78fa6: Notification scaffold/configuration/routing; delivery, reminders and retry remain outstanding.
TL-016 | 2026-09-23 | TungVPH | WBS-066 | Initialize Content service, Flyway schema and base content APIs | Coding | Updating | 3 | Content service baseline | Iteration 1 | Approved | LinhNDM | 2026-10-09 | BE 11a78fa: Content module, schema and base APIs.
TL-017 | 2026-09-23 | SonLT | WBS-079 | Build mock learning workspace and UI prototype | Coding | Updating | 6 | Initial learning UI | Iteration 1 | Approved | LinhNDM | 2026-10-09 | FE 6ffb8a4, b8d3f3f.
TL-018 | 2026-09-23 | PhuPD | WBS-068 | Initialize Access service, plans/points APIs and Access tests | Coding | Newly-Created | 2.5 | Access service baseline | Iteration 1 | Approved | LinhNDM | 2026-10-09 | BE 99b7d4f / 3678274: Access service initialization and tests.
TL-019 | 2026-09-23 | TungVPH | WBS-081 | Initialize Community service and initial community backend code | Coding | Newly-Created | 3 | Community service initial module/code | Iteration 1 | Approved | LinhNDM | 2026-10-09 | BE 559718a4 / 10433389: initial Community module/code; complete community flows remain outstanding.
TL-020 | 2026-09-23 | HoangNV | WBS-071 | Initialize historical Learning Support service before Library/activity migration | Coding | Newly-Created | 1.5 | Historical Learning Support module | Iteration 1 | Approved | LinhNDM | 2026-10-09 | BE 3512cc8f / b886d3f2: historical Learning Support module, later replaced by Library/activity migration.
TL-021 | 2026-09-24 | PhuPD | WBS-067 | Initialize Assessment service and attempt/answer domain structure | Coding | Updating | 3.5 | Assessment service baseline | Iteration 1 | Approved | LinhNDM | 2026-10-09 | BE c087a3f: Assessment module and attempt/answer structure.
TL-022 | 2026-09-24 | HieuLT | WBS-070 | Build the historical Python AI Learning prototype and local runtime | Coding | Updating | 4 | Earlier learning prototype | Iteration 1 | Submitted |  | 2026-10-07 | BE e1cf196, f430f61, 4ba99a5, 2860664.
TL-023 | 2026-09-24 | PhuPD | WBS-080 | Initialize Game service and initial game backend code | Coding | Newly-Created | 3 | Game service initial module/code | Iteration 1 | Approved | LinhNDM | 2026-10-09 | BE c12541b6 / c2561e23: initial Game module/code; full gameplay remains outstanding.
TL-024 | 2026-09-29 | SonLT | WBS-079 | Record learning page and interactive-tool verification | Testing | Reviewing | 3.5 | UI verification work | Iteration 1 | Approved | LinhNDM | 2026-10-09 | FE 43f537b.
TL-025 | 2026-09-29 | HieuLT | WBS-076 | Record backend MVP end-to-end acceptance evidence | Testing | Reviewing | 4 | Backend E2E report | Iteration 1 | Submitted |  | 2026-10-07 | BE 9140128.
TL-026 | 2026-09-30 | SonLT | WBS-079 | Add shared UI utilities, learning pages and interactive workspaces | Coding | Updating | 8 | FE pages and UI components | Iteration 1 | Approved | LinhNDM | 2026-10-09 | FE 015701d, b93604b.
TL-027 | 2026-09-30 | HieuLT | WBS-059 | Implement AssessmentCompleted consumer and update learning progress, review/test assignments | Coding | Updating | 8 | Learning result consumer / progress updates | Iteration 1 | Submitted |  | 2026-10-07 | BE 72d4e99 / dd109f5: result consumer, progress and review/test assignment updates.
TL-028 | 2026-09-30 | TungVPH | WBS-066 | Seed Writing, Listening and Reading-hint learning content | Coding | Updating | 5 | Published demo curriculum | Iteration 1 | Approved | LinhNDM | 2026-10-09 | BE 37a330c, 555ab81, a163b6b, 70f17a2.
TL-029 | 2026-10-01 | SonLT | WBS-071 | Initialize Library service; migrate activity/streak into User and remove legacy Learning Support | Coding | Updating | 6 | Library initialization / service migration | Iteration 1 | Approved | LinhNDM | 2026-10-09 | BE 465f543, d762660, fec5d14, ab613b1.
TL-030 | 2026-10-01 | TungVPH | WBS-066 | Implement lesson content endpoints and learner answer-redaction guard | Coding | Updating | 5 | Content lesson APIs / security | Iteration 1 | Approved | LinhNDM | 2026-10-09 | BE 34335aa, 20bed3b.
TL-031 | 2026-10-01 | HieuLT | WBS-070 | Initialize Java Learning service and implement lesson/mastery persistence | Coding | Updating | 8 | Java learning runtime | Iteration 1 | Submitted |  | 2026-10-07 | BE d96ab9e, 8195982.
TL-032 | 2026-10-02 | HieuLT | WBS-070 | Implement lesson essay grading, Listening media contract and hint visibility | Coding | Updating | 8 | Writing / Listening / Reading APIs | Iteration 1 | Submitted |  | 2026-10-07 | BE d08337a, 896fa2c, 60c72dd.
TL-033 | 2026-10-02 | HoangNV | WBS-056 | Connect frontend main flow to backend and correct submission behaviour | Coding | Updating | 8 | HTTP auth and learning flow | Iteration 1 | Approved | LinhNDM | 2026-10-09 | FE 5505282, f1d5bb0.
TL-034 | 2026-10-03 | HieuLT | WBS-057 | Implement skill-local progress, required Practice and remediation ladder | Coding | Updating | 8 | Practice / review rules | Iteration 1 | Submitted |  | 2026-10-07 | BE a3447b9, a90e5e1, 853ab82, 1a96c77, 8bb72cf, 6d9f623.
TL-035 | 2026-10-03 | HoangNV | WBS-076 | Document browser core-flow checks and API-assisted fresh-user E2E | Testing | Reviewing | 4.5 | FE E2E reports | Iteration 1 | Approved | LinhNDM | 2026-10-09 | FE caaf987, 6716dd9.
TL-036 | 2026-10-04 | HoangNV | WBS-012 | Fix assessment question snapshot parsing and integrate Practice/review UI | Coding | Bug-Fix | 8 | Test runner / Practice / Review UI | Iteration 1 | Approved | LinhNDM | 2026-10-09 | FE d2b737d, 6716dd9.
TL-037 | 2026-10-04 | HieuLT | WBS-065 | Complete requirements/data/NFR sections and record scope/BA review | Analyzing | Updating | 5.5 | Requirements and review reports | Iteration 1 | Submitted |  | 2026-10-07 | BE b2323f1 / f2e00d4 / 36b1092: requirements sections and BA/scope review.
TL-038 | 2026-10-05 | SonLT | WBS-001 | Build home access-plan views/navigation and merge real authentication | Coding | Updating | 6 | Home/auth integration | Iteration 1 | Approved | LinhNDM | 2026-10-09 | FE 5a0abcb, ac25901.
TL-039 | 2026-10-05 | HoangNV | WBS-005 | Implement forgot/reset pages and align password length/confirmation | Coding | Updating | 5 | Password recovery UI | Iteration 1 | Approved | LinhNDM | 2026-10-09 | FE 553a320, 51e64eb.
TL-040 | 2026-10-05 | HieuLT | WBS-072 | Stabilize course-test timestamp fixture and add course demo content | Coding | Bug-Fix | 4.5 | Course test fix / demo seeds | Iteration 1 | Pending |  | 2026-10-07 | BE a078675, a18241b.
TL-041 | 2026-10-06 | HieuLT | WBS-072 | Implement band courses, placement recommendations and course tests | Coding | Updating | 8 | Backend course extension | Iteration 1 | Pending |  | 2026-10-07 | BE d867758, 5926d93, 6935369, 559bf82, a401a33, 5ea098a.
TL-042 | 2026-10-06 | PhuPD | WBS-065 | Prepare/review RTW requirements, permission and business-rule traceability | Designing | Reviewing | 6 | RTW workbook | Iteration 1 | Pending |  | 2026-10-07 | BE ca065f6c / 4a925910: RTW preparation and traceability review.
TL-043 | 2026-10-07 | HoangNV | WBS-075 | Review course/multi-skill FE contracts, DTO changes and integration backlog | Analyzing | Reviewing | 5 | FE integration plan | Iteration 1 | Pending |  | 2026-10-07 | BE contract vs FE LearningApi; analysis only, code not completed.
TL-044 | 2026-10-07 | SonLT | WBS-077 | Build/review FDS screens, jobs and diagrams; record SRS handoff gaps | Designing | Reviewing | 6 | FDS v0.4 / diagrams | Iteration 1 | Pending |  | 2026-10-07 | BE 4153dd06 / 1b4b26b8.
TL-045 | 2026-10-07 | HieuLT | WBS-065 | Review requirements baseline and assign remaining iteration work | Reviewing | Reviewing | 2.5 | Iteration review | Iteration 1 | Pending |  | 2026-10-07 | Report 1 / SRS course-multi-skill handoff.
TL-046 | 2026-10-07 | TungVPH | WBS-078 | Review environment runbook, test prerequisites and operational gaps | Reviewing | Reviewing | 6 | Environment checklist | Iteration 1 | Pending |  | 2026-10-07 | BE README / Docker setup; no new test pass asserted.
TL-047 | 2026-10-07 | HieuLT | WBS-074 | Implement multi-skill lesson/Practice contracts and per-skill clearance | Coding | Newly-Created | 4 | Multi-skill backend code | Iteration 1 | Pending |  | 2026-10-07 | BE 8d2d2bb2 / 51468f60: multi-skill backend; FE alignment and live acceptance remain outstanding.
TL-048 | 2026-10-07 | PhuPD | WBS-060 | Implement Assessment AI worker for topic/course gate essays and examiner fallback | Coding | Newly-Created | 3 | Assessment AI gate-grading worker | Iteration 1 | Pending |  | 2026-10-07 | BE 34852704 / 8d2d2bb2: AI gate-essay worker; Speaking and live-provider acceptance excluded.
Hours by activity
Activity | Hours
Training | 0
Analyzing | 10.5
Designing | 12
Coding | 161
Testing | 12
Reviewing | 8.5
Deploying | 0
Meeting | 7.5
Total | 211.5
Hours by member and review status
Member | Hours | Approved | Submitted | Pending
PhuPD | 27.5 | 18.5 | 0 | 9
HoangNV | 33.5 | 28.5 | 0 | 5
SonLT | 37 | 31 | 0 | 6
HieuLT | 81 | 0 | 62 | 19
TungVPH | 32.5 | 26.5 | 0 | 6
Total | 211.5 | 104.5 | 62 | 45
TimeLog tracking notes
PM and project reviewer: LinhNDM. TimeLogs are reviewed by the PM; implementation status is tracked separately in WBS. One entry records one person, one date and one WBS package, with a maximum of 8 hours/person/day. Entries are sorted by date and numbered TL-001 to TL-048. Hours are retrospective estimates based on repository work packages. Git references identify code changes; service initialization does not imply full feature delivery.

## Defects
Defects — IELTSPath Phase 1
Log ALL defects found in any review or test · Severity: Critical / High / Medium / Low · Status: Pending → Open → Fixed → Closed
# | Date Found | Defect Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Activity | Product | Product Details | Assigned By | Assigned To | Status | Fixed Date | Fixed In Version | Updated | Notes
D-001 | 2026-10-05 | Topic lesson mapper omitted practiceStatus | Complete lessons while Practice is REQUIRED; open topic. | Show remaining Practice gate and a clear next action. | Gate state was dropped from mapped lessons. | High | High | System Test | Frontend | Topic mapper and final-test checklist | HieuLT | HoangNV | Fixed | 2026-10-05 | FE 6716dd9 (main 3b933051) | 2026-10-07 | frontend/plans/reports/e2e-main-flow-261005/fix-ux-cta-gates.md; frontend/plans/reports/e2e-practice-261005/report.md confirms gap closed; full fresh browser retest still open. ¦ Assignment proposed from team roles; not a historical signed assignment. Fixed indicates documented code fix; separate browser retest required, not Closed.
D-002 | 2026-10-05 | PRACTICE_REQUIRED error lacked actionable handling | Try to assign a test while Practice is required. | Explain remaining Practice, show lesson links, reload state. | Generic locked message did not explain Practice requirement. | High | High | System Test | Frontend | Assignment error handling | HieuLT | HoangNV | Fixed | 2026-10-05 | FE 6716dd9 (main 3b933051) | 2026-10-07 | frontend/plans/reports/e2e-main-flow-261005/fix-ux-cta-gates.md; frontend/plans/reports/e2e-practice-261005/report.md ¦ Assignment proposed from team roles; not a historical signed assignment. Fixed indicates documented code fix; separate browser retest required, not Closed.
D-003 | 2026-10-05 | Pending reviews were not hydrated in topic view | Open a topic with pending review. | Load reviews, display review checklist, hide locked test CTA. | Learner could not see why the final test was locked. | High | High | System Test | Frontend | Topic ReviewGate / GET reviews | HieuLT | HoangNV | Fixed | 2026-10-05 | FE 6716dd9 (main 3b933051) | 2026-10-07 | frontend/plans/reports/e2e-main-flow-261005/fix-ux-cta-gates.md; frontend/plans/reports/e2e-practice-261005/report.md browser smoke only. ¦ Assignment proposed from team roles; not a historical signed assignment. Fixed indicates documented code fix; separate browser retest required, not Closed.
D-004 | 2026-10-05 | Primary CTA click reliability requires fresh retest | Use accessibility-ref click on login or test CTA. | Accessible activation consistently reaches the button handler. | Automation sometimes missed; Enter or JS click completed the action. | Medium | Medium | System Test | Frontend | Auth and learning primary CTA | HieuLT | HoangNV | Pending |  |  | 2026-10-07 | frontend/plans/reports/e2e-main-flow-261005/fix-ux-cta-gates.md records layout fix, but frontend/plans/reports/e2e-main-flow-261005-fresh/report.md repeats observation. Application-wide reproduction is not established. ¦ Assignment proposed from team roles; not a historical signed assignment. Verification concern retained; not a confirmed universal product failure.
D-005 | 2026-10-05 | Assessment result accessibility snapshot omitted visible score details | Inspect result page accessibility tree after submit. | Score percent and correct-answer count are perceivable by assistive technology. | Interactive snapshot lacked percent/count despite visible UI text. | Medium | Medium | System Test | Frontend | Result summary accessibility | HieuLT | HoangNV | Pending |  |  | 2026-10-07 | frontend/plans/reports/e2e-main-flow-261005/report.md item 5. Verify with a screen reader before confirming defect. ¦ Assignment proposed from team roles; not a historical signed assignment.
D-006 | 2026-10-07 | Dashboard open-item formulas used incorrect status columns | Populate Q&A, Defects and Issues statuses; inspect Dashboard formulas. | Count Issues K, Defects N and Q&A K; risk priority from score F | Corrected Dashboard uses the actual status columns and includes risks with score >=4. | Medium | High | Review | Tracking workbook | Dashboard D8, G5/C8 and F5/B8 | HieuLT | HieuLT | Fixed | 2026-10-09 | Report 2.1 Dashboard update — 09/10/2026 | 2026-10-09 | Formulas recalculated and checked against source records. Awaiting LinhNDM review; not Closed.
D-007 | 2026-10-07 | Dashboard iteration formulas excluded WBS rows after row 68 | Compare WBS headers with Dashboard iteration COUNTIF/SUMIF formulas. | Count all 82 WBS packages through row 86 | Dashboard now uses WBS H for iteration, G for points and K for status across rows 5:86. | Medium | Medium | Review | Tracking workbook | Dashboard iteration table B27:J31; WBS summary A88:G93 | HieuLT | HieuLT | Fixed | 2026-10-09 | Report 2.1 Dashboard update — 09/10/2026 | 2026-10-09 | Full WBS range recalculated and reconciled with WBS summary. Awaiting LinhNDM review; not Closed.
D-008 | 2026-10-07 | Scope completion percentage still represents effort usage | Compare Scope headers and formulas with Dashboard deliverable counts. | Count statuses in Scope G and treat effort usage separately from completion. | Dashboard counts Scope G correctly. Scope F remains actual/estimated effort, which is not a completion measure. | Medium | Medium | Review | Tracking workbook | Scope F and Dashboard B5:E5 | HieuLT | HieuLT | Open |  |  | 2026-10-09 | Dashboard deliverable counts repaired; remaining Scope F interpretation needs separate correction. Defect stays Open.

## Issues
Issues — IELTSPath Phase 1
Issues = problems that have already occurred · Risks = problems that might occur (see Risks sheet) · Category: Technical / Process / Resource / Scope / External
# | Date | Issue Description | Category | Priority | Impact (Scope / Effort / Timeline) | Raised By | Owner | Due Date | Resolution | Status | Closed Date | Notes
I-001 | 2026-10-07 | Phase 1 boundary is not explicitly baselined against WBS. | Scope | High | Acceptance and phase reporting may use different feature populations. | HieuLT | HieuLT | 2026-10-12 | Confirm reconstructed WBS iteration windows, product acceptance list and extension priorities. See WBS plan, Q-001. Creating the plan does not supply formal acceptance. | Open |  | capstone-docs/rp_5.0_test_plan/Report 5.0_TestPlan_IELTSPath_v1.docx; original WBS ¦ Owner/deadline are proposed resolution assignments.
I-002 | 2026-10-07 | Actual member hours and approved timesheets were not supplied. | Process | High | Approved actual effort and productivity cannot be calculated. | HieuLT | HieuLT | 2026-10-12 | Validate the 48-row, 211.5-hour retrospective timesheet against member records, dates, hours and approval evidence. Review states are Pending, Submitted and Approved. See Q-014. | Open |  | Original tracking workbook contains unrelated sample hours and reporter. ¦ Owner/deadline are proposed resolution assignments.
I-003 | 2026-10-07 | Full fresh-user browser Practice/review/pass-to-next-topic flow lacks evidence. | Technical | High | Core MVP acceptance has an unverified UI segment. | HieuLT | SonLT | 2026-10-12 | Run without API gate clearance: lesson, first Practice submit, failed Practice review, pass test, next topic. Capture artifacts. | Open |  | frontend/plans/reports/e2e-main-flow-261005-fresh/report.md; frontend/plans/reports/e2e-practice-261005/report.md ¦ Owner/deadline are proposed resolution assignments.
I-004 | 2026-10-07 | Live Writing feedback quality and Listening media acceptance are unverified. | Technical | High | Writing quality and audio demo readiness cannot be concluded from UI/API wiring. | HieuLT | TungVPH | 2026-10-16 | Review real essays against rubric and play configured audio; verify timeout, points retry and transcript visibility. | Open |  | capstone-docs/rp_5.0_test_plan/Report 5.0_TestPlan_IELTSPath_v1.docx; frontend/plans/reports/e2e-practice-261005/report.md ¦ Owner/deadline are proposed resolution assignments.
I-005 | 2026-10-07 | SRS v0.9.21 course/multi-skill updates are not synchronized into RTW/FDS and Test Plan. | Process | High | Specifications, permission/feature traceability and tests can target different gates and feature populations. | HieuLT | SonLT | 2026-10-16 | Update FT-15/20/55, course/placement flow, BR-35..40, mixed-skill rules and assessment essay fallback; reconcile RTW/FDS/Test Plan. The latest Test Plan includes HTTP/browser tests; old mock-only finding withdrawn. | Open |  | BE 29810100 / de62b4eb; plans/reports/srs-to-rtw-fds-handoff-261007-1934-course-multi-skill-report.md. Later Test Plan reference still lists 54 features and one-skill assumptions; no completed reconciliation asserted.
I-006 | 2026-10-07 | Premium enforcement is absent in the current learning MVP. | Scope | High | Paid content cannot be accepted as protected solely by FE labels. | HieuLT | HieuLT | 2026-10-16 | Confirm free-only demo scope or implement entitlement checks as an approved follow-up before paid release. | Open |  | backend/docs/fe-main-flow-guide.md §6; capstone-docs/rp_5.0_test_plan/Report 5.0_TestPlan_IELTSPath_v1.docx ¦ Owner/deadline are proposed resolution assignments.
I-007 | 2026-10-07 | New course/multi-skill BE contracts are not aligned with FE course APIs and full browser acceptance. | Technical | Medium | End-to-end course recommendation and course-test completion remain incomplete. | HieuLT | HoangNV | 2026-10-21 | Complete WBS-073/075 after WBS-072/074; verify course selection, mixed Practice, essay gate submission, result processing and next topic. Fresh unassisted browser evidence required. | Open |  | backend/plans/261006-2228-course-band-levels/plan.md final concerns; frontend/src/features/learning-path/api/learningApi.ts ¦ Owner/deadline are proposed resolution assignments.
I-008 | 2026-10-07 | SRS/TDS metadata and formal approval records remain incomplete. | Process | Medium | Cannot substantiate a formally approved requirement/design baseline. | HieuLT | HieuLT | 2026-10-16 | Fill authors, reviewers, dates and approval references; reconcile Report 1, SRS and implementation. | Open |  | backend/capstone-docs/rp_3.0_system-requirements-system/Report 3.0_SRS_IELTSPath_IeltsPath_v1.docx metadata; backend/capstone-docs/rp_1_vision-scope/Report 1_Vision_Scope_IeltsPath.docx In Review; original Scope Approved By is not approval evidence. ¦ Owner/deadline are proposed resolution assignments.
I-009 | 2026-10-07 | Reset UI wiring exists but email delivery and OAuth acceptance are not evidenced. | External | Medium | Real password recovery and social login must not be reported as accepted. | HieuLT | PhuPD | 2026-10-16 | Reset UI is in Iteration 1; verify real email token delivery separately. OAuth remains Iteration 3 and unavailable until implementation/QA. Do not report either external flow as accepted. | Open |  | frontend/docs/journals/2026-10-05-fe-auth-forgot-reset-wiring.md; capstone-docs/rp_5.0_test_plan/Report 5.0_TestPlan_IELTSPath_v1.docx ¦ Owner/deadline are proposed resolution assignments.

## Risks
Risks — IELTSPath Phase 1
Probability: High(3) / Medium(2) / Low(1) · Impact: High(3) / Medium(2) / Low(1) · Risk Score = P × I · Score ≥ 6 = Critical; 4-5 = High; 2-3 = Medium; 1 = Low
# | Risk Description | Category | Probability | Impact | Risk Score (P×I) | Mitigation Plan | Contingency Plan | Owner | Due Date | Status | Notes
R-001 | Scope expands from the core MVP to every full-product feature before Phase 1 acceptance. | Scope | High | High | 9 | Baseline phase requirements; keep course/multi-skill/Speaking/mobile allocation explicit. | Replan approved changes and defer unaccepted extensions. | HieuLT | 2026-10-09 | Open | backend/capstone-docs/rp_1_vision-scope/Report 1_Vision_Scope_IeltsPath.docx versus capstone-docs/rp_5.0_test_plan/Report 5.0_TestPlan_IELTSPath_v1.docx; assessment: project-review judgement, not measured incidence. ¦ Assessment qualitative; owner and mitigation due date proposed.
R-002 | Frontend and backend gates or DTOs drift during course and lesson changes. | Technical | Medium | High | 6 | Freeze/version course and multi-skill DTO contracts; align FE skills[], course endpoints and essay flow, then run fresh-user integration. Link WBS-073/075 and I-007. | Keep the validated MVP baseline until compatible changes pass. | HoangNV | 2026-10-12 | Open | backend/docs/fe-main-flow-guide.md; backend/plans/261006-2228-course-band-levels/plan.md; backend/plans/261006-2309-multi-skill-lessons/plan.md; assessment: project-review judgement, not measured incidence. ¦ Assessment qualitative; owner and mitigation due date proposed.
R-003 | LLM timeout, cost or grading inconsistency disrupts Writing feedback. | External | Medium | High | 6 | Validate rubric/corpus, timeout, quota and point idempotency; keep provider secrets server-side. | Report grading unavailable and support safe retry without duplicate debit. | HieuLT | 2026-10-21 | Open | capstone-docs/rp_5.0_test_plan/Report 5.0_TestPlan_IELTSPath_v1.docx TP-LRN-06 / NFR-P02; backend/docs/fe-main-flow-guide.md; assessment: project-review judgement, not measured incidence. ¦ Assessment qualitative; owner and mitigation due date proposed.
R-004 | RabbitMQ retries or result replay produces stale or duplicate learning progress. | Technical | Medium | High | 6 | Test consumer version/idempotency, ACK-after-commit, retry and DLQ with real infrastructure. | Investigate failed events and replay through the existing idempotent consumer. | HieuLT | 2026-10-21 | Open | capstone-docs/rp_5.0_test_plan/Report 5.0_TestPlan_IELTSPath_v1.docx TP-LRN-05 / NFR-REL01; assessment: project-review judgement, not measured incidence. ¦ Assessment qualitative; owner and mitigation due date proposed.
R-005 | Protected content or answers are exposed through role, ownership or route mistakes. | Security | Medium | High | 6 | Run JWT, ownership, /internal route and answer-redaction cases through Gateway. | Block affected flow and fix authorization before acceptance. | PhuPD | 2026-10-21 | Open | capstone-docs/rp_5.0_test_plan/Report 5.0_TestPlan_IELTSPath_v1.docx NFR-SEC01 / TP-LRN-02; assessment: project-review judgement, not measured incidence. ¦ Assessment qualitative; owner and mitigation due date proposed.
R-006 | Missing media or question-pool data blocks a demo or remediation path. | Resource | Medium | High | 6 | Prepare validated audio URLs and unrevealed Practice/review packages before each cycle. | Use another real published package or document the blocked scenario. | TungVPH | 2026-10-21 | Open | backend/docs/fe-main-flow-guide.md; capstone-docs/rp_5.0_test_plan/Report 5.0_TestPlan_IELTSPath_v1.docx Data constraints; assessment: project-review judgement, not measured incidence. ¦ Assessment qualitative; owner and mitigation due date proposed.
R-007 | Docker or environment drift causes skipped integration tests to be reported as passes. | Technical | Medium | High | 6 | Record commits/config and Docker readiness; separate Passed, Skipped and Not Run. | Restore documented environment and rerun required integration tests. | TungVPH | 2026-10-21 | Open | capstone-docs/rp_5.0_test_plan/Report 5.0_TestPlan_IELTSPath_v1.docx NFR-OPS01; backend/plans/261006-2228-course-band-levels/plan.md verification; assessment: project-review judgement, not measured incidence. ¦ Assessment qualitative; owner and mitigation due date proposed.
R-008 | Insufficient browser coverage allows blocked controls or inaccessible feedback to escape. | Quality | Medium | Medium | 4 | Run fresh-user UI, keyboard, viewport and screen-reader checks on core screens. | Prioritize blocking usability fixes and rerun the affected flow. | SonLT | 2026-10-21 | Open | frontend/plans/reports/e2e-main-flow-261005-fresh/report.md; frontend/plans/reports/e2e-main-flow-261005/report.md; assessment: project-review judgement, not measured incidence. ¦ Assessment qualitative; owner and mitigation due date proposed.
R-009 | A key team member becomes unavailable before Phase 1 review. | Resource | Low | High | 3 | Document service contracts and share setup knowledge across the team. | PM reassigns remaining work and negotiates review schedule. | HieuLT | 2026-10-16 | Open | Original Risks R-002 adapted to Phase 1; no actual absence recorded.; assessment: project-review judgement, not measured incidence. ¦ Assessment qualitative; owner and mitigation due date proposed.
R-010 | Performance and operational targets are assumed from functional smoke results. | Quality | Medium | Medium | 4 | Agree test workload and measure non-LLM latency separately from provider latency. | Record unmet targets and obtain a scoped acceptance decision. | TungVPH | 2026-10-21 | Open | capstone-docs/rp_5.0_test_plan/Report 5.0_TestPlan_IELTSPath_v1.docx NFR-P01/P02; SRS Part 6; assessment: project-review judgement, not measured incidence. ¦ Assessment qualitative; owner and mitigation due date proposed.
R-011 | A paid release uses UI premium flags without server entitlement enforcement. | Security | Medium | High | 6 | Resolve I-006 before accepting paid premium access. | Limit Phase 1 demo to explicitly free content. | HieuLT | 2026-10-21 | Open | backend/docs/fe-main-flow-guide.md §6; assessment: project-review judgement, not measured incidence. ¦ Assessment qualitative; owner and mitigation due date proposed.

## ChangeLog
ChangeLog — IELTSPath Phase 1
Log ALL changes to requirements, design, or scope · No mid-sprint changes without approval · Reference this log when versions of SRS/SDS increment
# | Date | Change Description | Requested By | Affects (SRS/WBS/Code) | Impact on Scope | Impact on Effort (pds) | Impact on Timeline | Priority | Approved By | Status | Notes
C-001 | 2026-09-22 | Change auth transport to support HttpOnly cookies while retaining request-body refresh compatibility. | Not recorded | Auth API / FE session contract / security configuration; WBS-056/069 | Changes login/refresh/logout token delivery. Baseline setup itself stays in TimeLogs. | 1 | Implemented in Git; no substantiated schedule change. | High |  | Implemented | backend 2c9d37f; TimeLogs TL-014. Recorded date comes from Git/docs, not an approval date. Measured effort delta and formal approver unavailable. ¦ Effort is a reconstructed incremental estimate (1 person-day = 8 hours), not measured delta. Formal change approval unrecorded; technical implementation is not approval.
C-002 | 2026-10-01 | Change service ownership: separate Library from Content, move activity/streak to User and retire Learning Support. | Repository architecture plan; requester unconfirmed | TDS / service boundaries / databases / Gateway routes; WBS-071 | Redistributes existing capabilities across bounded contexts. | 3 | Migration and routing work required; no approved time delta supplied. | High |  | Implemented | backend 465f543, d762660, fec5d14, ab613b1; 4350505 records catalog-migration approval specifically. TimeLogs TL-029. Recorded date comes from Git/docs, not an approval date. Measured effort delta and formal approver unavailable. ¦ Effort is a reconstructed incremental estimate (1 person-day = 8 hours), not measured delta. Formal change approval unrecorded; technical implementation is not approval.
C-003 | 2026-10-01 | Replace Python AI Learning runtime with Java Learning Service. | Runtime-replacement plan; requester unconfirmed | Architecture / deployment / learning persistence and APIs; WBS-070 | Retires the historical Python runtime and ports the core learning flow to Java. | 4 | Historical prototype work remains in TimeLogs; no reliable schedule delta. | High |  | Implemented | backend 746e7dc plan, d96ab9e skeleton, 23904e8 retirement docs. TimeLogs TL-022, TL-031, TL-027. Recorded date comes from Git/docs, not an approval date. Measured effort delta and formal approver unavailable. ¦ Effort is a reconstructed incremental estimate (1 person-day = 8 hours), not measured delta. Formal change approval unrecorded; technical implementation is not approval.
C-004 | 2026-10-01 | Extend lesson contract with ESSAY blocks and Writing submissions with LLM grading and points. | Writing contract/roadmap; requester unconfirmed | SRS / lesson contract / Content / Learning / Access; WBS-057/070 | Adds essay-answer semantics, Writing rubric grading, quota and point-charge/retry rules. | 2 | Requires implementation and acceptance across services; hours/delay not inferred. | High |  | Implemented | backend 4fc7be6 contract, f2dfc72 contract approval record, d08337a implementation. TimeLogs TL-028, TL-032. Approval source applies only to that contract. Recorded date comes from Git/docs, not an approval date. Measured effort delta and formal approver unavailable. ¦ Effort is a reconstructed incremental estimate (1 person-day = 8 hours), not measured delta. Formal change approval unrecorded; technical implementation is not approval.
C-005 | 2026-10-03 | Change progression rules to skill-local gates, required lesson Practice and theory/remediation review without revealed-package reuse. | Skill-tracks plan; requester unconfirmed | SRS / Content ownership rules / Learning gates / FE workflow; WBS-012/014/057 | Lesson completion alone no longer unlocks final tests. Reviews are scoped by skill and unrevealed evidence rules. | 2 | BE recorded 03/10; FE followed 05/10. No measured delay asserted. | High |  | Implemented | backend a3447b9, 853ab82, 1a96c77, 8bb72cf, 6d9f623; frontend 6716dd9. TimeLogs TL-034, TL-036. Recorded date comes from Git/docs, not an approval date. Measured effort delta and formal approver unavailable. ¦ Effort is a reconstructed incremental estimate (1 person-day = 8 hours), not measured delta. Formal change approval unrecorded; technical implementation is not approval.
C-006 | 2026-10-07 | Add band-level courses, optional placement recommendations and a non-blocking course final test. | Mentor/product-owner decisions recorded in course plan | SRS / TDS / Content / Learning / Assessment contracts; FT-55, WBS-072/073 | Courses group ordered topics by band; recommendation does not lock access. FE integration/Phase 1 allocation unconfirmed. | 3 | BE implemented 07/10; FE follow-up proposed 08–21/10 within Iteration 2. No historical delay measured. | High |  | Implemented | backend d867758, 559bf82, a401a33, 5ea098a; merge df6c57f (#45); backend/plans/261006-2228-course-band-levels/plan.md decisions. TimeLogs TL-040, TL-041. Recorded date comes from Git/docs, not an approval date. Measured effort delta and formal approver unavailable. ¦ Effort is a reconstructed incremental estimate (1 person-day = 8 hours), not measured delta. Formal change approval unrecorded; technical implementation is not approval.
C-007 | 2026-10-07 | Revise Vision & Scope to reflect mentor feedback and the full product feature set. | Mentor feedback recorded in Report 1 history | Report 1 / SRS traceability / phase allocation; WBS-065/077 | Full product scope includes future features. This document revision does not prove their implementation or Phase 1 acceptance. | 1 | Reconcile phase baseline before approval. | High |  | In Review | Report 1 v1.1.0 dated 07/10/2026; backend 36b1092 records the supporting BA/vision review. TimeLogs TL-037. Recorded date comes from Git/docs, not an approval date. Measured effort delta and formal approver unavailable. ¦ Effort is a reconstructed incremental estimate (1 person-day = 8 hours), not measured delta. Formal change approval unrecorded; technical implementation is not approval.
C-008 | 2026-10-07 | Implement mixed-skill lesson/Practice contracts and free assessment AI essay grading with human fallback. | Multi-skill plan; formal requester/approver unconfirmed | Content / Learning / Assessment contracts and planned SRS changes; WBS-074/075/060 | Backend change merged; FE contract alignment remains separate. Speaking excluded; Writing Practice optional, objective skills gate completion; assessment essay uses passBand and no point debit. | 3 | BE merged 07/10; FE follow-up proposed 08–21/10 within Iteration 2. No measured slip asserted. | High |  | Implemented | BE 8d2d2bb (#47), 51468f60 and plans/261006-2309-multi-skill-lessons/plan.md verification. Supersedes V1 stale Pending. Implemented means backend scope only; FE/live-provider acceptance open. Incremental effort 3 person-days is estimated, not actual. Formal approver unrecorded.